## User Manual
User Manual
1. Purpose of This Tool
This workbook is used to perform:
*Building handover and delivery inspections
*Facilities Management (FM) performance audits
*Asset condition, compliance, and operational readiness assessments
It is a structured, weighted, and auditable checklist designed for professional and government use
2. Who Should Use This Handbook
This handbook is intended for:
*Inspectors
*Engineers
*Auditors
*FM Supervisors
*Consultants
3. Sheets Description
| Executive Assessment Summary | Summarizes the overall building condition, key risks, and final acceptance status.
| Government Compliance Checklist | Confirms compliance with applicable government regulations and approvals.
| Building Assessment | Assesses the technical condition and performance of building systems.
| Test Register | Logs all inspections and tests performed and their outcomes.
| CAPA Register | Tracks corrective actions, responsibilities, and closure status.
4. How to Perform an Inspection
1. Complete project information in Executive Assessment Summary Sheet
2. Review the weigh in the Executive Assessment Summary Sheet
3. Review the weight in the Building Assessment Sheet
4. Review the Risk Criticality and priority in Building Assessment sheet.
5. Inspect each inspection item under your system and fill all the required fields in the Building Assessment Sheet
6. Review results in the Executive Assessment Summary Sheet
7. Submit the final report to the Advisory team for review
5. Guideline
| Rating Scale |  | Risk Criticality
| Rating | Meaning | Risk | Meaning
| 5 | Excellent – Fully compliant | 5 | Critical - Severe safety or compliance risk
| 4 | Good – Minor observations | 4 | High - Significant safety or operational concern
| 3 | Fair – Acceptable | 3 | Medium - Moderate operational or maintenance risk
| 2 | Poor – Non-compliant | 2 | Low - Minor defect with limited impact
| 1 | Critical – Unacceptable | 1 | Observation - Non-critical finding
| 0 | Not Applicable | 0 | Not Applicable
Priority Levels
| Priority | Meaning
| P1 | Critical / Safety risk
| P2 | High
| P3 | Medium
| P4 | Low
| What Assessors Must Do |  | What Assessors Must NOT Do
| ✓ Test each line item |  | ❌ Do not edit formulas
| ✓ Fill all the required fields in the Building Assessment Sheet |  | ❌ Do not rename sheets
✓ Register all tests in the Test Register Sheet
✓ Fill the corrective and Preventive data in CAPA Register sheet
✓ Fill all data in the Government Compliance Checklist sheet
✓ Review the whole report with your administrator

## Executive Assessment Summary
Assessment Summary |  |  | Executive Assessment Summary
Project Information
|  | Please fill the details |  |  | Please fill the details
| Project / Building Name | ****** |  | Building Type | REINFORCED CONCRETE (RC)
| City | Riyadh |  | Primary Use | ADMIN
| Address | ****** |  | Gross Bulit Area (m²) | 50000
| GPS Coordinates (Lat, Long) | ****** |  | No. of Floors | 22
|  | Please fill the details |  |  | Please fill the details
| Last Major Renovation Date | 1905-07-17 |  | Estimated Life Time | 50
| FM Contractor / Service Provider | ***** |  | Planned Asset Retirement Year | 2058
| Current Year | 2025 |  | System Threshold (%) | 71%
| Construction Year | 2008 |  | Inspection Date | 2025-12-08
| Fail | 64.3% | 183 | 61.15% | Not Complied
| Inspection Result | Building Score | High Priority Classificated | FM Performance | Government Compliance
| 53.51% | 50 | 17 | 17.849 | 32.151
| Fire & Life Safety | Total economic life | Chronological (Actual) Age | Estimated Effective Age | Estimated Remaining life
Notes:
1- The building failed to meet the minimum acceptance criteria and is not approved for handover and/or operation until all deficiencies are rectified and verified.
2- One or more mandatory government compliance documents were unavailable or incomplete at the time of inspection; accordingly, handover and/or operational approval remains conditional pending submission and acceptance of the required documentation.
3- The inspection identified priority items that require corrective action and follow-up.
Systems Performance
| System | Item Count | Score % | Weight | Weighted Score
| Fire_LifeSafety | 35 | 53.51% | 17 | 9.097%
| Electrical | 30 | 73.29% | 10 | 7.329%
| Emergency_Power | 5 | 76% | 2 | 1.52%
| Mechanical_HVAC | 35 | 60.14% | 9 | 5.412%
| Plumbing_Water | 35 | 68.79% | 8 | 5.504%
| Gas_Systems | 35 | 69.21% | 2 | 1.384%
| Vertical_Transportation | 35 | 78.66% | 5 | 3.933%
| BMS_Controls | 35 | 62.51% | 6 | 3.751%
| ELV_Systems | 28 | 63.05% | 3 | 1.891%
| Security_Safety | 35 | 67.2% | 3 | 2.016%
| Digital_ICT | 35 | 63.68% | 2 | 1.274%
| Structural | 35 | 68.9% | 4 | 2.756%
| Architectural_Fabric | 35 | 64.06% | 2 | 1.281%
| External_Parking | 35 | 65.78% | 1 | 0.6578%
| Landscape | 35 | 64.06% | 1 | 0.6406%
| Pools_WaterFeatures | 35 | 61.2% | 1 | 0.612%
| Waste_Management | 35 | 65.21% | 2 | 1.304%
| Sustainability | 35 | 60.63% | 1 | 0.6063%
| Compliance_Documentation | 35 | 61.25% | 12 | 7.35%
| FM_Performance | 35 | 61.15% | 2 | 1.223%
| Governance_Readiness | 36 | 68% | 7 | 4.76%
| Total Inspected Items | 694 | Total Weight | 100 | 64.3%
This inspection was undertaken as a non-intrusive, visual, and advisory condition assessment based on information available and accessible at the time of inspection. The assessment does not constitute a statutory inspection, certification, commissioning, or authority approval, and does not replace inspections, tests, or certifications required by Civil Defense, municipalities, or other regulatory authorities.The scope of this assessment does not include detailed performance testing, commissioning, or compliance certification of life safety systems, including but not limited to fire-fighting systems, fire alarm systems, elevators, escalators, or other regulated systems, unless explicitly stated otherwise within the agreed scope of services. All findings, observations, and conclusions are limited to the apparent condition observed on the inspection date and are provided for decision-support purposes only. No express or implied warranty, guarantee, or representation is made regarding the future performance, compliance, or continued condition of the building or its systems. Dar Al Riyadh shall not be liable for any deterioration, failure, incident, non-compliance, or loss arising after the inspection date, or resulting from hidden defects, operational practices, maintenance deficiencies, design limitations, third-party actions, environmental conditions, or changes in regulatory requirements. Responsibility for regulatory compliance, operational safety, statutory approvals, and ongoing maintenance remains solely with the owner, operator, and/or appointed facility management entity.

## Government Compliance Checklist
Government Compliance Checklist | Area | Requirement | Status (Please Select from the list) | Evidence Required | Item Code | Evidence Ref | Remarks
| Legal & Municipal Approvals | Building Completion Certificate (Final) | Yes | Certificate copy with date & stamp | GC-LA-001
| Legal & Municipal Approvals | Occupancy License / Operational Permit | Yes | Valid license with classification | GC-LA-002
| Legal & Municipal Approvals | Valid Building Permit (Administrative Use) | No | Permit with all conditions met | GC-LA-003
| Legal & Municipal Approvals | National Address Registration (SPL) | Yes | Registration document with QR code | GC-LA-004
| Legal & Municipal Approvals | SBC Compliance Review Completion | Yes | Signed compliance checklist | GC-LA-005
| Legal & Municipal Approvals | Civil Defense Approval (Fire & Life Safety) | Yes | Valid certificate with expiry date | GC-LA-006
| Utility Connections | Electricity Connection Certificate (Active – SEC) | Yes | Connection contract & active account number | GC-UC-001
| Utility Connections | Water & Sewerage Connection (Active – NWC) | Yes | Connection contract & active account number | GC-UC-002
| Utility Connections | Waste Management Contract | Yes | Signed contract with collection schedule | GC-UC-004
| Safety Certificates | Elevator Inspection Certificate (Annual) | No | Current inspection certificate | GC-SC-001
| Documentation | Complete As-Built Drawing Set (All Disciplines) | Yes | Architectural, Structural, MEP, Fire, Security | GC-DC-001
| Documentation | Complete O&M Manuals (All Systems, Indexed) | No | OEM manuals + system operation guides | GC-DC-002
| Documentation | Commissioning Reports (All Systems, Signed) | Yes | Final reports with authority signatures | GC-DC-003
| Documentation | Test Certificates Complete Set | Yes | Electrical, Mechanical, Fire, Plumbing | GC-DC-004
| Documentation | Warranty Certificates (All Equipment) | Yes | Warranties with start dates & coverage | GC-DC-005
| Documentation | Asset Register (Complete with IDs) | Yes | Digital register with serial numbers, locations | GC-DC-006
| Documentation | Spare Parts Inventory (Critical Items) | Yes | Inventory list with storage location & quantities | GC-DC-007
| Documentation | Fire Strategy & Authority-Approved Drawings | Yes | Strategy document matching as-built | GC-DC-008
| Operational Readiness | FM Team Training Complete (All Systems) | Partial | Training records & certificates | GC-OR-001
| Operational Readiness | Critical Spare Parts On-Site & Verified | Yes | Inventory list with storage location | GC-OR-002
| Operational Readiness | CMMS/CAFM Configured & Populated | Yes | System demonstration with all assets loaded | GC-OR-003
| Operational Readiness | Maintenance Contracts in Place (All Systems) | Yes | Signed contracts with SLAs & response times | GC-OR-004
| Operational Readiness | Emergency Response Plan Approved | No | Approved plan with contact lists & procedures | GC-OR-005
| Operational Readiness | Fire Drill Conducted & Documented (First) | Yes | Drill report with observations & improvements | GC-OR-006
| Operational Readiness | BMS Points List & Access Available | Yes | Admin accounts & backup access confirmed | GC-OR-007
| Operational Readiness | Cleaning/Housekeeping Services Ready | Yes | Contract & staffing confirmed | GC-OR-009
| Governance & Authorization | Owner/Government Approval to Operate | Yes | Formal authorization letter | GC-GV-001
| Governance & Authorization | Defects Liability Period Agreement Signed | Yes | Signed agreement with defect schedule & period | GC-GV-006
| Compliance - Health & Safety | Public Health & Ventilation Compliance (Admin Use) | Yes | Inspection report/certificate | GC-HS-001
| Compliance - Health & Safety | Risk Register & HSE Compliance | Yes | Approved risk register & mitigation plan | GC-HS-003
| Compliance - Health & Safety | Training Records (HSE, Fire, Emergency) | N/A | FM & security staff certificates | GC-HS-004
| Environmental & Sustainability | Energy Efficiency Baseline Established | N/A | Baseline report with meter list | GC-EC-005

## Lists (hidden)
Priority | Status | Responsibility | EvidenceType | Rate/Weight | Status | Year | Estimated Life Time | System Threshold (%) | PRIMARY USE | Type | Test Method Categories
P1 | Open | MEP Contractor | Photo | 0 | Yes | 1900 | 0 | 50% | RESIDENTIAL | LOAD-BEARING MASONRY | Visual Inspection
P2 | In Progress | Main Contractor | Video | 1 | No | 1901 | 1 | 51% | COMMERCIAL | STEEL FRAME | Functional Test
P3 | Closed | FM Contractor | Test Report | 2 | Partial | 1902 | 2 | 52% | INDUSTRIAL | REINFORCED CONCRETE (RC) | Pressure/Flow Measurement
P4 | Verified | Specialist Vendor | IR Scan | 3 | N/A | 1903 | 3 | 53% | INSTITUTIONAL / PUBLIC | TIMBER/ WOOD FRAME | Electrical Testing
| N/A | Client/Owner | Certificate | 4 |  | 1904 | 4 | 54% | INFRASTRUCTURAL | PRECAST/ PREFABRICATED | Water/Plumbing Testing
|  |  | Inspector | 5 |  | 1905 | 5 | 55% | AGRICULTURAL | COMPOSITE | Fire Safety Testing
[6 empty] | 1906 | 6 | 56% | ADMIN |  | Structural Testing
System | Subsystem | Component |  |  |  | 1907 | 7 | 57% |  |  | HVAC Testing
Fire_LifeSafety | Fire Alarm | Fire Alarm Control Panel |  |  |  | 1908 | 8 | 58% |  |  | Calibration & Certification
Fire_LifeSafety | Fire Fighting | Detector |  |  |  | 1909 | 9 | 59% |  |  | Records & Documentation Review
Fire_LifeSafety | Smoke Control | Manual Call Point |  |  |  | 1910 | 10 | 60% |  |  | System Integration Testing
Fire_LifeSafety | Compartmentation | Sounder and Beacon |  |  |  | 1911 | 11 | 61% |  |  | Performance & Efficiency Analysis
Fire_LifeSafety | Emergency Lighting | Voice Evacuation System |  |  |  | 1912 | 12 | 62% |  |  | Environmental & Compliance Audit
Fire_LifeSafety | Interfaces | Fire Pump |  |  |  | 1913 | 13 | 63% |  |  | Specialist/Third-Party Reports
Fire_LifeSafety | Documentation | Jockey Pump |  |  |  | 1914 | 14 | 64% |  |  | Operational Procedure Verification
Fire_LifeSafety | Training | Sprinkler System |  |  |  | 1915 | 15 | 65% |  |  | Other
Fire_LifeSafety | Records | Hydrant / Hose Reel |  |  |  | 1916 | 16 | 66%
Fire_LifeSafety |  | Fire Extinguisher |  |  |  | 1917 | 17 | 67%
Fire_LifeSafety |  | Clean Agent System |  |  |  | 1918 | 18 | 68%
Fire_LifeSafety |  | Smoke Extract Fan |  |  |  | 1919 | 19 | 69%
Fire_LifeSafety |  | Pressurization Fan |  |  |  | 1920 | 20 | 70%
Fire_LifeSafety |  | Fire / Smoke Damper |  |  |  | 1921 | 21 | 71%
Fire_LifeSafety |  | Fire Door |  |  |  | 1922 | 22 | 72%
Fire_LifeSafety |  | Fire Curtain |  |  |  | 1923 | 23 | 73%
Fire_LifeSafety |  | Firestopping System |  |  |  | 1924 | 24 | 74%
Fire_LifeSafety |  | Emergency Light |  |  |  | 1925 | 25 | 75%
Fire_LifeSafety |  | Exit Sign |  |  |  | 1926 | 26 | 76%
Fire_LifeSafety |  | Central Battery System |  |  |  | 1927 | 27 | 77%
Fire_LifeSafety |  | Elevator Recall Interface |  |  |  | 1928 | 28 | 78%
Fire_LifeSafety |  | Access Control Fire Release |  |  |  | 1929 | 29 | 79%
Fire_LifeSafety |  | BMS Interface |  |  |  | 1930 | 30 | 80%
Fire_LifeSafety |  | HVAC Shutdown Interface |  |  |  | 1931 | 31 | 81%
Fire_LifeSafety |  | Civil Defense Certification |  |  |  | 1932 | 32 | 82%
Fire_LifeSafety |  | Fire Strategy Drawings |  |  |  | 1933 | 33 | 83%
Fire_LifeSafety |  | Fire System Test Certificates |  |  |  | 1934 | 34 | 84%
Fire_LifeSafety |  | Fire Panel Operator Training |  |  |  | 1935 | 35 | 85%
Fire_LifeSafety |  | Fire Pump Monthly Run Records |  |  |  | 1936 | 36 | 86%
Fire_LifeSafety |  | Fire Door Inspection Log |  |  |  | 1937 | 37 | 87%
Fire_LifeSafety |  | Smoke Control Sequences Record |  |  |  | 1938 | 38 | 88%
Fire_LifeSafety |  | Fire Drill Records |  |  |  | 1939 | 39 | 89%
Electrical | Power Distribution | Main LV Switchboard |  |  |  | 1940 | 40 | 90%
Electrical | Protection & Earthing | Distribution Board |  |  |  | 1941 | 41 | 91%
Electrical | Metering & PQ | Cable Containment |  |  |  | 1942 | 42 | 92%
Electrical | Lighting | Earthing System |  |  |  | 1943 | 43 | 93%
Electrical | Rooms | Bonding System |  |  |  | 1944 | 44 | 94%
Electrical | Interfaces | Protection Relay / Breaker |  |  |  | 1945 | 45 | 95%
Electrical | Documentation | RCD / ELCB |  |  |  | 1946 | 46 | 96%
Electrical | Spares & Safety | Surge Protection Device |  |  |  | 1947 | 47 | 97%
Electrical | Housekeeping | Power / Energy Meter |  |  |  | 1948 | 48 | 98%
Electrical |  | Harmonic Filter |  |  |  | 1949 | 49 | 99%
Electrical |  | Internal Lighting |  |  |  | 1950 | 50 | 100%
Electrical |  | External Lighting |  |  |  | 1951 | 51
Electrical |  | Electrical Room |  |  |  | 1952 | 52
Electrical |  | BMS / SCADA Electrical Interface |  |  |  | 1953 | 53
Electrical |  | Electrical As‑Built Drawings |  |  |  | 1954 | 54
Electrical |  | Electrical Test Certificates |  |  |  | 1955 | 55
Electrical |  | Spare Breakers / Fuses |  |  |  | 1956 | 56
Electrical |  | Safety Signage & PPE |  |  |  | 1957 | 57
Electrical |  | Clearances & Housekeeping |  |  |  | 1958 | 58
Emergency_Power | Generation | Diesel Generator |  |  |  | 1959 | 59
Emergency_Power | Transfer | Fuel System |  |  |  | 1960 | 60
Emergency_Power | Distribution | Automatic Transfer Switch |  |  |  | 1961 | 61
Emergency_Power | Storage | Emergency Distribution Board |  |  |  | 1962 | 62
Emergency_Power | Resilience | UPS System |  |  |  | 1963 | 63
Emergency_Power |  | Battery Bank |  |  |  | 1964 | 64
Emergency_Power |  | Redundancy / Single Point Review |  |  |  | 1965 | 65
Mechanical_HVAC | Central Plant | Chiller |  |  |  | 1966 | 66
Mechanical_HVAC | Air Handling | Cooling Tower |  |  |  | 1967 | 67
Mechanical_HVAC | Air Distribution | Chilled / Condenser Water Pump |  |  |  | 1968 | 68
Mechanical_HVAC | Ventilation | Air Handling Unit |  |  |  | 1969 | 69
Mechanical_HVAC | Hydronic System | Fan Coil Unit |  |  |  | 1970 | 70
Mechanical_HVAC | Controls & BMS | Ductwork |  |  |  | 1971 | 71
Mechanical_HVAC | Water Treatment | Volume / Fire Damper |  |  |  | 1972 | 72
Mechanical_HVAC | DX / VRF | VAV Box |  |  |  | 1973 | 73
Mechanical_HVAC |  | Grille / Diffuser |  |  |  | 1974 | 74
Mechanical_HVAC |  | Exhaust / Fresh Air Fan |  |  |  | 1975 | 75
Mechanical_HVAC |  | Pipework |  |  |  | 1976 | 76
Mechanical_HVAC |  | Valve |  |  |  | 1977 | 77
Mechanical_HVAC |  | Strainer |  |  |  | 1978 | 78
Mechanical_HVAC |  | Expansion Tank |  |  |  | 1979 | 79
Mechanical_HVAC |  | DDC Controller |  |  |  | 1980 | 80
Mechanical_HVAC |  | Sensor |  |  |  | 1981 | 81
Mechanical_HVAC |  | Actuator |  |  |  | 1982 | 82
Mechanical_HVAC |  | BMS Interface Panel |  |  |  | 1983 | 83
Mechanical_HVAC |  | Chemical Dosing System |  |  |  | 1984 | 84
Mechanical_HVAC |  | Refrigerant Piping |  |  |  | 1985 | 85
Plumbing_Water | Water Supply | Water Storage Tank |  |  |  | 1986 | 86
Plumbing_Water | Distribution | Booster Pump |  |  |  | 1987 | 87
Plumbing_Water | Fixtures | Water Meter |  |  |  | 1988 | 88
Plumbing_Water | Sanitary Drainage | Cold Water Pipework |  |  |  | 1989 | 89
Plumbing_Water | Hot Water | Isolation Valve |  |  |  | 1990 | 90
Plumbing_Water | Backflow Prevention | Pressure Reducing Valve |  |  |  | 1991 | 91
Plumbing_Water | Stormwater | Plumbing Fixture |  |  |  | 1992 | 92
Plumbing_Water | Greywater Reuse | Drain Pipe |  |  |  | 1993 | 93
Plumbing_Water | Leak Detection | Manhole |  |  |  | 1994 | 94
Plumbing_Water |  | Grease Trap |  |  |  | 1995 | 95
Plumbing_Water |  | Water Heater |  |  |  | 1996 | 96
Plumbing_Water |  | Thermostatic Mixing Valve |  |  |  | 1997 | 97
Plumbing_Water |  | Hot Water Circulation Pump |  |  |  | 1998 | 98
Plumbing_Water |  | Backflow Preventer |  |  |  | 1999 | 99
Plumbing_Water |  | Sump Pump |  |  |  | 2000 | 100
Plumbing_Water |  | Stormwater Pit |  |  |  | 2001 | 101
Plumbing_Water |  | Greywater Treatment Unit |  |  |  | 2002 | 102
Plumbing_Water |  | Recycled Water Tank |  |  |  | 2003 | 103
Plumbing_Water |  | Leak Detector |  |  |  | 2004 | 104
Gas_Systems | Distribution | Gas Meter |  |  |  | 2005 | 105
Gas_Systems | Safety | Gas Piping |  |  |  | 2006 | 106
Gas_Systems | Appliances | Isolation Valve |  |  |  | 2007 | 107
Gas_Systems |  | Gas Detector |  |  |  | 2008 | 108
Gas_Systems |  | Emergency Shutoff Valve |  |  |  | 2009 | 109
Gas_Systems |  | Boiler |  |  |  | 2010 | 110
Gas_Systems |  | Kitchen Equipment |  |  |  | 2011 | 111
Vertical_Transportation | Elevators | Elevator (Passenger / Service) |  |  |  | 2012 | 112
Vertical_Transportation | Escalators | Elevator Controller |  |  |  | 2013 | 113
Vertical_Transportation |  | Door Operator |  |  |  | 2014 | 114
Vertical_Transportation |  | Safety Devices (Governor / Brake) |  |  |  | 2015 | 115
Vertical_Transportation |  | Emergency Intercom |  |  |  | 2016 | 116
Vertical_Transportation |  | Machine Room Equipment |  |  |  | 2017 | 117
Vertical_Transportation |  | Pit Equipment |  |  |  | 2018 | 118
Vertical_Transportation |  | Traveling Cable |  |  |  | 2019 | 119
Vertical_Transportation |  | Escalator / Moving Walkway |  |  |  | 2020 | 120
Vertical_Transportation |  | Drive Motor |  |  |  | 2021 | 121
Vertical_Transportation |  | Handrail |  |  |  | 2022 | 122
Vertical_Transportation |  | Emergency Stop |  |  |  | 2023 | 123
Vertical_Transportation |  | Comb Plate |  |  |  | 2024 | 124
BMS_Controls | Central System | BMS Server |  |  |  | 2025 | 125
BMS_Controls | Field Devices | BMS Workstation |  |  |  | 2026 | 126
BMS_Controls | Control Logic | Network Switch |  |  |  | 2027 | 127
BMS_Controls | Alarms & Trends | BMS UPS |  |  |  | 2028 | 128
BMS_Controls | Integration | DDC Controller |  |  |  | 2029 | 129
BMS_Controls | Cybersecurity | Sensor |  |  |  | 2030 | 130
BMS_Controls |  | Actuator |  |  |  | 2031 | 131
BMS_Controls |  | Control Sequence |  |  |  | 2032 | 132
BMS_Controls |  | Time Schedule |  |  |  | 2033 | 133
BMS_Controls |  | Alarm Configuration |  |  |  | 2034 | 134
BMS_Controls |  | Trend Database |  |  |  | 2035 | 135
BMS_Controls |  | Fire Alarm Interface |  |  |  | 2036 | 136
BMS_Controls |  | HVAC Interface |  |  |  | 2037 | 137
BMS_Controls |  | Lighting Interface |  |  |  | 2038 | 138
BMS_Controls |  | Power Meter Interface |  |  |  | 2039 | 139
BMS_Controls |  | User Access Control |  |  |  | 2040 | 140
BMS_Controls |  | Network Segmentation |  |  |  | 2041 | 141
BMS_Controls |  | Password Policy |  |  |  | 2042 | 142
ELV_Systems | Time Systems | Master Clock |  |  |  | 2043 | 143
ELV_Systems | SATV / IPTV | Time Synchronization System |  |  |  | 2044 | 144
ELV_Systems | Building Automation | Headend System |  |  |  | 2045 | 145
ELV_Systems | Energy Management | Receiver / Decoder |  |  |  | 2046 | 146
ELV_Systems | Public Address | Gateway |  |  |  | 2047 | 147
ELV_Systems | Audio Visual | Integration Server |  |  |  | 2048 | 148
ELV_Systems | Digital Signage | Submetering System |  |  |  | 2049 | 149
ELV_Systems | Nurse Call | Energy Dashboard |  |  |  | 2050 | 150
ELV_Systems | Intercom | PA Control Console |  |  |  | 2051 | 151
ELV_Systems |  | Amplifier |  |  |  | 2052 | 152
ELV_Systems |  | Speaker |  |  |  | 2053 | 153
ELV_Systems |  | Projector |  |  |  | 2054 | 154
ELV_Systems |  | Display Screen |  |  |  | 2055 | 155
ELV_Systems |  | AV Control System |  |  |  | 2056 | 156
ELV_Systems |  | Digital Signage Player |  |  |  | 2057 | 157
ELV_Systems |  | Digital Display |  |  |  | 2058 | 158
ELV_Systems |  | Nurse Call Master Station |  |  |  | 2059 | 159
ELV_Systems |  | Patient / Staff Station |  |  |  | 2060 | 160
ELV_Systems |  | System Controller |  |  |  | 2061 | 161
ELV_Systems |  | Intercom Station |  |  |  | 2062 | 162
Security_Safety | CCTV | Camera |  |  |  | 2063 | 163
Security_Safety | Access Control | Network Video Recorder |  |  |  | 2064 | 164
Security_Safety | Intrusion Detection | Video Management System |  |  |  | 2065 | 165
Security_Safety | Control Room | Video Wall |  |  |  | 2066 | 166
Security_Safety | Key Management | Card / Biometric Reader |  |  |  | 2067 | 167
Security_Safety | Perimeter Security | Door Controller |  |  |  | 2068 | 168
Security_Safety |  | Electromagnetic Lock |  |  |  | 2069 | 169
Security_Safety |  | PIR / Glass Break Detector |  |  |  | 2070 | 170
Security_Safety |  | Intrusion Alarm Panel |  |  |  | 2071 | 171
Security_Safety |  | Control Console |  |  |  | 2072 | 172
Security_Safety |  | Monitoring System |  |  |  | 2073 | 173
Security_Safety |  | Key Cabinet / Tracking |  |  |  | 2074 | 174
Security_Safety |  | Fence / Bollard |  |  |  | 2075 | 175
Digital_ICT | LAN | Network Switch |  |  |  | 2076 | 176
Digital_ICT | WiFi | Router |  |  |  | 2077 | 177
Digital_ICT | Structured Cabling | Firewall |  |  |  | 2078 | 178
Digital_ICT | Server Room | Access Point |  |  |  | 2079 | 179
Digital_ICT | Telephony | Wireless Controller |  |  |  | 2080 | 180
Digital_ICT | Cybersecurity | Rack |  |  |  | 2081 | 181
Digital_ICT |  | Patch Panel |  |  |  | 2082 | 182
Digital_ICT |  | Cabling |  |  |  | 2083 | 183
Digital_ICT |  | Server |  |  |  | 2084 | 184
Digital_ICT |  | Storage Array |  |  |  | 2085 | 185
Digital_ICT |  | UPS System |  |  |  | 2086 | 186
Digital_ICT |  | Environmental Monitoring |  |  |  | 2087 | 187
Digital_ICT |  | Telephone System |  |  |  | 2088 | 188
Digital_ICT |  | VoIP Gateway |  |  |  | 2089 | 189
Digital_ICT |  | Antivirus / Antimalware |  |  |  | 2090 | 190
Digital_ICT |  | Patch Management |  |  |  | 2091 | 191
Digital_ICT |  | Backup System |  |  |  | 2092 | 192
Digital_ICT |  | Intrusion Detection System |  |  |  | 2093 | 193
Structural | Foundations | Foundation |  |  |  | 2094 | 194
Structural | Columns & Beams | Column |  |  |  | 2095 | 195
Structural | Slabs | Beam |  |  |  | 2096 | 196
Structural | Walls | Slab |  |  |  | 2097 | 197
Structural | Movement | Structural Wall |  |  |  | 2098 | 198
Structural | Waterproofing | Expansion Joint |  |  |  | 2099 | 199
Structural | Facade Structure | Control Joint |  |  |  | 2100 | 200
Structural | Retaining Structures | Waterproofing Membrane |  |  |  | 2101
Structural | Repair | Facade Anchor |  |  |  | 2102
Structural |  | Retaining Wall |  |  |  | 2103
Structural |  | Structural Repair Material |  |  |  | 2104
Architectural_Fabric | Internal Finishes | Tile / Paint / Gypsum / Wall Covering |  |  |  | 2105
Architectural_Fabric | Floors | Floor Finish |  |  |  | 2106
Architectural_Fabric | Ceilings | Ceiling Panel |  |  |  | 2107
Architectural_Fabric | Doors | Door Leaf |  |  |  | 2108
Architectural_Fabric | Windows | Door Hardware |  |  |  | 2109
Architectural_Fabric | Wet Areas | Window Frame / Glazing |  |  |  | 2110
Architectural_Fabric | Facade | Tile & Grout |  |  |  | 2111
Architectural_Fabric | Roof | Cladding / Facade Panel |  |  |  | 2112
Architectural_Fabric | Accessibility | Roofing Membrane / Insulation |  |  |  | 2113
Architectural_Fabric | Wayfinding | Ramp / Handrail |  |  |  | 2114
Architectural_Fabric | General Snagging | Signage |  |  |  | 2115
Architectural_Fabric |  | Skirting / Sealant |  |  |  | 2116
External_Parking | Pavement | Pavement / Markings |  |  |  | 2117
External_Parking | Drainage | Drain Inlet / Channel |  |  |  | 2118
External_Parking | Lighting | Light Pole / Flood Light |  |  |  | 2119
External_Parking | Barriers & Access | Barrier Gate / Traffic Arm / Bollard |  |  |  | 2120
External_Parking | Payment & Control | Payment Kiosk / Card Reader |  |  |  | 2121
External_Parking | CCTV | Camera |  |  |  | 2122
External_Parking | Ventilation | Ventilation Fan / CO Monitor |  |  |  | 2123
External_Parking | Perimeter | Fence / Gate |  |  |  | 2124
External_Parking | HSE | Safety Mirror / Speed Bump |  |  |  | 2125
Landscape | Irrigation | Sprinkler / Drip Line / Valve / Controller / Pump |  |  |  | 2126
Landscape | Planting | Tree / Shrub / Turf |  |  |  | 2127
Landscape | Soil & Mulch | Soil / Mulch |  |  |  | 2128
Landscape | Hardscape | Path Paver / Edging / Retaining Wall |  |  |  | 2129
Landscape | Lighting | Landscape Light Fixture |  |  |  | 2130
Landscape | Pest Control | Pest Control System |  |  |  | 2131
Landscape | Drainage | Drain Channel / French Drain |  |  |  | 2132
Landscape | Water Conservation | Soil Moisture Sensor |  |  |  | 2133
Pools_WaterFeatures | Filtration | Pool Pump / Filter |  |  |  | 2134
Pools_WaterFeatures | Chemical Treatment | Chlorinator / Dosing Pump / pH Controller |  |  |  | 2135
Pools_WaterFeatures | Heating | Heater / Heat Pump |  |  |  | 2136
Pools_WaterFeatures | Lighting | Pool Light |  |  |  | 2137
Pools_WaterFeatures | Safety | Safety Kit / Anti-slip Surface |  |  |  | 2138
Pools_WaterFeatures | Structure & Finishes | Pool Tile / Coping |  |  |  | 2139
Pools_WaterFeatures | Water Features | Feature Pump / Fountain Nozzle |  |  |  | 2140
Pools_WaterFeatures | Drainage | Drain Cover / Overflow Gutter |  |  |  | 2141
Pools_WaterFeatures | Controls | Pool Controller / Water Quality Sensor |  |  |  | 2142
Pools_WaterFeatures | Water Inlets | Skimmer / Inlet Fitting |  |  |  | 2143
Waste_Management | Infrastructure | Waste Room / Chute / Compactor / Baler / Bins |  |  |  | 2144
Waste_Management | HSE | Ventilation System / Pest Control System |  |  |  | 2145
Waste_Management | Hazardous Waste | Hazardous Waste Storage / Spill Kit |  |  |  | 2146
Sustainability | Energy | Energy Meter / Submeter |  |  |  | 2147
Sustainability | Water | Water Meter / Flow Restrictor |  |  |  | 2148
Sustainability | IAQ | Air Quality Monitor / CO2 Sensor |  |  |  | 2149
Sustainability | Envelope | Thermal Insulation / High Performance Glazing |  |  |  | 2150
Sustainability | Lighting | Efficient Light Fixture |  |  |  | 2151
Sustainability | Renewable Energy | Solar PV Panel / Inverter / Monitoring |  |  |  | 2152
Sustainability | EV Charging | EV Charging Station |  |  |  | 2153
Sustainability | BEMS | Building Energy Management System |  |  |  | 2154
Sustainability | ESG | Carbon Footprint Measurement / Energy Performance Report |  |  |  | 2155
Compliance_Documentation | Design | As-Built Drawings / O&M Manuals |  |  |  | 2156
Compliance_Documentation | Commissioning | Commissioning Report |  |  |  | 2157
Compliance_Documentation | Test Reports | Test Certificates |  |  |  | 2158
Compliance_Documentation | Warranties | Warranty Certificate |  |  |  | 2159
Compliance_Documentation | Asset Data | Asset Register / Spare Parts List |  |  |  | 2160
Compliance_Documentation | Contracts | Contract Documents |  |  |  | 2161
Compliance_Documentation | Permits | Licenses & Permits |  |  |  | 2162
FM_Performance | Maintenance | Preventive / Corrective Maintenance |  |  |  | 2163
FM_Performance | Resources | Staff Training Records |  |  |  | 2164
FM_Performance | Housekeeping | Cleaning Services |  |  |  | 2165
FM_Performance | CAFM / CMMS | System Utilization |  |  |  | 2166
FM_Performance | Vendor Management | Vendor Performance |  |  |  | 2167
FM_Performance | Cost Control | Cost Report |  |  |  | 2168
FM_Performance | Energy Management | Energy Audit |  |  |  | 2169
FM_Performance | Governance | KPI Reporting |  |  |  | 2170
Governance_Readiness | Integration | Fire‑BMS / Fire‑HVAC / Fire‑Security / Emergency Power / Elevator Recall / SPOF |  |  |  | 2171
Governance_Readiness | Operations | FM Staff Competency / Emergency Response Plan / Fire Drill Program / First Intervention / Control Room Procedures |  |  |  | 2172
Governance_Readiness | Lifecycle | Remaining Useful Life Assessment / Asset Criticality Matrix |  |  |  | 2173
Governance_Readiness | Risk | Risk Register / Business Continuity Plan |  |  |  | 2174
Governance_Readiness | Documentation | Digital Handover (BIM) / Asset Tagging System |  |  |  | 2175
2176
2177
2178
2179
2180
2181
2182
2183
2184
2185
2186
2187
2188
2189
2190
2191
2192
2193
2194
2195
2196
2197
2198
2199
2200

## Building Assessment
System | Subsystem (Please Select from the list) | Component (Please Select from the list) | Item Code | Inspection Item | Criteria | Test Method | Asset(s) Tag No. | Snag Location | Snag Evidence Ref. | Snag Evidence Type (Please Select from the list) | Rate (Please Select from the list) | Score % | Item Weight (Please Select from the list) | Weighted Score | Risk Criticality (0-5) | Responsibility (Please Select from the list) | CAPA ID | Priority (Please Select from the list) | Due Date | Status (Please Select from the list) | Remarks | .
Fire_LifeSafety | Fire Alarm | Fire Alarm Control Panel | FL-CP-001 | Fire alarm control panel test | All zones operational; no faults | Visual Inspection | FLS-03-A-001 | External - Service Yard |  | Checklist | 4 | 80% | 3.31 | 2.648 | 5 | Specialist Vendor |  | P3 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Fire_LifeSafety | Fire Fighting | Detector | FL-DT-002 | Smoke/heat detector functional test | Response within manufacturer spec | Visual Inspection | FLS-03-D-002 | Level 02 - Office Area | PHOTO-FIR-0002 | Photo | 3 | 60% | 3.31 | 1.986 | 5 | MEP Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
Fire_LifeSafety | Smoke Control | Manual Call Point | FL-MCP-003 | Manual call point activation test | Activates alarm; location correct | Visual Inspection | FLS-05-C-003 | External - Service Yard | PHOTO-FIR-0003 | Photo | 3 | 60% | 2.65 | 1.59 | 4 | Specialist Vendor | CAPA-0001 | P2 | 2024-05-09 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | .
Fire_LifeSafety | Compartmentation | Sounder and Beacon | FL-SB-004 | Audible/visual alarm device test | Sound level ≥75dB(A); lights visible | Visual Inspection | FLS-03-C-004 | External - Service Yard | PHOTO-FIR-0004 | Photo | 3 | 60% | 3.31 | 1.986 | 5 | Specialist Vendor | CAPA-0002 | P2 | 2024-05-09 | Open | Condition acceptable but requires attention; minor deficiencies observed. Evidence captured; recommend rectification and re-test. | .
Fire_LifeSafety | Emergency Lighting | Voice Evacuation System | FL-VE-005 | Voice evacuation system test | Clear audio; zoning correct | Visual Inspection | FLS-04-C-005 | Level 01 - Office Area | PHOTO-FIR-0005 | Photo | 3 | 60% | 2.65 | 1.59 | 4 | Specialist Vendor | CAPA-0003 | P2 | 2024-05-09 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Evidence captured; recommend rectification and re-test. | .
Fire_LifeSafety | Fire Alarm | Fire Alarm Control Panel | FL-BT-006 | Battery backup duration test | ≥30 minutes autonomy | Visual Inspection | FLS-02-C-006 | Staircase Core | PHOTO-FIR-0006 | Photo | 1 | 20% | 2.65 | 0.53 | 4 | Specialist Vendor | CAPA-0004 | P1 | 22/08/2024 | Open | Critical deficiency observed; immediate corrective action required to mitigate risk. Trend indicates aging components; prioritize within next maintenance cycle. | .
Fire_LifeSafety | Interfaces | Fire Pump | FL-FP-007 | Fire pump auto-start test | Starts within 30s of pressure drop | Visual Inspection | FLS-01-B-007 | Electrical Room - LV | PHOTO-FIR-0007 | Photo | 3 | 60% | 3.31 | 1.986 | 5 | FM Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | .
Fire_LifeSafety | Documentation | Jockey Pump | FL-JP-008 | Jockey pump operation test | Maintains pressure; cycles correctly | Visual Inspection | FLS-04-D-008 | External - Service Yard | PHOTO-FIR-0008 | Photo | 2 | 40% | 3.31 | 1.324 | 5 | MEP Contractor | CAPA-0005 | P1 | 22/08/2024 | Open | Non-compliance / degraded condition observed; corrective action required. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Fire_LifeSafety | Training | Sprinkler System | FL-SS-009 | Sprinkler system pressure test | Pressure stable; no leaks | Visual Inspection | FLS-03-A-009 | Parking - Basement | PHOTO-FIR-0009 | Photo | 3 | 60% | 3.31 | 1.986 | 5 | FM Contractor | CAPA-0006 | P2 | 2024-05-09 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Fire_LifeSafety | Records | Hydrant / Hose Reel | FL-HH-010 | Hydrant/hose reel flow test | Adequate flow/pressure; valves operable | Visual Inspection | FLS-05-C-010 | Roof - Mechanical Area | PHOTO-FIR-0010 | Photo | 1 | 20% | 2.65 | 0.53 | 4 | Specialist Vendor | CAPA-0007 | P1 | 22/08/2024 | Open | Critical deficiency observed; immediate corrective action required to mitigate risk. Preventive maintenance records incomplete; verify PM completion. | .
Fire_LifeSafety |  | Fire Extinguisher | FL-FE-011 | Fire extinguisher inspection | In date; pressure ok; accessible | Visual Inspection | FLS-B1-C-011 | Staircase Core | PHOTO-FIR-0011 | Photo | 0 | 0% | 2.65 | 0 | 4 | FM Contractor |  | - |  | N/A | Not applicable for this building / scope. | .
Fire_LifeSafety |  | Clean Agent System | FL-CA-012 | Clean agent system readiness | Pressure ok; nozzles unobstructed | Visual Inspection | FLS-01-C-012 | Level 02 - Office Area |  | Photo | 4 | 80% | 2.65 | 2.12 | 4 | MEP Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Fire_LifeSafety | Fire Fighting | Detector | FL-SE-013 | Smoke extract fan test | Starts on command; airflow adequate | Visual Inspection | FLS-05-B-013 | Level 01 - Office Area |  | Test Report | 4 | 80% | 3.31 | 2.648 | 5 | FM Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Fire_LifeSafety |  | Pressurization Fan | FL-PF-014 | Pressurization fan test | Creates positive pressure as designed | Visual Inspection | FLS-G-C-014 | Parking - Basement | PHOTO-FIR-0014 | Photo | 2 | 40% | 2.65 | 1.06 | 4 | FM Contractor | CAPA-0008 | P1 | 22/08/2024 | In Progress | Non-compliance / degraded condition observed; corrective action required. Evidence captured; recommend rectification and re-test. | .
Fire_LifeSafety | Fire Fighting | Detector | FL-FD-015 | Fire/smoke damper operation test | Closes on signal; seals intact | Visual Inspection | FLS-03-B-015 | Basement B1 - Plantroom | PHOTO-FIR-0015 | Photo | 3 | 60% | 3.31 | 1.986 | 5 | MEP Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Evidence captured; recommend rectification and re-test. | .
Fire_LifeSafety |  | Fire Door | FL-FD-016 | Fire door inspection | Self-closing; gaps ≤4mm; seals intact | Visual Inspection | FLS-G-B-016 | External - Service Yard |  | Test Report | 4 | 80% | 2.65 | 2.12 | 4 | Specialist Vendor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Fire_LifeSafety |  | Fire Curtain | FL-FC-017 | Fire curtain drop test | Drops automatically; no obstruction | Visual Inspection | FLS-02-D-017 | Electrical Room - LV | PHOTO-FIR-0017 | Photo | 2 | 40% | 2.65 | 1.06 | 4 | MEP Contractor | CAPA-0009 | P1 | 22/08/2024 | Open | Non-compliance / degraded condition observed; corrective action required. Evidence captured; recommend rectification and re-test. | .
Fire_LifeSafety |  | Firestopping System | FL-FS-018 | Firestopping integrity check | Penetrations sealed; material intact | Visual Inspection | FLS-02-B-018 | Level 03 - Office Area | PHOTO-FIR-0018 | Photo | 2 | 40% | 2.65 | 1.06 | 4 | MEP Contractor | CAPA-0010 | P1 | 22/08/2024 | Open | Non-compliance / degraded condition observed; corrective action required. Preventive maintenance records incomplete; verify PM completion. | .
Fire_LifeSafety |  | Emergency Light | FL-EL-019 | Emergency lighting duration test | ≥90 minutes operation | Visual Inspection | FLS-B1-B-019 | Level 01 - Office Area |  | Checklist | 4 | 80% | 2.65 | 2.12 | 4 | FM Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Fire_LifeSafety |  | Exit Sign | FL-ES-020 | Exit sign illumination test | Clearly visible; illuminated | Visual Inspection | FLS-01-D-020 | Staircase Core | PHOTO-FIR-0020 | Photo | 3 | 60% | 2.65 | 1.59 | 4 | FM Contractor |  | P2 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
Fire_LifeSafety |  | Central Battery System | FL-CB-021 | Central battery system test | Charging ok; load test passed | Visual Inspection | FLS-B1-C-021 | Basement B1 - Plantroom | PHOTO-FIR-0021 | Photo | 3 | 60% | 2.65 | 1.59 | 4 | MEP Contractor | CAPA-0011 | P2 | 2024-05-09 | Open | Condition acceptable but requires attention; minor deficiencies observed. Evidence captured; recommend rectification and re-test. | .
Fire_LifeSafety |  | Elevator Recall Interface | FL-ER-022 | Elevator recall interface test | Elevators recall to designated floor | Visual Inspection | FLS-03-B-022 | External - Service Yard | PHOTO-FIR-0022 | Photo | 3 | 60% | 2.65 | 1.59 | 4 | Specialist Vendor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | .
Fire_LifeSafety |  | Access Control Fire Release | FL-AC-023 | Access control release test | Doors unlock on fire signal | Visual Inspection | FLS-01-B-023 | Level 03 - Office Area | PHOTO-FIR-0023 | Photo | 3 | 60% | 2.65 | 1.59 | 4 | Specialist Vendor | CAPA-0012 | P2 | 2024-05-09 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | .
Fire_LifeSafety |  | BMS Interface | FL-BI-024 | BMS interface verification | Alarms received; HVAC shutdown works | Visual Inspection | FLS-B1-B-024 | Staircase Core | PHOTO-FIR-0024 | Photo | 3 | 60% | 2.65 | 1.59 | 4 | MEP Contractor | CAPA-0013 | P2 | 2024-05-09 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Evidence captured; recommend rectification and re-test. | .
Fire_LifeSafety |  | HVAC Shutdown Interface | FL-HS-025 | HVAC shutdown test | AHUs/Fans stop on fire signal | Visual Inspection | FLS-04-C-025 | External - Service Yard | PHOTO-FIR-0025 | Photo | 2 | 40% | 2.65 | 1.06 | 4 | MEP Contractor | CAPA-0014 | P1 | 22/08/2024 | In Progress | Non-compliance / degraded condition observed; corrective action required. Evidence captured; recommend rectification and re-test. | .
Fire_LifeSafety |  | Civil Defense Certification | FL-CD-026 | Civil defense certification | Valid certificate available | Visual Inspection | FLS-03-B-026 | Roof - Mechanical Area | PHOTO-FIR-0026 | Photo | 3 | 60% | 2.65 | 1.59 | 4 | Specialist Vendor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Housekeeping and labeling improvements required. | .
Fire_LifeSafety |  | Fire Strategy Drawings | FL-FS-027 | Fire strategy drawing verification | Matches as-built; accessible | Visual Inspection | FLS-04-D-027 | Level 03 - Office Area | PHOTO-FIR-0027 | Photo | 3 | 60% | 2.65 | 1.59 | 4 | FM Contractor | CAPA-0015 | P2 | 2024-05-09 | Open | Condition acceptable but requires attention; minor deficiencies observed. Housekeeping and labeling improvements required. | .
Fire_LifeSafety |  | Fire System Test Certificates | FL-TC-028 | Fire system test certificates | Complete set available | Visual Inspection | FLS-G-A-028 | Roof - Mechanical Area | PHOTO-FIR-0028 | Photo | 1 | 20% | 3.31 | 0.662 | 5 | FM Contractor | CAPA-0016 | P1 | 22/08/2024 | Open | Critical deficiency observed; immediate corrective action required to mitigate risk. Housekeeping and labeling improvements required. | .
Fire_LifeSafety | Fire Alarm | Fire Alarm Control Panel | FL-OP-029 | Fire panel operator training | FM staff trained; records available | Visual Inspection | FLS-04-A-029 | Roof - Mechanical Area | PHOTO-FIR-0029 | Photo | 3 | 60% | 2.65 | 1.59 | 4 | Specialist Vendor | CAPA-0017 | P3 | 29/09/2024 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | .
Fire_LifeSafety | Interfaces | Fire Pump | FL-MP-030 | Fire pump monthly run test | Records available; pump operational | Visual Inspection | FLS-02-A-030 | Level 01 - Office Area | PHOTO-FIR-0030 | Photo | 3 | 60% | 3.31 | 1.986 | 5 | FM Contractor |  | P2 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | .
Fire_LifeSafety |  | Fire Door | FL-FI-031 | Fire door inspection log | Regular inspections documented | Visual Inspection | FLS-02-A-031 | Electrical Room - LV | PHOTO-FIR-0031 | Photo | 1 | 20% | 2.65 | 0.53 | 4 | FM Contractor | CAPA-0018 | P1 | 22/08/2024 | In Progress | Critical deficiency observed; immediate corrective action required to mitigate risk. Housekeeping and labeling improvements required. | .
Fire_LifeSafety | Fire Fighting | Detector | FL-SC-032 | Smoke control sequence verification | Sequences match fire strategy | Visual Inspection | FLS-05-A-032 | Level 03 - Office Area | PHOTO-FIR-0032 | Photo | 3 | 60% | 3.31 | 1.986 | 5 | Specialist Vendor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Fire_LifeSafety | Fire Alarm | Fire Alarm Control Panel | FL-ZN-033 | Zone identification accuracy | Panel display matches physical zones | Visual Inspection | FLS-03-C-033 | Basement B1 - Plantroom | PHOTO-FIR-0033 | Photo | 2 | 40% | 2.65 | 1.06 | 4 | FM Contractor | CAPA-0019 | P2 | 2024-05-09 | In Progress | Non-compliance / degraded condition observed; corrective action required. Housekeeping and labeling improvements required. | .
Fire_LifeSafety | Fire Alarm | Fire Alarm Control Panel | FL-RS-034 | Emergency responder communication test | Tested with authorities if required | Visual Inspection | FLS-03-B-034 | Roof - Mechanical Area | PHOTO-FIR-0034 | Photo | 3 | 60% | 2.65 | 1.59 | 4 | MEP Contractor | CAPA-0020 | P2 | 2024-05-09 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Fire_LifeSafety |  | Fire Drill Records | FL-DR-035 | Fire drill records | Regular drills conducted; documented | Visual Inspection | FLS-04-D-035 | Roof - Mechanical Area | PHOTO-FIR-0035 | Photo | 3 | 60% | 2.65 | 1.59 | 4 | Specialist Vendor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Electrical | Power Distribution | Main LV Switchboard | EL-IR-001 | Main feeder insulation resistance (Megger) | MΩ values meet acceptance criteria | Visual Inspection | EL-02-A-036 | Level 03 - Office Area | PHOTO-ELE-0036 | Photo | 2 | 40% | 3.31 | 1.324 | 4 | MEP Contractor | CAPA-0021 | P1 | 22/08/2024 | In Progress | Non-compliance / degraded condition observed; corrective action required. Preventive maintenance records incomplete; verify PM completion. | .
Electrical | Power Distribution | Main LV Switchboard | EL-CT-002 | Circuit continuity test (random sample) | Ω within acceptable range, no open circuits | Visual Inspection | EL-04-A-037 | Level 03 - Office Area |  | Test Report | 4 | 80% | 3.31 | 2.648 | 4 | MEP Contractor |  | P3 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Electrical | Power Distribution | Main LV Switchboard | EL-LD-003 | Load test / load profiling (peak hour) | Load % within design, no overload | Visual Inspection | EL-G-A-038 | Basement B1 - Plantroom |  | Photo | 4 | 80% | 3.31 | 2.648 | 4 | FM Contractor |  | P3 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Electrical | Lighting | Earthing System | EL-ER-004 | Earth resistance test | Ω meets acceptance limit | Visual Inspection | EL-02-D-039 | Level 02 - Office Area |  | Photo | 4 | 80% | 3.31 | 2.648 | 4 | Specialist Vendor | CAPA-0022 | P3 | 29/09/2024 | In Progress | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Electrical | Interfaces | Protection Relay / Breaker | EL-PR-005 | Protection relay / breaker trip test | Trip settings verified, test records available | Visual Inspection | EL-B1-B-040 | Ground Floor - Lobby |  | Checklist | 5 | 100% | 4.13 | 4.13 | 5 | FM Contractor |  | P4 |  | Verified | Inspected and found fully compliant; no observations noted. | .
Electrical | Housekeeping | Power / Energy Meter | EL-PQ-006 | Power quality (THD/imbalance) | Voltage THD < 5% (or project criterion) | Visual Inspection | EL-03-D-041 | Staircase Core | PHOTO-ELE-0041 | Photo | 3 | 60% | 3.31 | 1.986 | 4 | Owner | CAPA-0023 | P2 | 2024-05-09 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | .
Electrical | Power Distribution | Main LV Switchboard | EL-TH-007 | Thermal scan of LV boards | No hotspots above acceptable ΔT | Visual Inspection | EL-04-B-042 | Level 03 - Office Area |  | Checklist | 4 | 80% | 3.31 | 2.648 | 4 | Specialist Vendor |  | P3 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Electrical | Documentation | RCD / ELCB | EL-RCD-008 | RCD/ELCB trip time test | ≤30ms at 1x IΔn (or project criterion) | Visual Inspection | EL-G-B-043 | Level 02 - Office Area | PHOTO-ELE-0043 | Photo | 2 | 40% | 4.13 | 1.652 | 5 | FM Contractor | CAPA-0024 | P1 | 22/08/2024 | Open | Non-compliance / degraded condition observed; corrective action required. Evidence captured; recommend rectification and re-test. | .
Electrical |  | Internal Lighting | EL-LX-009 | Internal lighting lux test | Lux meets area requirement; uniformity acceptable | Visual Inspection | EL-02-A-044 | External - Service Yard | PHOTO-ELE-0044 | Photo | 3 | 60% | 3.31 | 1.986 | 4 | FM Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Housekeeping and labeling improvements required. | .
Electrical |  | Internal Lighting | EL-ELX-010 | External lighting lux coverage | Coverage meets security/parking requirement | Visual Inspection | EL-02-B-045 | Level 03 - Office Area |  | Checklist | 4 | 80% | 3.31 | 2.648 | 4 | MEP Contractor |  | P3 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Electrical | Housekeeping | Power / Energy Meter | EL-MTR-015 | Main & sub-metering functionality | Meters read correctly; logging works | Visual Inspection | EL-02-A-046 | Ground Floor - Lobby |  | Test Report | 4 | 80% | 3.31 | 2.648 | 4 | Main Contractor |  | P3 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Electrical | Power Distribution | Main LV Switchboard | EL-LBL-016 | Panel/circuit labeling & directories | Accurate, durable, matches as-built | Visual Inspection | EL-02-C-047 | Roof - Mechanical Area | PHOTO-ELE-0047 | Photo | 3 | 60% | 2.48 | 1.488 | 3 | FM Contractor | CAPA-0025 | P2 | 2024-05-09 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Housekeeping and labeling improvements required. | .
Electrical |  | Electrical Room | EL-CLR-017 | Electrical room clearances & housekeeping | Access/clearances compliant, tidy | Visual Inspection | EL-G-A-048 | Basement B1 - Plantroom | PHOTO-ELE-0048 | Photo | 3 | 60% | 2.48 | 1.488 | 3 | Owner |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
Electrical | Metering & PQ | Cable Containment | EL-EXB-018 | Cable containment condition | Trays/ladder/supports secure; no damage | Visual Inspection | EL-04-A-049 | External - Service Yard |  | Photo | 4 | 80% | 3.31 | 2.648 | 4 | FM Contractor |  | P3 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Electrical | Power Distribution | Main LV Switchboard | EL-FST-019 | Firestopping at penetrations (electrical) | Seals present and intact | Visual Inspection | EL-01-A-050 | External - Service Yard |  | Photo | 4 | 80% | 3.31 | 2.648 | 4 | Specialist Vendor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Electrical | Lighting | Earthing System | EL-GND-020 | Bonding/earthing of metallic systems | Bonds present, secure | Visual Inspection | EL-B1-C-051 | External - Service Yard |  | Photo | 5 | 100% | 4.13 | 4.13 | 5 | FM Contractor |  | P4 |  | Verified | Inspected and found fully compliant; no observations noted. | .
Electrical | Power Distribution | Main LV Switchboard | EL-SKT-021 | Socket polarity and earth test | Correct polarity; earth present | Visual Inspection | EL-B1-D-052 | Roof - Mechanical Area |  | Test Report | 5 | 100% | 4.13 | 4.13 | 5 | Specialist Vendor |  | P4 |  | Closed | Inspected and found fully compliant; no observations noted. | .
Electrical | Power Distribution | Main LV Switchboard | EL-PRF-023 | Power factor correction operation | Stages switch correctly; no overheating | Visual Inspection | EL-02-D-053 | External - Service Yard |  | Checklist | 4 | 80% | 3.31 | 2.648 | 4 | MEP Contractor |  | P3 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Electrical | Housekeeping | Power / Energy Meter | EL-HAR-024 | Harmonics mitigation (if installed) | Filters operational; readings within limits | Visual Inspection | EL-01-A-054 | Electrical Room - LV |  | Checklist | 5 | 100% | 3.31 | 3.31 | 4 | Specialist Vendor |  | P4 |  | Verified | Inspected and found fully compliant; no observations noted. | .
Electrical |  | BMS / SCADA Electrical Interface | EL-BMS-025 | BMS/SCADA electrical points verification | Points mapped; alarms/trends working | Visual Inspection | EL-03-A-055 | Staircase Core |  | Photo | 4 | 80% | 3.31 | 2.648 | 4 | FM Contractor |  | P3 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Electrical | Power Distribution | Main LV Switchboard | EL-IRN-026 | IR scan report availability & actions | Report attached; actions closed | Visual Inspection | EL-B1-C-056 | Level 02 - Office Area |  | Checklist | 4 | 80% | 3.31 | 2.648 | 4 | MEP Contractor |  | P3 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Electrical | Power Distribution | Main LV Switchboard | EL-OPS-027 | Operating procedures and LOTO signage | Procedures posted; LOTO available | Visual Inspection | EL-01-D-057 | Level 03 - Office Area | PHOTO-ELE-0057 | Photo | 3 | 60% | 3.31 | 1.986 | 4 | MEP Contractor | CAPA-0026 | P2 | 2024-05-09 | Open | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
Electrical |  | Spare Breakers / Fuses | EL-SPR-028 | Spare breakers/fuses availability | Critical spares available | Visual Inspection | EL-01-C-058 | Ground Floor - Lobby |  | Photo | 4 | 80% | 2.48 | 1.984 | 3 | FM Contractor |  | P3 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Electrical | Power Distribution | Main LV Switchboard | EL-TRN-029 | Electrical training records (FM) | Training completed; attendance proof | Visual Inspection | EL-03-C-059 | Level 01 - Office Area | PHOTO-ELE-0059 | Photo | 2 | 40% | 3.31 | 1.324 | 4 | FM Contractor | CAPA-0027 | P1 | 22/08/2024 | Open | Non-compliance / degraded condition observed; corrective action required. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Electrical |  | Electrical Asâ€‘Built Drawings | EL-COM-030 | As-built electrical drawings complete | Up-to-date revisions available | Visual Inspection | EL-B1-A-060 | Parking - Basement | PHOTO-ELE-0060 | Photo | 3 | 60% | 3.31 | 1.986 | 4 | FM Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
Electrical |  | Electrical Test Certificates | EL-TST-031 | Electrical test certificates present | Megger/earth/RCD results filed | Visual Inspection | EL-B1-D-061 | External - Service Yard |  | Test Report | 4 | 80% | 3.31 | 2.648 | 4 | FM Contractor |  | P3 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Electrical | Power Distribution | Main LV Switchboard | EL-QA-032 | Defect log and closure evidence | Defects tracked; verification done | Visual Inspection | EL-03-A-062 | Level 02 - Office Area | PHOTO-ELE-0062 | Photo | 2 | 40% | 3.31 | 1.324 | 4 | FM Contractor | CAPA-0028 | P1 | 22/08/2024 | Open | Non-compliance / degraded condition observed; corrective action required. Trend indicates aging components; prioritize within next maintenance cycle. | .
Electrical |  | Safety Signage & PPE | EL-SAF-033 | Safety signage & PPE availability | PPE, warnings, restricted access | Visual Inspection | EL-02-D-063 | Level 03 - Office Area |  | Photo | 4 | 80% | 3.31 | 2.648 | 4 | FM Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Electrical | Power Distribution | Main LV Switchboard | EL-ENV-034 | Room temperature/ventilation for switchgear | Within acceptable; no overheating | Visual Inspection | EL-02-A-064 | Staircase Core | PHOTO-ELE-0064 | Photo | 3 | 60% | 3.31 | 1.986 | 4 | Specialist Vendor | CAPA-0029 | P2 | 2024-05-09 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
Electrical | Interfaces | Protection Relay / Breaker | EL-SPE-014 | Surge protection device status | SPD healthy; indicators normal | Visual Inspection | EL-02-A-065 | Electrical Room - LV |  | Test Report | 4 | 80% | 3.31 | 2.648 | 4 | Specialist Vendor |  | P3 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Emergency_Power | Generation | Diesel Generator | EL-GEN-012 | Generator auto-start test | Start/transfer within required seconds | Visual Inspection | EP-04-C-066 | External - Service Yard | PHOTO-EME-0066 | Photo | 3 | 60% | 20 | 12 | 4 | MEP Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Emergency_Power | Distribution | Automatic Transfer Switch | EL-ATS-013 | ATS transfer test | Transfer successful; interlocks functional | Visual Inspection | EP-05-C-067 | External - Service Yard |  | Photo | 4 | 80% | 20 | 16 | 4 | Owner |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Emergency_Power | Resilience | UPS System | EL-UPS-011 | UPS autonomy test | Autonomy meets design minutes; alarms normal | Visual Inspection | EP-01-D-068 | Roof - Mechanical Area |  | Checklist | 4 | 80% | 20 | 16 | 4 | Owner |  | P3 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Emergency_Power | Storage | Emergency Distribution Board | EL-EML-022 | Emergency power distribution boards | Operational, labeled, accessible | Visual Inspection | EP-05-A-069 | Electrical Room - LV |  | Photo | 5 | 100% | 20 | 20 | 4 | FM Contractor |  | P4 |  | Closed | Inspected and found fully compliant; no observations noted. | .
Emergency_Power |  | Redundancy / Single Point Review | EL-RES-035 | Resilience check (single point failures) | Redundancy verified where applicable | Visual Inspection | EP-02-D-070 | Basement B1 - Plantroom | PHOTO-EME-0070 | Photo | 3 | 60% | 20 | 12 | 4 | MEP Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | .
Mechanical_HVAC | Central Plant | Chiller | ME-COP-001 | COP/EER performance spot-check | Calculated COP/EER within expectation | Visual Inspection | HVAC-01-D-071 | Electrical Room - LV |  | Photo | 4 | 80% | 2.94 | 2.352 | 4 | FM Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Mechanical_HVAC | Central Plant | Chiller | ME-TAB-002 | Airflow & balance (TAB) verification | Within ±10% of design (or criterion) | Visual Inspection | HVAC-G-A-072 | Electrical Room - LV | PHOTO-MEC-0072 | Photo | 3 | 60% | 2.21 | 1.326 | 3 | MEP Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | .
Mechanical_HVAC | Central Plant | Chiller | ME-IAQ-003 | Ventilation effectiveness / CO₂ check | CO₂ ppm within target; fresh air adequate | Visual Inspection | HVAC-02-D-073 | Electrical Room - LV |  | Photo | 4 | 80% | 2.94 | 2.352 | 4 | MEP Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Mechanical_HVAC | Central Plant | Chiller | ME-NV-004 | Noise & vibration test (plant/occupied) | dB(A) and mm/s within limits | Visual Inspection | HVAC-05-D-074 | Roof - Mechanical Area | PHOTO-MEC-0074 | Photo | 2 | 40% | 2.94 | 1.176 | 4 | Main Contractor | CAPA-0030 | P2 | 2024-05-09 | Open | Non-compliance / degraded condition observed; corrective action required. Housekeeping and labeling improvements required. | .
Mechanical_HVAC | Central Plant | Chiller | ME-CH-005 | Chiller operating stability (if any) | Stable parameters; no abnormal alarms | Visual Inspection | HVAC-03-D-075 | Roof - Mechanical Area | PHOTO-MEC-0075 | Photo | 2 | 40% | 3.68 | 1.472 | 5 | Main Contractor | CAPA-0031 | P1 | 22/08/2024 | In Progress | Non-compliance / degraded condition observed; corrective action required. Preventive maintenance records incomplete; verify PM completion. | .
Mechanical_HVAC | Air Handling | Cooling Tower | ME-CT-006 | Cooling tower condition (if any) | Basin clean; drift eliminators OK | Visual Inspection | HVAC-05-D-076 | Basement B1 - Plantroom |  | Checklist | 5 | 100% | 2.94 | 2.94 | 4 | MEP Contractor |  | P4 |  | Closed | Inspected and found fully compliant; no observations noted. | .
Mechanical_HVAC | Air Distribution | Chilled / Condenser Water Pump | ME-PU-007 | CHW/CW pump duty point check | Flow/pressure within ±10% | Visual Inspection | HVAC-02-A-077 | Level 01 - Office Area | PHOTO-MEC-0077 | Photo | 1 | 20% | 2.94 | 0.588 | 4 | Owner | CAPA-0032 | P1 | 22/08/2024 | In Progress | Critical deficiency observed; immediate corrective action required to mitigate risk. Preventive maintenance records incomplete; verify PM completion. | .
Mechanical_HVAC | Ventilation | Air Handling Unit | ME-AHU-008 | AHU condition (filters/coils/drain pans) | Clean; drains functional; ΔP acceptable | Visual Inspection | HVAC-B1-D-078 | Level 03 - Office Area | PHOTO-MEC-0078 | Photo | 3 | 60% | 2.94 | 1.764 | 4 | MEP Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Evidence captured; recommend rectification and re-test. | .
Mechanical_HVAC | Hydronic System | Fan Coil Unit | ME-FCU-009 | FCU performance & condensate drainage | No leaks; cooling adequate | Visual Inspection | HVAC-05-A-079 | External - Service Yard | PHOTO-MEC-0079 | Photo | 3 | 60% | 2.94 | 1.764 | 4 | Owner | CAPA-0033 | P2 | 2024-05-09 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
Mechanical_HVAC | Controls & BMS | Ductwork | ME-DCT-010 | Ductwork condition & insulation | No damage; insulation intact; no sweating | Visual Inspection | HVAC-B1-A-080 | Roof - Mechanical Area | PHOTO-MEC-0080 | Photo | 3 | 60% | 2.94 | 1.764 | 4 | MEP Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | .
Mechanical_HVAC |  | Actuator | ME-DMP-011 | Dampers/actuators operation | Full stroke; accessible; seals OK | Visual Inspection | HVAC-G-B-081 | Ground Floor - Lobby | PHOTO-MEC-0081 | Photo | 3 | 60% | 2.94 | 1.764 | 4 | MEP Contractor |  | P2 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Mechanical_HVAC | DX / VRF | VAV Box | ME-VAV-012 | VAV box response & calibration | Responds; sensor accurate | Visual Inspection | HVAC-02-C-082 | Basement B1 - Plantroom | PHOTO-MEC-0082 | Photo | 2 | 40% | 2.94 | 1.176 | 4 | MEP Contractor | CAPA-0034 | P2 | 2024-05-09 | In Progress | Non-compliance / degraded condition observed; corrective action required. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Mechanical_HVAC |  | Grille / Diffuser | ME-DIF-013 | Diffusers/grilles cleanliness & throw | Clean; no obstruction; noise OK | Visual Inspection | HVAC-04-D-083 | Level 03 - Office Area | PHOTO-MEC-0083 | Photo | 3 | 60% | 2.94 | 1.764 | 4 | Main Contractor | CAPA-0035 | P2 | 2024-05-09 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
Mechanical_HVAC | Central Plant | Chiller | ME-CTRL-014 | Controls/BMS sequences verification | Occupied/unoccupied tested | Visual Inspection | HVAC-04-C-084 | Basement B1 - Plantroom | PHOTO-MEC-0084 | Photo | 3 | 60% | 2.94 | 1.764 | 4 | MEP Contractor | CAPA-0036 | P2 | 2024-05-09 | Open | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Mechanical_HVAC | Central Plant | Chiller | ME-ALM-015 | Alarm management & trending | Trends available; alarm priorities set | Visual Inspection | HVAC-05-C-085 | Level 02 - Office Area | PHOTO-MEC-0085 | Photo | 3 | 60% | 2.94 | 1.764 | 4 | Main Contractor | CAPA-0037 | P3 | 29/09/2024 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
Mechanical_HVAC |  | Refrigerant Piping | ME-REF-016 | Refrigerant leak indicators | No leaks; log maintained | Visual Inspection | HVAC-01-D-086 | Basement B1 - Plantroom | PHOTO-MEC-0086 | Photo | 2 | 40% | 2.94 | 1.176 | 4 | MEP Contractor | CAPA-0038 | P2 | 2024-05-09 | Open | Non-compliance / degraded condition observed; corrective action required. Evidence captured; recommend rectification and re-test. | .
Mechanical_HVAC |  | Pipework | ME-INS-017 | Pipe insulation integrity | Vapor barrier sealed; no condensation | Visual Inspection | HVAC-G-B-087 | Staircase Core | PHOTO-MEC-0087 | Photo | 2 | 40% | 2.94 | 1.176 | 4 | Specialist Vendor | CAPA-0039 | P2 | 2024-05-09 | In Progress | Non-compliance / degraded condition observed; corrective action required. Trend indicates aging components; prioritize within next maintenance cycle. | .
Mechanical_HVAC | Central Plant | Chiller | ME-HYD-018 | Hydrostatic pressure test (if executed) | Pressure/hold duration recorded; pass | Visual Inspection | HVAC-05-A-088 | Electrical Room - LV |  | Photo | 4 | 80% | 2.94 | 2.352 | 4 | Specialist Vendor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Mechanical_HVAC | Central Plant | Chiller | ME-LK-019 | Piping leak test | No leaks; evidence recorded | Visual Inspection | HVAC-B1-D-089 | Basement B1 - Plantroom | PHOTO-MEC-0089 | Photo | 2 | 40% | 2.94 | 1.176 | 4 | Owner | CAPA-0040 | P1 | 22/08/2024 | In Progress | Non-compliance / degraded condition observed; corrective action required. Housekeeping and labeling improvements required. | .
Mechanical_HVAC |  | Valve | ME-VAL-020 | Valves & isolation points labeling | Labeled; accessible; operable | Visual Inspection | HVAC-02-A-090 | External - Service Yard | PHOTO-MEC-0090 | Photo | 3 | 60% | 2.94 | 1.764 | 4 | FM Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Evidence captured; recommend rectification and re-test. | .
Mechanical_HVAC |  | Expansion Tank | ME-EXP-021 | Expansion tanks/air separators (if any) | Operational; pressure OK | Visual Inspection | HVAC-04-D-091 | Ground Floor - Lobby | PHOTO-MEC-0091 | Photo | 2 | 40% | 2.94 | 1.176 | 4 | Main Contractor | CAPA-0041 | P1 | 22/08/2024 | Open | Non-compliance / degraded condition observed; corrective action required. Housekeeping and labeling improvements required. | .
Mechanical_HVAC |  | Chemical Dosing System | ME-WTR-022 | Water treatment logs (if any) | Logs complete; dosing OK | Visual Inspection | HVAC-04-D-092 | External - Service Yard |  | Test Report | 4 | 80% | 2.94 | 2.352 | 4 | FM Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Mechanical_HVAC |  | Exhaust / Fresh Air Fan | ME-FAN-023 | Exhaust/ventilation fans operation | Interlocks OK; airflow adequate | Visual Inspection | HVAC-B1-C-093 | Level 02 - Office Area |  | Checklist | 4 | 80% | 2.94 | 2.352 | 4 | MEP Contractor |  | P3 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Mechanical_HVAC | Central Plant | Chiller | ME-ECN-024 | Energy waste check (runtime/schedules) | Schedules optimized; no wasted runtime | Visual Inspection | HVAC-G-A-094 | Electrical Room - LV |  | Photo | 4 | 80% | 2.94 | 2.352 | 4 | FM Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Mechanical_HVAC | Central Plant | Chiller | ME-PRS-025 | Room pressurization (as required) | Within design; doors not hard to open | Visual Inspection | HVAC-05-B-095 | Ground Floor - Lobby |  | Test Report | 4 | 80% | 2.94 | 2.352 | 4 | FM Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Mechanical_HVAC | Water Treatment | Volume / Fire Damper | ME-FIR-026 | Fire/smoke dampers interface (mechanical) | Accessible; tested if applicable | Visual Inspection | HVAC-G-C-096 | Level 01 - Office Area |  | Photo | 4 | 80% | 2.94 | 2.352 | 4 | FM Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Mechanical_HVAC | Central Plant | Chiller | ME-MNT-027 | Preventive maintenance execution | PM checklists completed | Visual Inspection | HVAC-G-C-097 | Basement B1 - Plantroom |  | Photo | 5 | 100% | 2.94 | 2.94 | 4 | MEP Contractor |  | P4 |  | Closed | Inspected and found fully compliant; no observations noted. | .
Mechanical_HVAC | Central Plant | Chiller | ME-SPR-028 | Spare parts availability (filters/belts) | Critical spares available | Visual Inspection | HVAC-03-A-098 | Staircase Core | PHOTO-MEC-0098 | Photo | 3 | 60% | 2.21 | 1.326 | 3 | MEP Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Evidence captured; recommend rectification and re-test. | .
Mechanical_HVAC | Central Plant | Chiller | ME-ACC-029 | Maintenance access & safety | Safe access; isolation available | Visual Inspection | HVAC-02-D-099 | Ground Floor - Lobby | PHOTO-MEC-0099 | Photo | 2 | 40% | 2.94 | 1.176 | 4 | MEP Contractor | CAPA-0042 | P1 | 22/08/2024 | Open | Non-compliance / degraded condition observed; corrective action required. Evidence captured; recommend rectification and re-test. | .
Mechanical_HVAC | Central Plant | Chiller | ME-DOC-030 | O&M manuals complete for HVAC | Manuals, warranties, start-up sheets | Visual Inspection | HVAC-02-D-100 | Ground Floor - Lobby | PHOTO-MEC-0100 | Photo | 2 | 40% | 2.21 | 0.884 | 3 | FM Contractor | CAPA-0043 | P2 | 2024-05-09 | Open | Non-compliance / degraded condition observed; corrective action required. Preventive maintenance records incomplete; verify PM completion. | .
Mechanical_HVAC | Central Plant | Chiller | ME-TST-031 | Commissioning & TAB reports complete | Final reports attached | Visual Inspection | HVAC-02-D-101 | Ground Floor - Lobby | PHOTO-MEC-0101 | Photo | 2 | 40% | 2.21 | 0.884 | 3 | MEP Contractor | CAPA-0044 | P2 | 2024-05-09 | In Progress | Non-compliance / degraded condition observed; corrective action required. Housekeeping and labeling improvements required. | .
Mechanical_HVAC | Central Plant | Chiller | ME-TRN-032 | FM training on HVAC systems | Training records available | Visual Inspection | HVAC-02-A-102 | Roof - Mechanical Area | PHOTO-MEC-0102 | Photo | 3 | 60% | 2.21 | 1.326 | 3 | Specialist Vendor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Evidence captured; recommend rectification and re-test. | .
Mechanical_HVAC | Central Plant | Chiller | ME-CLN-033 | Plantroom housekeeping | Clean; no leaks; no trip hazards | Visual Inspection | HVAC-01-C-103 | Roof - Mechanical Area | PHOTO-MEC-0103 | Photo | 2 | 40% | 2.94 | 1.176 | 4 | Main Contractor | CAPA-0045 | P1 | 22/08/2024 | Open | Non-compliance / degraded condition observed; corrective action required. Trend indicates aging components; prioritize within next maintenance cycle. | .
Mechanical_HVAC | Central Plant | Chiller | ME-RES-034 | Redundancy verification (if applicable) | N+1 or standby proven | Visual Inspection | HVAC-03-B-104 | Parking - Basement | PHOTO-MEC-0104 | Photo | 3 | 60% | 2.94 | 1.764 | 4 | FM Contractor | CAPA-0046 | P3 | 29/09/2024 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Mechanical_HVAC |  | Sensor | ME-SNS-035 | Sensor calibration certificates | Calibration within last 12 months | Visual Inspection | HVAC-B1-B-105 | Level 03 - Office Area |  | Test Report | 4 | 80% | 2.94 | 2.352 | 4 | MEP Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Plumbing_Water | Water Supply | Water Storage Tank | PL-WP-001 | Water pressure test (top/furthest) | ≥ project minimum bar; stable | Visual Inspection | PLW-04-A-106 | Ground Floor - Lobby |  | Test Report | 4 | 80% | 3.25 | 2.6 | 4 | FM Contractor |  | P3 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Plumbing_Water | Water Supply | Water Storage Tank | PL-FLW-002 | Flow rate spot-check | Meets fixture flow requirements | Visual Inspection | PLW-01-A-107 | Basement B1 - Plantroom |  | Photo | 4 | 80% | 2.44 | 1.952 | 3 | FM Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Plumbing_Water | Water Supply | Water Storage Tank | PL-DF-003 | Drainage flow test | No slow drainage/gurgling | Visual Inspection | PLW-02-C-108 | Level 02 - Office Area |  | Test Report | 4 | 80% | 3.25 | 2.6 | 4 | MEP Contractor |  | P3 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Plumbing_Water | Water Supply | Water Storage Tank | PL-LK-004 | Supply pipe leak test | No leaks; dry cabinets/ceiling | Visual Inspection | PLW-B1-B-109 | Parking - Basement |  | Test Report | 4 | 80% | 3.25 | 2.6 | 4 | MEP Contractor |  | P3 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Plumbing_Water | Water Supply | Water Storage Tank | PL-SLK-005 | Sanitary leak/odor check | No foul odors; traps sealed | Visual Inspection | PLW-02-D-110 | Level 01 - Office Area |  | Photo | 4 | 80% | 3.25 | 2.6 | 4 | FM Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Plumbing_Water | Water Supply | Water Storage Tank | PL-TK-006 | Water tank integrity & cleanliness | No leaks; hygienic; access OK | Visual Inspection | PLW-B1-D-111 | Basement B1 - Plantroom | PHOTO-PLU-0111 | Photo | 2 | 40% | 2.44 | 0.976 | 3 | FM Contractor | CAPA-0047 | P2 | 2024-05-09 | In Progress | Non-compliance / degraded condition observed; corrective action required. Housekeeping and labeling improvements required. | .
Plumbing_Water | Water Supply | Water Storage Tank | PL-DIS-007 | Tank disinfection evidence | Records/certificates available | Visual Inspection | PLW-B1-C-112 | Level 01 - Office Area | PHOTO-PLU-0112 | Photo | 2 | 40% | 2.44 | 0.976 | 3 | FM Contractor | CAPA-0048 | P1 | 22/08/2024 | In Progress | Non-compliance / degraded condition observed; corrective action required. Housekeeping and labeling improvements required. | .
Plumbing_Water | Water Supply | Water Storage Tank | PL-WQ-008 | Potable water quality tests (TDS/pH) | Within limits; lab report attached | Visual Inspection | PLW-02-A-113 | Parking - Basement | PHOTO-PLU-0113 | Photo | 3 | 60% | 4.07 | 2.442 | 5 | FM Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
Plumbing_Water | Water Supply | Water Storage Tank | PL-MIC-009 | Microbial test (if required) | Lab report; compliant | Visual Inspection | PLW-05-C-114 | Roof - Mechanical Area |  | Test Report | 4 | 80% | 4.07 | 3.256 | 5 | MEP Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Plumbing_Water | Water Supply | Water Storage Tank | PL-HW-010 | Hot water storage temperature | >60°C at storage (or criterion) | Visual Inspection | PLW-B1-B-115 | Electrical Room - LV |  | Checklist | 4 | 80% | 2.44 | 1.952 | 3 | MEP Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Plumbing_Water |  | Thermostatic Mixing Valve | PL-TMV-011 | TMV calibration (if applicable) | Setpoints correct; fail-safe OK | Visual Inspection | PLW-01-B-116 | Electrical Room - LV | PHOTO-PLU-0116 | Photo | 2 | 40% | 2.44 | 0.976 | 3 | Main Contractor | CAPA-0049 | P2 | 2024-05-09 | In Progress | Non-compliance / degraded condition observed; corrective action required. Housekeeping and labeling improvements required. | .
Plumbing_Water | Water Supply | Water Storage Tank | PL-REC-012 | Hot water recirculation performance | Stable outlet temperatures | Visual Inspection | PLW-02-D-117 | Basement B1 - Plantroom | PHOTO-PLU-0117 | Photo | 2 | 40% | 2.44 | 0.976 | 3 | MEP Contractor | CAPA-0050 | P2 | 2024-05-09 | In Progress | Non-compliance / degraded condition observed; corrective action required. Evidence captured; recommend rectification and re-test. | .
Plumbing_Water | Hot Water | Isolation Valve | PL-VAL-013 | Isolation valves labeling & access | Labeled; operable | Visual Inspection | PLW-05-A-118 | Electrical Room - LV |  | Test Report | 4 | 80% | 2.44 | 1.952 | 3 | MEP Contractor |  | P3 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Plumbing_Water |  | Backflow Preventer | PL-BFP-014 | Backflow preventer test | Annual test evidence | Visual Inspection | PLW-04-A-119 | Staircase Core | PHOTO-PLU-0119 | Photo | 3 | 60% | 4.07 | 2.442 | 5 | MEP Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | .
Plumbing_Water | Distribution | Booster Pump | PL-PMP-015 | Booster pump duty point check | Flow/pressure within ±10% | Visual Inspection | PLW-02-D-120 | Roof - Mechanical Area | PHOTO-PLU-0120 | Photo | 2 | 40% | 3.25 | 1.3 | 4 | FM Contractor | CAPA-0051 | P2 | 2024-05-09 | In Progress | Non-compliance / degraded condition observed; corrective action required. Evidence captured; recommend rectification and re-test. | .
Plumbing_Water | Water Supply | Water Storage Tank | PL-DRN-016 | Drain pumps performance (if any) | Auto-start; alarms OK | Visual Inspection | PLW-05-B-121 | Roof - Mechanical Area | PHOTO-PLU-0121 | Photo | 3 | 60% | 2.44 | 1.464 | 3 | FM Contractor | CAPA-0052 | P2 | 2024-05-09 | Open | Condition acceptable but requires attention; minor deficiencies observed. Housekeeping and labeling improvements required. | .
Plumbing_Water | Leak Detection | Manhole | PL-MH-017 | Manholes condition & access | Clean; covers intact; safe access | Visual Inspection | PLW-01-D-122 | Roof - Mechanical Area | PHOTO-PLU-0122 | Photo | 3 | 60% | 2.44 | 1.464 | 3 | MEP Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Plumbing_Water | Water Supply | Water Storage Tank | PL-CLN-018 | Cleanouts availability | Accessible; not blocked | Visual Inspection | PLW-01-C-123 | Level 01 - Office Area | PHOTO-PLU-0123 | Photo | 2 | 40% | 2.44 | 0.976 | 3 | MEP Contractor | CAPA-0053 | P1 | 22/08/2024 | In Progress | Non-compliance / degraded condition observed; corrective action required. Trend indicates aging components; prioritize within next maintenance cycle. | .
Plumbing_Water |  | Grease Trap | PL-GT-019 | Grease trap condition (if any) | Clean; baffles intact | Visual Inspection | PLW-05-A-124 | Roof - Mechanical Area |  | Test Report | 4 | 80% | 2.44 | 1.952 | 3 | MEP Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Plumbing_Water |  | Greywater Treatment Unit | PL-GW-020 | Greywater treatment system test | Operational; quality meets design | Visual Inspection | PLW-02-C-125 | Level 02 - Office Area |  | Checklist | 4 | 80% | 2.44 | 1.952 | 3 | Specialist Vendor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Plumbing_Water | Water Supply | Water Storage Tank | PL-RWH-021 | Rainwater harvesting (if any) | Operational; filtration OK | Visual Inspection | PLW-01-D-126 | Electrical Room - LV | PHOTO-PLU-0126 | Photo | 3 | 60% | 2.44 | 1.464 | 3 | Main Contractor | CAPA-0054 | P2 | 2024-05-09 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Plumbing_Water | Water Supply | Water Storage Tank | PL-INS-022 | Pipe insulation integrity | Complete; no sweating | Visual Inspection | PLW-G-C-127 | Basement B1 - Plantroom |  | Test Report | 4 | 80% | 2.44 | 1.952 | 3 | Specialist Vendor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Plumbing_Water | Backflow Prevention | Pressure Reducing Valve | PL-PRS-023 | PRV settings & stability | Set correctly; no hunting | Visual Inspection | PLW-01-D-128 | Staircase Core |  | Photo | 5 | 100% | 2.44 | 2.44 | 3 | FM Contractor |  | P4 |  | Closed | Inspected and found fully compliant; no observations noted. | .
Plumbing_Water | Water Supply | Water Storage Tank | PL-HMR-024 | Water hammer check | No water hammer; arrestors if needed | Visual Inspection | PLW-B1-D-129 | Staircase Core |  | Checklist | 4 | 80% | 2.44 | 1.952 | 3 | Main Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Plumbing_Water | Fixtures | Water Meter | PL-MTR-025 | Water meters and logging | Accurate; records available | Visual Inspection | PLW-B1-C-130 | Electrical Room - LV |  | Test Report | 5 | 100% | 2.44 | 2.44 | 3 | Specialist Vendor |  | P4 |  | Verified | Inspected and found fully compliant; no observations noted. | .
Plumbing_Water | Water Supply | Water Storage Tank | PL-LEK-026 | Leak detection system (if any) | Sensors functional; alarms tested | Visual Inspection | PLW-01-B-131 | Level 01 - Office Area |  | Test Report | 4 | 80% | 3.25 | 2.6 | 4 | Main Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Plumbing_Water | Stormwater | Plumbing Fixture | PL-FIX-027 | Fixtures operation | No drips; WC flush ok; aerators | Visual Inspection | PLW-03-A-132 | Staircase Core |  | Test Report | 4 | 80% | 2.44 | 1.952 | 3 | FM Contractor |  | P3 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Plumbing_Water | Water Supply | Water Storage Tank | PL-ACC-028 | Maintenance access & safety | Safe access; signage | Visual Inspection | PLW-03-D-133 | Level 01 - Office Area |  | Test Report | 4 | 80% | 2.44 | 1.952 | 3 | MEP Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Plumbing_Water | Water Supply | Water Storage Tank | PL-DOC-029 | O&M manuals complete (plumbing) | Manuals/warranties/test reports | Visual Inspection | PLW-B1-D-134 | Roof - Mechanical Area | PHOTO-PLU-0134 | Photo | 2 | 40% | 2.44 | 0.976 | 3 | FM Contractor | CAPA-0055 | P2 | 2024-05-09 | In Progress | Non-compliance / degraded condition observed; corrective action required. Housekeeping and labeling improvements required. | .
Plumbing_Water | Water Supply | Water Storage Tank | PL-TST-030 | Pressure test certificates | Certificates attached (if executed) | Visual Inspection | PLW-04-A-135 | External - Service Yard | PHOTO-PLU-0135 | Photo | 3 | 60% | 3.25 | 1.95 | 4 | FM Contractor | CAPA-0056 | P3 | 29/09/2024 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
Plumbing_Water | Water Supply | Water Storage Tank | PL-SAN-031 | Sanitary ventilation/vents | Vents clear; no blockages | Visual Inspection | PLW-02-D-136 | Level 01 - Office Area | PHOTO-PLU-0136 | Photo | 2 | 40% | 3.25 | 1.3 | 4 | Specialist Vendor | CAPA-0057 | P2 | 2024-05-09 | In Progress | Non-compliance / degraded condition observed; corrective action required. Evidence captured; recommend rectification and re-test. | .
Plumbing_Water | Water Supply | Water Storage Tank | PL-EXT-032 | External drainage performance | No ponding; proper slopes | Visual Inspection | PLW-01-C-137 | Staircase Core | PHOTO-PLU-0137 | Photo | 3 | 60% | 3.25 | 1.95 | 4 | Specialist Vendor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Plumbing_Water | Water Supply | Water Storage Tank | PL-MOI-033 | Condensation/roof leak linkage | Moisture mapping; causes noted | Visual Inspection | PLW-05-C-138 | Level 03 - Office Area |  | Photo | 5 | 100% | 3.25 | 3.25 | 4 | FM Contractor |  | P4 |  | Verified | Inspected and found fully compliant; no observations noted. | .
Plumbing_Water | Water Supply | Water Storage Tank | PL-RSK-034 | Legionella risk control (if applicable) | Controls documented | Visual Inspection | PLW-02-D-139 | Roof - Mechanical Area |  | Test Report | 4 | 80% | 4.07 | 3.256 | 5 | FM Contractor |  | P3 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Plumbing_Water | Water Supply | Water Storage Tank | PL-RES-035 | Resilience of water supply | Redundancy/backup verified | Visual Inspection | PLW-B1-A-140 | Roof - Mechanical Area |  | Test Report | 4 | 80% | 2.44 | 1.952 | 3 | MEP Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Gas_Systems | Distribution | Gas Meter | GS-MT-001 | Gas meter reading accuracy | Matches supplier readings (±2%) | Visual Inspection | GEN-04-C-141 | External - Service Yard |  | Checklist | 4 | 80% | 2.78 | 2.224 | 4 | FM Contractor |  | P3 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Gas_Systems | Distribution | Gas Meter | GS-GP-002 | Gas piping pressure test | Hold pressure; no leaks detected | Visual Inspection | GEN-05-D-142 | Basement B1 - Plantroom | PHOTO-GAS-0142 | Photo | 3 | 60% | 2.78 | 1.668 | 4 | Owner |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Housekeeping and labeling improvements required. | .
Gas_Systems | Distribution | Gas Meter | GS-IV-003 | Isolation valve operation | All valves operable; labeled | Visual Inspection | GEN-01-C-143 | Electrical Room - LV | PHOTO-GAS-0143 | Photo | 3 | 60% | 2.78 | 1.668 | 4 | MEP Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | .
Gas_Systems | Distribution | Gas Meter | GS-GD-004 | Gas detector calibration/ test | Alarms at setpoint; calibrated recently | Visual Inspection | GEN-03-D-144 | Staircase Core | PHOTO-GAS-0144 | Photo | 3 | 60% | 2.78 | 1.668 | 4 | Specialist Vendor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | .
Gas_Systems | Distribution | Gas Meter | GS-ES-005 | Emergency shutoff test | Valve closes on command/manual | Visual Inspection | GEN-G-A-145 | Level 01 - Office Area |  | Photo | 5 | 100% | 3.47 | 3.47 | 5 | MEP Contractor |  | P4 |  | Verified | Inspected and found fully compliant; no observations noted. | .
Gas_Systems | Distribution | Gas Meter | GS-BH-006 | Gas appliance combustion test | CO levels within safe limits | Visual Inspection | GEN-03-C-146 | Level 03 - Office Area |  | Photo | 4 | 80% | 2.78 | 2.224 | 4 | MEP Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Gas_Systems | Distribution | Gas Meter | GS-KE-007 | Kitchen equipment safety | Flame failure devices functional | Visual Inspection | GEN-G-D-147 | Basement B1 - Plantroom | PHOTO-GAS-0147 | Photo | 1 | 20% | 2.78 | 0.556 | 4 | Owner | CAPA-0058 | P1 | 22/08/2024 | In Progress | Critical deficiency observed; immediate corrective action required to mitigate risk. Preventive maintenance records incomplete; verify PM completion. | .
Gas_Systems | Distribution | Gas Meter | GS-PT-008 | Pressure test certificate | Valid certificate available | Visual Inspection | GEN-04-D-148 | Staircase Core | PHOTO-GAS-0148 | Photo | 2 | 40% | 3.47 | 1.388 | 5 | FM Contractor | CAPA-0059 | P2 | 2024-05-09 | In Progress | Non-compliance / degraded condition observed; corrective action required. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Gas_Systems | Distribution | Gas Meter | GS-AA-009 | Authority approval documents | All required approvals obtained | Visual Inspection | GEN-02-C-149 | Level 01 - Office Area | PHOTO-GAS-0149 | Photo | 3 | 60% | 2.78 | 1.668 | 4 | MEP Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
Gas_Systems | Distribution | Gas Meter | GS-LK-010 | Leak detection survey | No leaks detected with gas sniffer | Visual Inspection | GEN-G-B-150 | Roof - Mechanical Area |  | Test Report | 4 | 80% | 2.78 | 2.224 | 4 | MEP Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Gas_Systems | Distribution | Gas Meter | GS-VE-011 | Ventilation adequacy | Gas room ventilation meets requirements | Visual Inspection | GEN-G-C-151 | External - Service Yard | PHOTO-GAS-0151 | Photo | 3 | 60% | 2.78 | 1.668 | 4 | FM Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Gas_Systems | Distribution | Gas Meter | GS-AC-012 | Access to valves | All valves accessible in emergency | Visual Inspection | GEN-05-A-152 | Ground Floor - Lobby |  | Photo | 4 | 80% | 2.78 | 2.224 | 4 | Specialist Vendor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Gas_Systems | Distribution | Gas Meter | GS-AL-013 | Alarm integration with BMS/Fire | Alarms received at control room | Visual Inspection | GEN-02-C-153 | Level 03 - Office Area |  | Checklist | 4 | 80% | 3.47 | 2.776 | 5 | MEP Contractor |  | P3 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Gas_Systems | Distribution | Gas Meter | GS-RS-014 | Remote shutoff functionality | Can be activated from control room | Visual Inspection | GEN-02-D-154 | Level 02 - Office Area | PHOTO-GAS-0154 | Photo | 3 | 60% | 3.47 | 2.082 | 5 | FM Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Housekeeping and labeling improvements required. | .
Gas_Systems | Distribution | Gas Meter | GS-EF-015 | Efficiency measurement | Combustion efficiency within spec | Visual Inspection | GEN-05-C-155 | Staircase Core |  | Test Report | 4 | 80% | 2.78 | 2.224 | 4 | Owner |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Gas_Systems | Distribution | Gas Meter | GS-MA-016 | Maintenance records | Regular maintenance documented | Visual Inspection | GEN-05-D-156 | Level 02 - Office Area | PHOTO-GAS-0156 | Photo | 3 | 60% | 2.78 | 1.668 | 4 | FM Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Gas_Systems | Distribution | Gas Meter | GS-IN-017 | Insurance inspection compliance | Meets insurer requirements | Visual Inspection | GEN-03-D-157 | Electrical Room - LV | PHOTO-GAS-0157 | Photo | 3 | 60% | 2.78 | 1.668 | 4 | Specialist Vendor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | .
Gas_Systems | Distribution | Gas Meter | GS-TR-018 | Training on gas safety | FM staff trained; records available | Visual Inspection | GEN-02-D-158 | Level 03 - Office Area |  | Test Report | 4 | 80% | 2.78 | 2.224 | 4 | FM Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Gas_Systems | Distribution | Gas Meter | GS-SU-019 | Supply pressure stability | Pressure stable within allowable range | Visual Inspection | GEN-01-A-159 | Parking - Basement | PHOTO-GAS-0159 | Photo | 3 | 60% | 2.78 | 1.668 | 4 | Specialist Vendor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Housekeeping and labeling improvements required. | .
Gas_Systems | Distribution | Gas Meter | GS-CO-020 | Corrosion protection | Piping protected; no corrosion | Visual Inspection | GEN-G-A-160 | Parking - Basement |  | Checklist | 4 | 80% | 2.78 | 2.224 | 4 | Specialist Vendor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Gas_Systems | Distribution | Gas Meter | GS-ID-021 | Valve identification | All valves clearly labeled | Visual Inspection | GEN-03-A-161 | Basement B1 - Plantroom |  | Photo | 4 | 80% | 2.78 | 2.224 | 4 | MEP Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Gas_Systems | Distribution | Gas Meter | GS-LO-022 | Location of detectors | Detectors in correct locations per risk | Visual Inspection | GEN-G-D-162 | External - Service Yard | PHOTO-GAS-0162 | Photo | 3 | 60% | 2.78 | 1.668 | 4 | FM Contractor | CAPA-0060 | P3 | 29/09/2024 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Gas_Systems | Distribution | Gas Meter | GS-TE-023 | Testing frequency | Tested quarterly; records available | Visual Inspection | GEN-02-A-163 | Roof - Mechanical Area | PHOTO-GAS-0163 | Photo | 3 | 60% | 2.78 | 1.668 | 4 | Specialist Vendor | CAPA-0061 | P2 | 2024-05-09 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Gas_Systems | Distribution | Gas Meter | GS-FL-024 | Flue gas analysis | Emission levels within limits | Visual Inspection | GEN-04-B-164 | Basement B1 - Plantroom |  | Test Report | 5 | 100% | 2.78 | 2.78 | 4 | MEP Contractor |  | P4 |  | Verified | Inspected and found fully compliant; no observations noted. | .
Gas_Systems | Distribution | Gas Meter | GS-CL-025 | Cleanliness of burners | Burners clean; flame pattern good | Visual Inspection | GEN-G-A-165 | Electrical Room - LV | PHOTO-GAS-0165 | Photo | 2 | 40% | 2.78 | 1.112 | 4 | FM Contractor | CAPA-0062 | P2 | 2024-05-09 | In Progress | Non-compliance / degraded condition observed; corrective action required. Trend indicates aging components; prioritize within next maintenance cycle. | .
Gas_Systems | Distribution | Gas Meter | GS-RE-026 | Regulator station condition | Secure; protected; gauges working | Visual Inspection | GEN-03-C-166 | Electrical Room - LV |  | Test Report | 4 | 80% | 2.78 | 2.224 | 4 | Specialist Vendor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Gas_Systems | Distribution | Gas Meter | GS-SO-027 | SOPs for gas emergencies | Procedures documented; accessible | Visual Inspection | GEN-03-D-167 | Level 02 - Office Area | PHOTO-GAS-0167 | Photo | 1 | 20% | 2.78 | 0.556 | 4 | MEP Contractor | CAPA-0063 | P1 | 22/08/2024 | In Progress | Critical deficiency observed; immediate corrective action required to mitigate risk. Trend indicates aging components; prioritize within next maintenance cycle. | .
Gas_Systems | Distribution | Gas Meter | GS-RD-028 | Remote reading capability | If applicable, remote reading works | Visual Inspection | GEN-01-D-168 | Roof - Mechanical Area |  | Test Report | 5 | 100% | 2.78 | 2.78 | 4 | MEP Contractor |  | P4 |  | Verified | Inspected and found fully compliant; no observations noted. | .
Gas_Systems | Distribution | Gas Meter | GS-IN-029 | Insulation where required | Pipes insulated per design | Visual Inspection | GEN-01-A-169 | Level 03 - Office Area | PHOTO-GAS-0169 | Photo | 3 | 60% | 2.78 | 1.668 | 4 | Specialist Vendor | CAPA-0064 | P2 | 2024-05-09 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Housekeeping and labeling improvements required. | .
Gas_Systems | Distribution | Gas Meter | GS-OP-030 | Operational procedures | Lockout/tagout procedures exist | Visual Inspection | GEN-G-A-170 | External - Service Yard |  | Test Report | 4 | 80% | 2.78 | 2.224 | 4 | Main Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Gas_Systems | Distribution | Gas Meter | GS-BU-031 | Battery backup | Detectors have battery backup | Visual Inspection | GEN-04-D-171 | Ground Floor - Lobby |  | Test Report | 5 | 100% | 2.78 | 2.78 | 4 | FM Contractor |  | P4 |  | Closed | Inspected and found fully compliant; no observations noted. | .
Gas_Systems | Distribution | Gas Meter | GS-VI-032 | Visual indicators | Shutoff status clearly visible | Visual Inspection | GEN-01-C-172 | Basement B1 - Plantroom |  | Photo | 5 | 100% | 2.78 | 2.78 | 4 | MEP Contractor |  | P4 |  | Closed | Inspected and found fully compliant; no observations noted. | .
Gas_Systems | Distribution | Gas Meter | GS-NO-033 | Noise levels | Burner noise within acceptable limits | Visual Inspection | GEN-B1-D-173 | Electrical Room - LV | PHOTO-GAS-0173 | Photo | 3 | 60% | 2.78 | 1.668 | 4 | MEP Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Housekeeping and labeling improvements required. | .
Gas_Systems | Distribution | Gas Meter | GS-SA-034 | Safety signage | All required safety signs present | Visual Inspection | GEN-01-D-174 | Staircase Core |  | Test Report | 4 | 80% | 2.78 | 2.224 | 4 | Main Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Gas_Systems | Distribution | Gas Meter | GS-DO-035 | Documentation completeness | All gas-related documents filed | Visual Inspection | GEN-01-B-175 | Electrical Room - LV | PHOTO-GAS-0175 | Photo | 3 | 60% | 2.78 | 1.668 | 4 | FM Contractor | CAPA-0065 | P2 | 2024-05-09 | Open | Condition acceptable but requires attention; minor deficiencies observed. Evidence captured; recommend rectification and re-test. | .
Vertical_Transportation | Elevators | Elevator (Passenger / Service) | VT-EL-001 | Elevator inspection certificate | Valid certificate; within date | Visual Inspection | VT-05-D-176 | Staircase Core |  | Checklist | 4 | 80% | 3.29 | 2.632 | 5 | FM Contractor |  | P3 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Vertical_Transportation | Elevators | Elevator (Passenger / Service) | VT-EC-002 | Controller operation test | Smooth acceleration/deceleration | Visual Inspection | VT-01-D-177 | Level 02 - Office Area | PHOTO-VER-0177 | Photo | 3 | 60% | 2.63 | 1.578 | 4 | FM Contractor | CAPA-0066 | P2 | 2024-05-09 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Housekeeping and labeling improvements required. | .
Vertical_Transportation | Elevators | Elevator (Passenger / Service) | VT-DO-003 | Door operation safety test | Reopen on obstruction; timing correct | Visual Inspection | VT-02-C-178 | Level 01 - Office Area |  | Checklist | 4 | 80% | 3.29 | 2.632 | 5 | Specialist Vendor |  | P3 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Vertical_Transportation | Elevators | Elevator (Passenger / Service) | VT-SD-004 | Safety device test | Governor, buffers, brakes functional | Visual Inspection | VT-02-B-179 | Electrical Room - LV |  | Test Report | 4 | 80% | 3.29 | 2.632 | 5 | Specialist Vendor |  | P3 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Vertical_Transportation | Elevators | Elevator (Passenger / Service) | VT-OG-005 | Overspeed governor test | Activates at set speed | Visual Inspection | VT-03-D-180 | Staircase Core |  | Test Report | 4 | 80% | 3.29 | 2.632 | 5 | Specialist Vendor |  | P3 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Vertical_Transportation | Elevators | Elevator (Passenger / Service) | VT-BS-006 | Brake system test | Holds load; stops smoothly | Visual Inspection | VT-05-D-181 | Ground Floor - Lobby | PHOTO-VER-0181 | Photo | 3 | 60% | 3.29 | 1.974 | 5 | Specialist Vendor | CAPA-0067 | P2 | 2024-05-09 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Evidence captured; recommend rectification and re-test. | .
Vertical_Transportation | Elevators | Elevator (Passenger / Service) | VT-EI-007 | Emergency intercom test | Clear communication; auto-dial works | Visual Inspection | VT-03-D-182 | Level 03 - Office Area |  | Test Report | 4 | 80% | 3.29 | 2.632 | 5 | Specialist Vendor |  | P3 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Vertical_Transportation | Elevators | Elevator (Passenger / Service) | VT-MR-008 | Machine room inspection | Clean; well-lit; ventilated | Visual Inspection | VT-03-A-183 | Ground Floor - Lobby |  | Checklist | 4 | 80% | 2.63 | 2.104 | 4 | Specialist Vendor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Vertical_Transportation | Elevators | Elevator (Passenger / Service) | VT-PE-009 | Pit inspection | Clean; dry; no debris | Visual Inspection | VT-05-D-184 | Parking - Basement |  | Photo | 4 | 80% | 2.63 | 2.104 | 4 | FM Contractor | CAPA-0068 | P3 | 29/09/2024 | In Progress | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Vertical_Transportation | Elevators | Elevator (Passenger / Service) | VT-TC-010 | Traveling cable condition | No visible damage; movement free | Visual Inspection | VT-03-D-185 | Staircase Core | PHOTO-VER-0185 | Photo | 2 | 40% | 2.63 | 1.052 | 4 | Specialist Vendor | CAPA-0069 | P1 | 22/08/2024 | Open | Non-compliance / degraded condition observed; corrective action required. Trend indicates aging components; prioritize within next maintenance cycle. | .
Vertical_Transportation | Elevators | Elevator (Passenger / Service) | VT-ES-011 | Escalator operation test | Smooth start/stop; handrail sync | Visual Inspection | VT-02-B-186 | Level 02 - Office Area |  | Checklist | 4 | 80% | 2.63 | 2.104 | 4 | Specialist Vendor |  | P3 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Vertical_Transportation | Elevators | Elevator (Passenger / Service) | VT-MW-012 | Moving walkway test | Constant speed; no vibrations | Visual Inspection | VT-05-A-187 | Level 02 - Office Area | PHOTO-VER-0187 | Photo | 2 | 40% | 2.63 | 1.052 | 4 | Specialist Vendor | CAPA-0070 | P2 | 2024-05-09 | Open | Non-compliance / degraded condition observed; corrective action required. Preventive maintenance records incomplete; verify PM completion. | .
Vertical_Transportation | Elevators | Elevator (Passenger / Service) | VT-HR-013 | Handrail safety test | Moves with steps; no entrapment | Visual Inspection | VT-05-A-188 | Level 01 - Office Area |  | Test Report | 4 | 80% | 3.29 | 2.632 | 5 | Specialist Vendor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Vertical_Transportation | Elevators | Elevator (Passenger / Service) | VT-DM-014 | Drive motor condition | No unusual noise; temperature ok | Visual Inspection | VT-03-B-189 | Parking - Basement |  | Checklist | 4 | 80% | 2.63 | 2.104 | 4 | FM Contractor |  | P3 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Vertical_Transportation | Elevators | Elevator (Passenger / Service) | VT-ES-015 | Emergency stop button test | Stops immediately; resets correctly | Visual Inspection | VT-01-D-190 | Parking - Basement | PHOTO-VER-0190 | Photo | 3 | 60% | 3.29 | 1.974 | 5 | Specialist Vendor | CAPA-0071 | P2 | 2024-05-09 | Open | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Vertical_Transportation | Elevators | Elevator (Passenger / Service) | VT-CP-016 | Comb plate safety check | Gaps within tolerance; no sharp edges | Visual Inspection | VT-B1-D-191 | Parking - Basement |  | Test Report | 4 | 80% | 3.29 | 2.632 | 5 | FM Contractor |  | P3 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Vertical_Transportation | Elevators | Elevator (Passenger / Service) | VT-IC-017 | Annual inspection certificate | Current; all items passed | Visual Inspection | VT-05-B-192 | Basement B1 - Plantroom |  | Checklist | 4 | 80% | 3.29 | 2.632 | 5 | Specialist Vendor |  | P3 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Vertical_Transportation | Elevators | Elevator (Passenger / Service) | VT-ML-018 | Maintenance logbook completeness | All PMs documented; up-to-date | Visual Inspection | VT-04-B-193 | Electrical Room - LV |  | Photo | 4 | 80% | 2.63 | 2.104 | 4 | FM Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Vertical_Transportation | Elevators | Elevator (Passenger / Service) | VT-SE-019 | Service elevator load test | Rated capacity handled safely | Visual Inspection | VT-G-D-194 | Level 02 - Office Area |  | Test Report | 4 | 80% | 2.63 | 2.104 | 4 | Specialist Vendor |  | P3 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Vertical_Transportation | Elevators | Elevator (Passenger / Service) | VT-RS-020 | Rescue operation procedure | Rescue procedure documented; staff trained | Visual Inspection | VT-02-A-195 | Electrical Room - LV |  | Checklist | 5 | 100% | 2.63 | 2.63 | 4 | Specialist Vendor |  | P4 |  | Verified | Inspected and found fully compliant; no observations noted. | .
Vertical_Transportation | Elevators | Elevator (Passenger / Service) | VT-LV-021 | Leveling accuracy | Stops within ±10mm of floor level | Visual Inspection | VT-04-D-196 | Level 03 - Office Area |  | Photo | 5 | 100% | 2.63 | 2.63 | 4 | FM Contractor |  | P4 |  | Verified | Inspected and found fully compliant; no observations noted. | .
Vertical_Transportation | Elevators | Elevator (Passenger / Service) | VT-DT-022 | Door timing adjustment | Opening/closing times as per spec | Visual Inspection | VT-01-C-197 | Electrical Room - LV | PHOTO-VER-0197 | Photo | 3 | 60% | 2.63 | 1.578 | 4 | Specialist Vendor | CAPA-0072 | P2 | 2024-05-09 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | .
Vertical_Transportation | Elevators | Elevator (Passenger / Service) | VT-SF-023 | Step/skirt panel gaps | Within safety standards (≤4mm) | Visual Inspection | VT-B1-A-198 | Ground Floor - Lobby |  | Test Report | 4 | 80% | 2.63 | 2.104 | 4 | FM Contractor |  | P3 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Vertical_Transportation | Elevators | Elevator (Passenger / Service) | VT-BL-024 | Balustrade integrity | Secure; no cracks/damage | Visual Inspection | VT-03-D-199 | Roof - Mechanical Area |  | Photo | 4 | 80% | 2.63 | 2.104 | 4 | Specialist Vendor |  | P3 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Vertical_Transportation | Elevators | Elevator (Passenger / Service) | VT-RP-025 | Repair history review | Recurring issues addressed | Visual Inspection | VT-03-C-200 | Basement B1 - Plantroom |  | Test Report | 5 | 100% | 2.63 | 2.63 | 4 | Specialist Vendor |  | P4 |  | Closed | Inspected and found fully compliant; no observations noted. | .
Vertical_Transportation | Elevators | Elevator (Passenger / Service) | VT-TH-026 | Machine room temperature | Within manufacturer limits (≤40°C) | Visual Inspection | VT-G-C-201 | Roof - Mechanical Area |  | Checklist | 4 | 80% | 2.63 | 2.104 | 4 | Specialist Vendor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Vertical_Transportation | Elevators | Elevator (Passenger / Service) | VT-LT-027 | Pit lighting/ventilation | Functional; adequate | Visual Inspection | VT-05-A-202 | Ground Floor - Lobby |  | Checklist | 4 | 80% | 2.63 | 2.104 | 4 | FM Contractor |  | P3 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Vertical_Transportation | Elevators | Elevator (Passenger / Service) | VT-HC-028 | Handrail cleanliness/condition | Clean; no damage; moves smoothly | Visual Inspection | VT-04-C-203 | External - Service Yard |  | Photo | 5 | 100% | 2.63 | 2.63 | 4 | Specialist Vendor |  | P4 |  | Verified | Inspected and found fully compliant; no observations noted. | .
Vertical_Transportation | Elevators | Elevator (Passenger / Service) | VT-VB-029 | Vibration/noise levels | Within acceptable limits | Visual Inspection | VT-G-C-204 | Basement B1 - Plantroom |  | Photo | 5 | 100% | 2.63 | 2.63 | 4 | Specialist Vendor |  | P4 |  | Verified | Inspected and found fully compliant; no observations noted. | .
Vertical_Transportation | Elevators | Elevator (Passenger / Service) | VT-EL-030 | Edge lighting (if any) | Functional; evenly illuminated | Visual Inspection | VT-G-D-205 | Staircase Core |  | Checklist | 4 | 80% | 2.63 | 2.104 | 4 | Specialist Vendor |  | P3 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Vertical_Transportation | Elevators | Elevator (Passenger / Service) | VT-SP-031 | Spare parts availability | Critical spares on site | Visual Inspection | VT-01-D-206 | Roof - Mechanical Area |  | Photo | 5 | 100% | 2.63 | 2.63 | 4 | Specialist Vendor |  | P4 |  | Closed | Inspected and found fully compliant; no observations noted. | .
Vertical_Transportation | Elevators | Elevator (Passenger / Service) | VT-CC-032 | Control cable condition | No damage; connections secure | Visual Inspection | VT-G-D-207 | Ground Floor - Lobby |  | Test Report | 4 | 80% | 2.63 | 2.104 | 4 | FM Contractor |  | P3 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Vertical_Transportation | Elevators | Elevator (Passenger / Service) | VT-PS-033 | Pit stop switch test | Stops elevator when activated | Visual Inspection | VT-B1-A-208 | Level 03 - Office Area |  | Checklist | 4 | 80% | 2.63 | 2.104 | 4 | Specialist Vendor |  | P3 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Vertical_Transportation | Elevators | Elevator (Passenger / Service) | VT-GT-034 | Governor tension test | Tension as per manufacturer spec | Visual Inspection | VT-03-D-209 | Ground Floor - Lobby |  | Photo | 4 | 80% | 3.29 | 2.632 | 5 | Specialist Vendor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Vertical_Transportation | Elevators | Elevator (Passenger / Service) | VT-BL-035 | Brake lining wear check | Within acceptable wear limits | Visual Inspection | VT-04-B-210 | External - Service Yard |  | Test Report | 4 | 80% | 3.29 | 2.632 | 5 | Specialist Vendor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
BMS_Controls | Central System | BMS Server | BM-SV-001 | BMS server operation | CPU/memory usage normal; no errors | Visual Inspection | GEN-G-A-211 | Level 01 - Office Area | PHOTO-BMS-0211 | Photo | 2 | 40% | 2.54 | 1.016 | 3 | FM Contractor | CAPA-0073 | P2 | 2024-05-09 | In Progress | Non-compliance / degraded condition observed; corrective action required. Preventive maintenance records incomplete; verify PM completion. | .
BMS_Controls | Central System | BMS Server | BM-WS-002 | Workstation functionality | All software operational; responsive | Visual Inspection | GEN-02-A-212 | Level 01 - Office Area | PHOTO-BMS-0212 | Photo | 2 | 40% | 2.54 | 1.016 | 3 | MEP Contractor | CAPA-0074 | P1 | 22/08/2024 | In Progress | Non-compliance / degraded condition observed; corrective action required. Housekeeping and labeling improvements required. | .
BMS_Controls | Central System | BMS Server | BM-NS-003 | Network connectivity test | All nodes communicating; no packet loss | Visual Inspection | GEN-02-C-213 | Parking - Basement |  | Test Report | 5 | 100% | 2.54 | 2.54 | 3 | Specialist Vendor |  | P4 |  | Closed | Inspected and found fully compliant; no observations noted. | .
BMS_Controls | Central System | BMS Server | BM-UP-004 | BMS UPS test | Autonomy meets requirement; transfer smooth | Visual Inspection | GEN-03-B-214 | Roof - Mechanical Area |  | Checklist | 4 | 80% | 2.54 | 2.032 | 3 | FM Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
BMS_Controls | Central System | BMS Server | BM-SP-005 | Control sequence verification | All sequences operating as programmed | Visual Inspection | GEN-03-B-215 | Staircase Core |  | Photo | 4 | 80% | 2.54 | 2.032 | 3 | Main Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
BMS_Controls | Central System | BMS Server | BM-TS-006 | Time schedule operation | Schedules activate/deactivate correctly | Visual Inspection | GEN-04-D-216 | Level 01 - Office Area |  | Test Report | 4 | 80% | 2.54 | 2.032 | 3 | Specialist Vendor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
BMS_Controls | Central System | BMS Server | BM-AC-007 | Alarm generation test | Alarms trigger at setpoints; priorities correct | Visual Inspection | GEN-03-D-217 | Staircase Core | PHOTO-BMS-0217 | Photo | 2 | 40% | 2.54 | 1.016 | 3 | FM Contractor | CAPA-0075 | P1 | 22/08/2024 | In Progress | Non-compliance / degraded condition observed; corrective action required. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
BMS_Controls | Central System | BMS Server | BM-TD-008 | Trend logging verification | Data logging continuously; accessible | Visual Inspection | GEN-G-A-218 | External - Service Yard |  | Test Report | 4 | 80% | 2.54 | 2.032 | 3 | MEP Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
BMS_Controls | Central System | BMS Server | BM-DC-009 | DDC controller health | All I/O points responsive; no comms errors | Visual Inspection | GEN-01-B-219 | Staircase Core | PHOTO-BMS-0219 | Photo | 3 | 60% | 2.54 | 1.524 | 3 | FM Contractor | CAPA-0076 | P2 | 2024-05-09 | Open | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | .
BMS_Controls | Central System | BMS Server | BM-SE-010 | Sensor calibration check | Readings within ±5% of reference | Visual Inspection | GEN-02-A-220 | Level 03 - Office Area | PHOTO-BMS-0220 | Photo | 2 | 40% | 2.54 | 1.016 | 3 | FM Contractor | CAPA-0077 | P2 | 2024-05-09 | In Progress | Non-compliance / degraded condition observed; corrective action required. Evidence captured; recommend rectification and re-test. | .
BMS_Controls | Central System | BMS Server | BM-AC-011 | Actuator operation test | Full stroke; responds to commands | Visual Inspection | GEN-02-B-221 | Staircase Core |  | Checklist | 4 | 80% | 2.54 | 2.032 | 3 | FM Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
BMS_Controls | Central System | BMS Server | BM-FI-012 | Fire alarm interface test | Fire signals received; actions triggered | Visual Inspection | GEN-B1-C-222 | Ground Floor - Lobby | PHOTO-BMS-0222 | Photo | 3 | 60% | 4.24 | 2.544 | 5 | Specialist Vendor | CAPA-0078 | P3 | 29/09/2024 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
BMS_Controls | Central System | BMS Server | BM-HI-013 | HVAC control verification | All HVAC points controllable via BMS | Visual Inspection | GEN-02-B-223 | Parking - Basement | PHOTO-BMS-0223 | Photo | 3 | 60% | 2.54 | 1.524 | 3 | FM Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | .
BMS_Controls | Central System | BMS Server | BM-LI-014 | Lighting control test | Lighting schedules/zones work correctly | Visual Inspection | GEN-02-A-224 | Level 02 - Office Area | PHOTO-BMS-0224 | Photo | 0 | 0% | 2.54 | 0 | 3 | MEP Contractor |  | - |  | N/A | Not applicable for this building / scope. | .
BMS_Controls | Central System | BMS Server | BM-PI-015 | Power metering interface | Meter data logged; alarms generated | Visual Inspection | GEN-01-C-225 | Level 02 - Office Area | PHOTO-BMS-0225 | Photo | 3 | 60% | 2.54 | 1.524 | 3 | MEP Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
BMS_Controls | Central System | BMS Server | BM-UA-016 | User access levels | Different access levels functional | Visual Inspection | GEN-03-A-226 | Roof - Mechanical Area | PHOTO-BMS-0226 | Photo | 2 | 40% | 2.54 | 1.016 | 3 | MEP Contractor | CAPA-0079 | P2 | 2024-05-09 | In Progress | Non-compliance / degraded condition observed; corrective action required. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
BMS_Controls | Central System | BMS Server | BM-NS-017 | Network security check | Segmented as per design; firewalls active | Visual Inspection | GEN-B1-B-227 | Level 03 - Office Area | PHOTO-BMS-0227 | Photo | 3 | 60% | 4.24 | 2.544 | 5 | MEP Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
BMS_Controls | Central System | BMS Server | BM-PP-018 | Password policy enforcement | Complex passwords; regular changes | Visual Inspection | GEN-G-D-228 | Staircase Core | PHOTO-BMS-0228 | Photo | 2 | 40% | 4.24 | 1.696 | 5 | MEP Contractor |  | P2 |  | Closed | Non-compliance / degraded condition observed; corrective action required. Trend indicates aging components; prioritize within next maintenance cycle. | .
BMS_Controls | Central System | BMS Server | BM-CR-019 | Commissioning report availability | Complete report; all points signed off | Visual Inspection | GEN-05-C-229 | Basement B1 - Plantroom | PHOTO-BMS-0229 | Photo | 3 | 60% | 2.54 | 1.524 | 3 | Specialist Vendor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
BMS_Controls | Central System | BMS Server | BM-AH-020 | Alarm history retention | ≥90 days history available | Visual Inspection | GEN-02-D-230 | Electrical Room - LV | PHOTO-BMS-0230 | Photo | 3 | 60% | 2.54 | 1.524 | 3 | MEP Contractor | CAPA-0080 | P2 | 2024-05-09 | Open | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
BMS_Controls | Central System | BMS Server | BM-BK-021 | Database backup test | Backup successful; restore verified | Visual Inspection | GEN-03-A-231 | External - Service Yard | PHOTO-BMS-0231 | Photo | 3 | 60% | 3.39 | 2.034 | 4 | Specialist Vendor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
BMS_Controls | Central System | BMS Server | BM-VE-022 | Software version control | Latest version; documented changes | Visual Inspection | GEN-03-B-232 | Parking - Basement |  | Photo | 4 | 80% | 2.54 | 2.032 | 3 | Specialist Vendor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
BMS_Controls | Central System | BMS Server | BM-EN-023 | Energy trending accuracy | Matches utility meter readings (±2%) | Visual Inspection | GEN-05-B-233 | Level 02 - Office Area | PHOTO-BMS-0233 | Photo | 2 | 40% | 2.54 | 1.016 | 3 | Main Contractor | CAPA-0081 | P1 | 22/08/2024 | In Progress | Non-compliance / degraded condition observed; corrective action required. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
BMS_Controls | Central System | BMS Server | BM-PM-024 | Preventive maintenance execution | PM completed on schedule | Visual Inspection | GEN-05-B-234 | Basement B1 - Plantroom |  | Test Report | 5 | 100% | 2.54 | 2.54 | 3 | MEP Contractor |  | P4 |  | Closed | Inspected and found fully compliant; no observations noted. | .
BMS_Controls | Central System | BMS Server | BM-CL-025 | Sensor location verification | Locations match drawings; accessible | Visual Inspection | GEN-G-D-235 | Basement B1 - Plantroom | PHOTO-BMS-0235 | Photo | 3 | 60% | 2.54 | 1.524 | 3 | Owner |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
BMS_Controls | Central System | BMS Server | BM-DR-026 | Disaster recovery test | System restores from backup | Visual Inspection | GEN-05-B-236 | Parking - Basement | PHOTO-BMS-0236 | Photo | 3 | 60% | 3.39 | 2.034 | 4 | FM Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | .
BMS_Controls | Central System | BMS Server | BM-OP-027 | Operator training records | FM staff trained; competency verified | Visual Inspection | GEN-04-C-237 | Electrical Room - LV |  | Checklist | 5 | 100% | 2.54 | 2.54 | 3 | MEP Contractor |  | P4 |  | Closed | Inspected and found fully compliant; no observations noted. | .
BMS_Controls | Central System | BMS Server | BM-DO-028 | Documentation availability | All manuals, drawings accessible | Visual Inspection | GEN-05-A-238 | Staircase Core |  | Checklist | 4 | 80% | 2.54 | 2.032 | 3 | MEP Contractor |  | P3 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
BMS_Controls | Central System | BMS Server | BM-RE-029 | Redundancy verification | Failover to backup server works | Visual Inspection | GEN-03-D-239 | Roof - Mechanical Area | PHOTO-BMS-0239 | Photo | 3 | 60% | 3.39 | 2.034 | 4 | FM Contractor | CAPA-0082 | P3 | 29/09/2024 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Evidence captured; recommend rectification and re-test. | .
BMS_Controls | Central System | BMS Server | BM-AU-030 | Audit trail functionality | All user actions logged | Visual Inspection | GEN-02-D-240 | Basement B1 - Plantroom | PHOTO-BMS-0240 | Photo | 3 | 60% | 2.54 | 1.524 | 3 | FM Contractor | CAPA-0083 | P2 | 2024-05-09 | Open | Condition acceptable but requires attention; minor deficiencies observed. Housekeeping and labeling improvements required. | .
BMS_Controls | Central System | BMS Server | BM-SC-031 | System security scan | No vulnerabilities detected | Visual Inspection | GEN-04-B-241 | Basement B1 - Plantroom |  | Checklist | 4 | 80% | 4.24 | 3.392 | 5 | FM Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
BMS_Controls | Central System | BMS Server | BM-EX-032 | External access security | VPN/remote access secure | Visual Inspection | GEN-B1-B-242 | Electrical Room - LV | PHOTO-BMS-0242 | Photo | 3 | 60% | 4.24 | 2.544 | 5 | MEP Contractor | CAPA-0084 | P2 | 2024-05-09 | Open | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
BMS_Controls | Central System | BMS Server | BM-PT-033 | Point database accuracy | All points match as-built drawings | Visual Inspection | GEN-04-B-243 | Electrical Room - LV |  | Photo | 5 | 100% | 2.54 | 2.54 | 3 | Owner |  | P4 |  | Closed | Inspected and found fully compliant; no observations noted. | .
BMS_Controls | Central System | BMS Server | BM-RS-034 | Response time to alarms | Alarms acknowledged within 5 minutes | Visual Inspection | GEN-02-B-244 | Level 01 - Office Area | PHOTO-BMS-0244 | Photo | 3 | 60% | 2.54 | 1.524 | 3 | Main Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
BMS_Controls | Central System | BMS Server | BM-KP-035 | KPI reporting capability | All required reports generated | Visual Inspection | GEN-05-B-245 | Ground Floor - Lobby | PHOTO-BMS-0245 | Photo | 2 | 40% | 2.54 | 1.016 | 3 | Main Contractor | CAPA-0085 | P2 | 2024-05-09 | Open | Non-compliance / degraded condition observed; corrective action required. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
ELV_Systems | Time Systems | Master Clock | EL-MC-001 | Master clock synchronization | All slave clocks show correct time | Visual Inspection | GEN-05-B-246 | Level 02 - Office Area |  | Checklist | 4 | 80% | 3.49 | 2.792 | 3 | Owner |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
ELV_Systems | Time Systems | Master Clock | EL-TS-002 | Time sync accuracy | Within ±1 second of reference | Visual Inspection | GEN-04-D-247 | Level 03 - Office Area | PHOTO-ELV-0247 | Photo | 3 | 60% | 3.49 | 2.094 | 3 | FM Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | .
ELV_Systems | Time Systems | Master Clock | EL-HD-003 | Headend equipment operation | All channels clear; no signal loss | Visual Inspection | GEN-03-A-248 | Roof - Mechanical Area | PHOTO-ELV-0248 | Photo | 2 | 40% | 3.49 | 1.396 | 3 | MEP Contractor | CAPA-0086 | P2 | 2024-05-09 | In Progress | Non-compliance / degraded condition observed; corrective action required. Housekeeping and labeling improvements required. | .
ELV_Systems | Time Systems | Master Clock | EL-RD-004 | Receiver/decoder test | All units operational; channels accessible | Visual Inspection | GEN-B1-C-249 | Level 02 - Office Area |  | Photo | 4 | 80% | 3.49 | 2.792 | 3 | FM Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
ELV_Systems | Time Systems | Master Clock | EL-GW-007 | Gateway communication test | All protocols communicating | Visual Inspection | GEN-02-D-250 | Ground Floor - Lobby |  | Test Report | 4 | 80% | 3.49 | 2.792 | 3 | MEP Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
ELV_Systems | Time Systems | Master Clock | EL-IS-008 | Integration server operation | Data exchange between systems working | Visual Inspection | GEN-03-A-251 | Level 03 - Office Area |  | Test Report | 5 | 100% | 3.49 | 3.49 | 3 | MEP Contractor |  | P4 |  | Closed | Inspected and found fully compliant; no observations noted. | .
ELV_Systems | Time Systems | Master Clock | EL-EM-009 | Submeter data collection | All meters reporting; data accurate | Visual Inspection | GEN-B1-D-252 | External - Service Yard | PHOTO-ELV-0252 | Photo | 2 | 40% | 3.49 | 1.396 | 3 | FM Contractor | CAPA-0087 | P2 | 2024-05-09 | Open | Non-compliance / degraded condition observed; corrective action required. Evidence captured; recommend rectification and re-test. | .
ELV_Systems | Time Systems | Master Clock | EL-ED-010 | Energy dashboard functionality | Real-time display; historical data accessible | Visual Inspection | GEN-02-C-253 | Staircase Core | PHOTO-ELV-0253 | Photo | 0 | 0% | 3.49 | 0 | 3 | Specialist Vendor |  | - |  | N/A | Not applicable for this building / scope. | .
ELV_Systems | Time Systems | Master Clock | EL-BC-011 | Battery backup for master clock | Maintains time during power loss | Visual Inspection | GEN-04-A-254 | Basement B1 - Plantroom |  | Checklist | 4 | 80% | 4.65 | 3.72 | 4 | FM Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
ELV_Systems | Time Systems | Master Clock | EL-SG-012 | Signal quality measurement | Signal strength/quality within limits | Visual Inspection | GEN-B1-D-255 | External - Service Yard | PHOTO-ELV-0255 | Photo | 3 | 60% | 3.49 | 2.094 | 3 | MEP Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Evidence captured; recommend rectification and re-test. | .
ELV_Systems | Time Systems | Master Clock | EL-CP-013 | Content protection (if applicable) | Encryption/access control functional | Visual Inspection | GEN-G-A-256 | Electrical Room - LV | PHOTO-ELV-0256 | Photo | 3 | 60% | 3.49 | 2.094 | 3 | FM Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
ELV_Systems | Time Systems | Master Clock | EL-PR-016 | Protocol conversion accuracy | Data translation correct; no errors | Visual Inspection | GEN-G-C-257 | Level 02 - Office Area | PHOTO-ELV-0257 | Photo | 3 | 60% | 3.49 | 2.094 | 3 | MEP Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Housekeeping and labeling improvements required. | .
ELV_Systems | Time Systems | Master Clock | EL-SC-017 | Scalability verification | Can add new devices/systems | Visual Inspection | GEN-02-A-258 | Electrical Room - LV |  | Checklist | 4 | 80% | 3.49 | 2.792 | 3 | FM Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
ELV_Systems | Time Systems | Master Clock | EL-AL-018 | Alarm generation for consumption | Alarms trigger at set thresholds | Visual Inspection | GEN-04-B-259 | Electrical Room - LV | PHOTO-ELV-0259 | Photo | 0 | 0% | 3.49 | 0 | 3 | FM Contractor |  | - |  | N/A | Not applicable for this building / scope. | .
ELV_Systems | Time Systems | Master Clock | EL-RP-019 | Reporting capability | Custom reports generated correctly | Visual Inspection | GEN-04-B-260 | Level 01 - Office Area |  | Photo | 4 | 80% | 3.49 | 2.792 | 3 | Owner |  | P3 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
ELV_Systems | Time Systems | Master Clock | EL-NT-020 | NTP server connection | Connected to reliable time source | Visual Inspection | GEN-05-C-261 | Ground Floor - Lobby | PHOTO-ELV-0261 | Photo | 3 | 60% | 3.49 | 2.094 | 3 | FM Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | .
ELV_Systems | Time Systems | Master Clock | EL-MA-021 | Maintenance access | All equipment accessible for service | Visual Inspection | GEN-04-C-262 | Ground Floor - Lobby | PHOTO-ELV-0262 | Photo | 3 | 60% | 3.49 | 2.094 | 3 | Owner |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
ELV_Systems | Time Systems | Master Clock | EL-FW-024 | Firmware version control | Latest firmware; documented | Visual Inspection | GEN-04-D-263 | Ground Floor - Lobby |  | Test Report | 4 | 80% | 3.49 | 2.792 | 3 | MEP Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
ELV_Systems | Time Systems | Master Clock | EL-BK-025 | Database backup | Regular backups; restore tested | Visual Inspection | GEN-04-C-264 | Roof - Mechanical Area | PHOTO-ELV-0264 | Photo | 3 | 60% | 4.65 | 2.79 | 4 | Main Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
ELV_Systems | Time Systems | Master Clock | EL-CL-026 | Calibration certificates | All meters calibrated; certificates available | Visual Inspection | GEN-01-D-265 | Ground Floor - Lobby | PHOTO-ELV-0265 | Photo | 3 | 60% | 3.49 | 2.094 | 3 | FM Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | .
ELV_Systems | Time Systems | Master Clock | EL-EX-027 | Export functionality | Data export to CSV/Excel works | Visual Inspection | GEN-G-C-266 | External - Service Yard | PHOTO-ELV-0266 | Photo | 3 | 60% | 3.49 | 2.094 | 3 | Main Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
ELV_Systems | Time Systems | Master Clock | EL-DS-028 | Daylight saving adjustment | Automatic adjustment works | Visual Inspection | GEN-05-B-267 | Basement B1 - Plantroom | PHOTO-ELV-0267 | Photo | 3 | 60% | 3.49 | 2.094 | 3 | MEP Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
ELV_Systems | Time Systems | Master Clock | EL-RM-029 | Remote management | Can manage units remotely | Visual Inspection | GEN-05-B-268 | Ground Floor - Lobby |  | Photo | 4 | 80% | 3.49 | 2.792 | 3 | FM Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
ELV_Systems | Time Systems | Master Clock | EL-MT-031 | MTBF monitoring | Mean time between failures tracked | Visual Inspection | GEN-03-C-269 | Ground Floor - Lobby |  | Photo | 4 | 80% | 3.49 | 2.792 | 3 | MEP Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
ELV_Systems | Time Systems | Master Clock | EL-PF-032 | Performance metrics | System performance within spec | Visual Inspection | GEN-B1-A-270 | Electrical Room - LV |  | Photo | 4 | 80% | 3.49 | 2.792 | 3 | Main Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
ELV_Systems | Time Systems | Master Clock | EL-VA-033 | Validation of meter readings | Matches utility bills (±5%) | Visual Inspection | GEN-01-B-271 | Level 01 - Office Area | PHOTO-ELV-0271 | Photo | 3 | 60% | 3.49 | 2.094 | 3 | MEP Contractor | CAPA-0088 | P2 | 2024-05-09 | Open | Condition acceptable but requires attention; minor deficiencies observed. Evidence captured; recommend rectification and re-test. | .
ELV_Systems | Time Systems | Master Clock | EL-TR-034 | Training records | FM staff trained on system | Visual Inspection | GEN-02-D-272 | Basement B1 - Plantroom | PHOTO-ELV-0272 | Photo | 2 | 40% | 3.49 | 1.396 | 3 | MEP Contractor | CAPA-0089 | P2 | 2024-05-09 | Open | Non-compliance / degraded condition observed; corrective action required. Preventive maintenance records incomplete; verify PM completion. | .
ELV_Systems | Time Systems | Master Clock | EL-DC-035 | Documentation completeness | All manuals, diagrams available | Visual Inspection | GEN-02-D-273 | Roof - Mechanical Area |  | Test Report | 4 | 80% | 3.49 | 2.792 | 3 | Owner |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Security_Safety | CCTV | Camera | SE-CCTV-001 | CCTV field of view verification | Coverage adequate; blind spots logged | Visual Inspection | GEN-B1-D-274 | Staircase Core | PHOTO-SEC-0274 | Photo | 0 | 0% | 2.44 | 0 | 3 | FM Contractor |  | - |  | N/A | Not applicable for this building / scope. | .
Security_Safety | CCTV | Camera | SE-REC-002 | Recording retention & playback | Meets policy; playback OK | Visual Inspection | GEN-G-B-275 | Level 03 - Office Area | PHOTO-SEC-0275 | Photo | 3 | 60% | 2.44 | 1.464 | 3 | Owner | CAPA-0090 | P3 | 29/09/2024 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Evidence captured; recommend rectification and re-test. | .
Security_Safety | CCTV | Camera | SE-AC-003 | Access control system test | Readers/doors function; logs OK | Visual Inspection | GEN-G-B-276 | External - Service Yard |  | Checklist | 4 | 80% | 2.44 | 1.952 | 3 | FM Contractor | CAPA-0091 | P3 | 29/09/2024 | In Progress | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Security_Safety | CCTV | Camera | SE-INT-004 | Intercom/emergency call test | Clear audio; response confirmed | Visual Inspection | GEN-03-B-277 | External - Service Yard | PHOTO-SEC-0277 | Photo | 3 | 60% | 2.44 | 1.464 | 3 | Specialist Vendor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | .
Security_Safety | CCTV | Camera | SE-IDS-005 | Intrusion/motion detection test | Sensors trigger alarms | Visual Inspection | GEN-B1-D-278 | Basement B1 - Plantroom | PHOTO-SEC-0278 | Photo | 3 | 60% | 2.44 | 1.464 | 3 | FM Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
Security_Safety | CCTV | Camera | SE-CTR-006 | Control room operations | Procedures/logs present | Visual Inspection | GEN-B1-A-279 | Level 01 - Office Area |  | Test Report | 4 | 80% | 2.44 | 1.952 | 3 | Specialist Vendor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Security_Safety | CCTV | Camera | SE-LOG-007 | Incident reporting quality | Records complete | Visual Inspection | GEN-03-A-280 | Roof - Mechanical Area |  | Checklist | 5 | 100% | 2.44 | 2.44 | 3 | Specialist Vendor |  | P4 |  | Closed | Inspected and found fully compliant; no observations noted. | .
Security_Safety | CCTV | Camera | SE-GRD-008 | Guard deployment adequacy | Coverage meets plan | Visual Inspection | GEN-04-C-281 | Level 01 - Office Area | PHOTO-SEC-0281 | Photo | 2 | 40% | 2.44 | 0.976 | 3 | Specialist Vendor | CAPA-0092 | P1 | 22/08/2024 | Open | Non-compliance / degraded condition observed; corrective action required. Preventive maintenance records incomplete; verify PM completion. | .
Security_Safety | CCTV | Camera | SE-TRN-009 | Security staff training | Records available | Visual Inspection | GEN-05-A-282 | Level 01 - Office Area | PHOTO-SEC-0282 | Photo | 3 | 60% | 4.07 | 2.442 | 5 | Main Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Security_Safety | CCTV | Camera | SE-SGN-010 | Safety signage (general) | Adequate; visible | Visual Inspection | GEN-G-C-283 | Roof - Mechanical Area | PHOTO-SEC-0283 | Photo | 3 | 60% | 2.44 | 1.464 | 3 | FM Contractor | CAPA-0093 | P2 | 2024-05-09 | Open | Condition acceptable but requires attention; minor deficiencies observed. Housekeeping and labeling improvements required. | .
Security_Safety | CCTV | Camera | SE-HSE-011 | HSE hazards in common areas | No hazards; controls | Visual Inspection | GEN-04-A-284 | Basement B1 - Plantroom | PHOTO-SEC-0284 | Photo | 3 | 60% | 2.44 | 1.464 | 3 | FM Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
Security_Safety | CCTV | Camera | SE-EMG-012 | Emergency contact lists & comms | Up-to-date | Visual Inspection | GEN-03-D-285 | Ground Floor - Lobby |  | Checklist | 4 | 80% | 2.44 | 1.952 | 3 | Main Contractor | CAPA-0094 | P3 | 29/09/2024 | In Progress | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Security_Safety | CCTV | Camera | SE-PER-013 | Perimeter security (fences/gates) | Intact; controlled | Visual Inspection | GEN-01-A-286 | Ground Floor - Lobby | PHOTO-SEC-0286 | Photo | 3 | 60% | 4.07 | 2.442 | 5 | FM Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
Security_Safety | CCTV | Camera | SE-LGT-014 | Security lighting adequacy | No dark areas | Visual Inspection | GEN-04-A-287 | Parking - Basement |  | Test Report | 4 | 80% | 4.07 | 3.256 | 5 | FM Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Security_Safety | CCTV | Camera | SE-KEY-015 | Key management system | Controlled; logs | Visual Inspection | GEN-04-C-288 | Level 03 - Office Area |  | Photo | 4 | 80% | 2.44 | 1.952 | 3 | MEP Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Security_Safety | CCTV | Camera | SE-VIS-016 | Visitor management process | Registers; badges | Visual Inspection | GEN-01-D-289 | Level 02 - Office Area |  | Photo | 4 | 80% | 2.44 | 1.952 | 3 | FM Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Security_Safety | CCTV | Camera | SE-CAM-017 | Camera health monitoring | Fault alerts configured | Visual Inspection | GEN-B1-D-290 | Level 01 - Office Area | PHOTO-SEC-0290 | Photo | 3 | 60% | 2.44 | 1.464 | 3 | MEP Contractor | CAPA-0095 | P2 | 2024-05-09 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Housekeeping and labeling improvements required. | .
Security_Safety | CCTV | Camera | SE-NET-018 | Security network segregation | As designed | Visual Inspection | GEN-01-B-291 | Level 03 - Office Area | PHOTO-SEC-0291 | Photo | 3 | 60% | 4.07 | 2.442 | 5 | FM Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Evidence captured; recommend rectification and re-test. | .
Security_Safety | CCTV | Camera | SE-DOC-019 | Security SOPs available | Approved versions | Visual Inspection | GEN-05-D-292 | Staircase Core |  | Test Report | 4 | 80% | 4.07 | 3.256 | 5 | MEP Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Security_Safety | CCTV | Camera | SE-RES-020 | Resilience/backup (UPS for security) | Functional | Visual Inspection | GEN-03-B-293 | Ground Floor - Lobby | PHOTO-SEC-0293 | Photo | 2 | 40% | 4.07 | 1.628 | 5 | FM Contractor | CAPA-0096 | P2 | 2024-05-09 | Open | Non-compliance / degraded condition observed; corrective action required. Trend indicates aging components; prioritize within next maintenance cycle. | .
Security_Safety | CCTV | Camera | SE-PRV-021 | Privacy compliance (if required) | Signage/policy present | Visual Inspection | GEN-05-C-294 | Roof - Mechanical Area |  | Test Report | 4 | 80% | 2.44 | 1.952 | 3 | FM Contractor |  | P3 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Security_Safety | CCTV | Camera | SE-ACC-022 | Access rights review | Least privilege | Visual Inspection | GEN-05-D-295 | Ground Floor - Lobby |  | Checklist | 4 | 80% | 2.44 | 1.952 | 3 | MEP Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Security_Safety | CCTV | Camera | SE-ALM-023 | Alarm escalation workflow | Clear | Visual Inspection | GEN-02-C-296 | Parking - Basement | PHOTO-SEC-0296 | Photo | 3 | 60% | 2.44 | 1.464 | 3 | Main Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Evidence captured; recommend rectification and re-test. | .
Security_Safety | CCTV | Camera | SE-MNT-024 | PM compliance for security systems | Completed | Visual Inspection | GEN-B1-D-297 | Roof - Mechanical Area | PHOTO-SEC-0297 | Photo | 3 | 60% | 4.07 | 2.442 | 5 | FM Contractor | CAPA-0097 | P2 | 2024-05-09 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Housekeeping and labeling improvements required. | .
Security_Safety | CCTV | Camera | SE-KPI-025 | Security contractor KPIs | Met / gaps | Visual Inspection | GEN-05-A-298 | Level 02 - Office Area |  | Photo | 5 | 100% | 4.07 | 4.07 | 5 | FM Contractor |  | P4 |  | Closed | Inspected and found fully compliant; no observations noted. | .
Security_Safety | CCTV | Camera | SE-EXT-026 | External camera coverage (parking/perimeter) | Adequate | Visual Inspection | GEN-03-A-299 | Level 02 - Office Area | PHOTO-SEC-0299 | Photo | 3 | 60% | 2.44 | 1.464 | 3 | FM Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | .
Security_Safety | CCTV | Camera | SE-PTZ-027 | PTZ control responsiveness | OK | Visual Inspection | GEN-G-A-300 | Level 01 - Office Area |  | Photo | 4 | 80% | 2.44 | 1.952 | 3 | FM Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Security_Safety | CCTV | Camera | SE-RET-028 | Retention storage capacity | Sufficient | Visual Inspection | GEN-04-B-301 | Level 03 - Office Area | PHOTO-SEC-0301 | Photo | 2 | 40% | 2.44 | 0.976 | 3 | FM Contractor | CAPA-0098 | P1 | 22/08/2024 | In Progress | Non-compliance / degraded condition observed; corrective action required. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Security_Safety | CCTV | Camera | SE-AUD-029 | Audit trail availability | Accessible | Visual Inspection | GEN-G-D-302 | External - Service Yard |  | Test Report | 4 | 80% | 2.44 | 1.952 | 3 | FM Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Security_Safety | CCTV | Camera | SE-RSK-030 | Risk classification | P1–P4 | Visual Inspection | GEN-B1-B-303 | External - Service Yard | PHOTO-SEC-0303 | Photo | 3 | 60% | 2.44 | 1.464 | 3 | FM Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
Security_Safety | CCTV | Camera | SE-REC2-031 | Corrective actions logged | CAPA linked | Visual Inspection | GEN-02-B-304 | Level 01 - Office Area | PHOTO-SEC-0304 | Photo | 3 | 60% | 2.44 | 1.464 | 3 | Main Contractor | CAPA-0099 | P3 | 29/09/2024 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
Security_Safety | CCTV | Camera | SE-PHT-032 | Photo evidence (if needed) | IDs | Visual Inspection | GEN-02-D-305 | Roof - Mechanical Area |  | Checklist | 4 | 80% | 2.44 | 1.952 | 3 | Specialist Vendor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Security_Safety | CCTV | Camera | SE-SUM-033 | Security summary | Overall status | Visual Inspection | GEN-03-C-306 | Level 03 - Office Area |  | Test Report | 4 | 80% | 4.07 | 3.256 | 5 | FM Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Security_Safety | CCTV | Camera | SE-HRD-034 | Hardware condition (racks/cabinets) | Secure | Visual Inspection | GEN-04-C-307 | Level 02 - Office Area | PHOTO-SEC-0307 | Photo | 3 | 60% | 2.44 | 1.464 | 3 | Main Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Evidence captured; recommend rectification and re-test. | .
Security_Safety | CCTV | Camera | SE-KPI2-035 | Monthly reporting quality | Available | Visual Inspection | GEN-04-D-308 | Level 03 - Office Area |  | Checklist | 4 | 80% | 2.44 | 1.952 | 3 | MEP Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Digital_ICT | LAN | Network Switch | DG-LAN-001 | LAN speed test (wired) | Meets target Mbps/latency | Visual Inspection | GEN-04-D-309 | Roof - Mechanical Area | PHOTO-DIG-0309 | Photo | 2 | 40% | 2.61 | 1.044 | 3 | FM Contractor | CAPA-0100 | P2 | 2024-05-09 | Open | Non-compliance / degraded condition observed; corrective action required. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Digital_ICT | LAN | Network Switch | DG-WIF-002 | Wi‑Fi coverage & speed test | Meets target; dead zones logged | Visual Inspection | GEN-04-C-310 | Ground Floor - Lobby |  | Photo | 4 | 80% | 2.61 | 2.088 | 3 | Specialist Vendor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Digital_ICT | LAN | Network Switch | DG-SWT-003 | Network switches health | No errors; labeled | Visual Inspection | GEN-02-A-311 | Electrical Room - LV |  | Photo | 4 | 80% | 2.61 | 2.088 | 3 | FM Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Digital_ICT | LAN | Network Switch | DG-RCK-004 | Racks/cabling management | Neat; labeled; grounded | Visual Inspection | GEN-G-B-312 | Roof - Mechanical Area |  | Checklist | 4 | 80% | 2.61 | 2.088 | 3 | MEP Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Digital_ICT | LAN | Network Switch | DG-PWR-005 | UPS for ICT equipment | Autonomy meets requirement | Visual Inspection | GEN-01-A-313 | Basement B1 - Plantroom | PHOTO-DIG-0313 | Photo | 3 | 60% | 2.61 | 1.566 | 3 | FM Contractor | CAPA-0101 | P2 | 2024-05-09 | Open | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Digital_ICT | LAN | Network Switch | DG-PA-006 | PA/audio clarity test | Intelligibility acceptable | Visual Inspection | GEN-04-D-314 | Parking - Basement | PHOTO-DIG-0314 | Photo | 2 | 40% | 2.61 | 1.044 | 3 | FM Contractor | CAPA-0102 | P2 | 2024-05-09 | In Progress | Non-compliance / degraded condition observed; corrective action required. Preventive maintenance records incomplete; verify PM completion. | .
Digital_ICT | LAN | Network Switch | DG-BMS-007 | BMS functional test (non-fire) | Sequences, trends, alarms OK | Visual Inspection | GEN-01-B-315 | Basement B1 - Plantroom | PHOTO-DIG-0315 | Photo | 0 | 0% | 4.35 | 0 | 5 | Specialist Vendor |  | - |  | N/A | Not applicable for this building / scope. | .
Digital_ICT | LAN | Network Switch | DG-INT-008 | System integration response test | Event triggers as expected | Visual Inspection | GEN-01-B-316 | Ground Floor - Lobby | PHOTO-DIG-0316 | Photo | 3 | 60% | 2.61 | 1.566 | 3 | FM Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
Digital_ICT | LAN | Network Switch | DG-SEC-009 | Basic cybersecurity controls review | Hardening baseline checked | Visual Inspection | GEN-02-B-317 | Roof - Mechanical Area |  | Checklist | 5 | 100% | 4.35 | 4.35 | 5 | Specialist Vendor |  | P4 |  | Closed | Inspected and found fully compliant; no observations noted. | .
Digital_ICT | LAN | Network Switch | DG-PEN-010 | Cyber penetration test (if required) | Specialist report attached | Visual Inspection | GEN-04-B-318 | Level 02 - Office Area |  | Test Report | 4 | 80% | 4.35 | 3.48 | 5 | FM Contractor |  | P3 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Digital_ICT | LAN | Network Switch | DG-ERP-011 | CAFM/ERP integration compatibility | Interfaces verified | Visual Inspection | GEN-05-A-319 | External - Service Yard | PHOTO-DIG-0319 | Photo | 3 | 60% | 2.61 | 1.566 | 3 | Main Contractor | CAPA-0103 | P2 | 2024-05-09 | Open | Condition acceptable but requires attention; minor deficiencies observed. Evidence captured; recommend rectification and re-test. | .
Digital_ICT | LAN | Network Switch | DG-DATA-012 | Asset data quality check | Completeness/accuracy assessed | Visual Inspection | GEN-03-C-320 | Electrical Room - LV | PHOTO-DIG-0320 | Photo | 2 | 40% | 2.61 | 1.044 | 3 | MEP Contractor | CAPA-0104 | P1 | 22/08/2024 | Open | Non-compliance / degraded condition observed; corrective action required. Housekeeping and labeling improvements required. | .
Digital_ICT | LAN | Network Switch | DG-BCK-013 | Backup & recovery test | Restore spot-check successful | Visual Inspection | GEN-03-A-321 | Level 03 - Office Area |  | Photo | 4 | 80% | 3.48 | 2.784 | 4 | MEP Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Digital_ICT | LAN | Network Switch | DG-ACC-014 | User access roles review | Least privilege | Visual Inspection | GEN-01-B-322 | Basement B1 - Plantroom |  | Test Report | 4 | 80% | 2.61 | 2.088 | 3 | FM Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Digital_ICT | LAN | Network Switch | DG-LOG-015 | Logging & monitoring | Alerts configured | Visual Inspection | GEN-05-D-323 | Level 01 - Office Area | PHOTO-DIG-0323 | Photo | 3 | 60% | 2.61 | 1.566 | 3 | MEP Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Evidence captured; recommend rectification and re-test. | .
Digital_ICT | LAN | Network Switch | DG-LIC-016 | Software licenses & renewals | Valid | Visual Inspection | GEN-02-C-324 | Level 03 - Office Area | PHOTO-DIG-0324 | Photo | 3 | 60% | 2.61 | 1.566 | 3 | Main Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Evidence captured; recommend rectification and re-test. | .
Digital_ICT | LAN | Network Switch | DG-DOC-017 | ICT as-builts & schematics | Up-to-date | Visual Inspection | GEN-05-A-325 | Basement B1 - Plantroom | PHOTO-DIG-0325 | Photo | 2 | 40% | 2.61 | 1.044 | 3 | Specialist Vendor | CAPA-0105 | P1 | 22/08/2024 | Open | Non-compliance / degraded condition observed; corrective action required. Housekeeping and labeling improvements required. | .
Digital_ICT | LAN | Network Switch | DG-MNT-018 | PM compliance for ICT systems | Completed | Visual Inspection | GEN-04-A-326 | Roof - Mechanical Area |  | Checklist | 4 | 80% | 2.61 | 2.088 | 3 | Owner |  | P3 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Digital_ICT | LAN | Network Switch | DG-KPI-019 | Service provider performance | SLA met | Visual Inspection | GEN-B1-B-327 | Basement B1 - Plantroom | PHOTO-DIG-0327 | Photo | 3 | 60% | 2.61 | 1.566 | 3 | Specialist Vendor | CAPA-0106 | P2 | 2024-05-09 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Digital_ICT | LAN | Network Switch | DG-IO-020 | Interoperability protocols (BACnet/Modbus) | Verified where applicable | Visual Inspection | GEN-03-A-328 | Level 01 - Office Area |  | Checklist | 4 | 80% | 2.61 | 2.088 | 3 | MEP Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Digital_ICT | LAN | Network Switch | DG-AP-021 | Access points placement check | Optimized | Visual Inspection | GEN-04-C-329 | Staircase Core |  | Test Report | 4 | 80% | 2.61 | 2.088 | 3 | Specialist Vendor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Digital_ICT | LAN | Network Switch | DG-EMG-022 | Emergency communications (non-fire) | Functional | Visual Inspection | GEN-B1-B-330 | Staircase Core |  | Checklist | 4 | 80% | 4.35 | 3.48 | 5 | FM Contractor |  | P3 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Digital_ICT | LAN | Network Switch | DG-CLN-023 | Server room environmental conditions | Temp/humidity OK | Visual Inspection | GEN-03-D-331 | Parking - Basement | PHOTO-DIG-0331 | Photo | 3 | 60% | 2.61 | 1.566 | 3 | FM Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Digital_ICT | LAN | Network Switch | DG-EMI-024 | EMI/grounding practices | Adequate | Visual Inspection | GEN-02-A-332 | Ground Floor - Lobby | PHOTO-DIG-0332 | Photo | 3 | 60% | 2.61 | 1.566 | 3 | MEP Contractor | CAPA-0107 | P2 | 2024-05-09 | Open | Condition acceptable but requires attention; minor deficiencies observed. Evidence captured; recommend rectification and re-test. | .
Digital_ICT | LAN | Network Switch | DG-PAT-025 | Patch management status | Updated | Visual Inspection | GEN-01-C-333 | Basement B1 - Plantroom |  | Photo | 4 | 80% | 2.61 | 2.088 | 3 | MEP Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Digital_ICT | LAN | Network Switch | DG-AV-026 | Endpoint protection | Enabled | Visual Inspection | GEN-B1-B-334 | Basement B1 - Plantroom | PHOTO-DIG-0334 | Photo | 3 | 60% | 2.61 | 1.566 | 3 | Specialist Vendor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Digital_ICT | LAN | Network Switch | DG-PRV-027 | Data privacy compliance | Policy present | Visual Inspection | GEN-B1-C-335 | External - Service Yard | PHOTO-DIG-0335 | Photo | 3 | 60% | 2.61 | 1.566 | 3 | MEP Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
Digital_ICT | LAN | Network Switch | DG-TRN-028 | FM/IT training records | Complete | Visual Inspection | GEN-05-D-336 | Basement B1 - Plantroom | PHOTO-DIG-0336 | Photo | 3 | 60% | 2.61 | 1.566 | 3 | Specialist Vendor | CAPA-0108 | P3 | 29/09/2024 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Digital_ICT | LAN | Network Switch | DG-RSK-029 | Risk classification | P1–P4 | Visual Inspection | GEN-03-A-337 | Staircase Core |  | Checklist | 4 | 80% | 2.61 | 2.088 | 3 | Owner |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Digital_ICT | LAN | Network Switch | DG-REC-030 | Corrective actions logged | CAPA linked | Visual Inspection | GEN-04-B-338 | Ground Floor - Lobby | PHOTO-DIG-0338 | Photo | 3 | 60% | 2.61 | 1.566 | 3 | MEP Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Digital_ICT | LAN | Network Switch | DG-PHT-031 | Evidence references | IDs | Visual Inspection | GEN-01-D-339 | Level 01 - Office Area | PHOTO-DIG-0339 | Photo | 2 | 40% | 2.61 | 1.044 | 3 | FM Contractor | CAPA-0109 | P2 | 2024-05-09 | In Progress | Non-compliance / degraded condition observed; corrective action required. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Digital_ICT | LAN | Network Switch | DG-SUM-032 | Digital systems summary | Overall status | Visual Inspection | GEN-04-C-340 | Level 01 - Office Area | PHOTO-DIG-0340 | Photo | 3 | 60% | 2.61 | 1.566 | 3 | FM Contractor | CAPA-0110 | P3 | 29/09/2024 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
Digital_ICT | LAN | Network Switch | DG-RES-033 | Resilience (redundant links) | Verified | Visual Inspection | GEN-03-D-341 | Staircase Core | PHOTO-DIG-0341 | Photo | 3 | 60% | 3.48 | 2.088 | 4 | Specialist Vendor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | .
Digital_ICT | LAN | Network Switch | DG-HLP-034 | Helpdesk/ticketing performance | Metrics available | Visual Inspection | GEN-B1-A-342 | Level 02 - Office Area | PHOTO-DIG-0342 | Photo | 3 | 60% | 2.61 | 1.566 | 3 | FM Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
Digital_ICT | LAN | Network Switch | DG-OPS-035 | Operating procedures | Available | Visual Inspection | GEN-G-A-343 | Roof - Mechanical Area | PHOTO-DIG-0343 | Photo | 3 | 60% | 2.61 | 1.566 | 3 | MEP Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Structural | Foundations | Foundation | ST-VIS-001 | Visual structural survey | No critical cracks/spalling | Visual Inspection | STR-02-D-344 | Parking - Basement | PHOTO-STR-0344 | Photo | 3 | 60% | 2.61 | 1.566 | 3 | MEP Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Evidence captured; recommend rectification and re-test. | .
Structural | Foundations | Foundation | ST-CRK-002 | Crack mapping & measurement | Widths recorded; trend noted | Visual Inspection | STR-05-B-345 | Level 02 - Office Area |  | Checklist | 4 | 80% | 3.48 | 2.784 | 4 | Specialist Vendor |  | P3 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Structural | Foundations | Foundation | ST-SE-003 | Settlement survey (if required) | Benchmarks/points recorded | Visual Inspection | STR-02-A-346 | Parking - Basement |  | Checklist | 5 | 100% | 4.35 | 4.35 | 5 | Specialist Vendor |  | P4 |  | Verified | Inspected and found fully compliant; no observations noted. | .
Structural | Foundations | Foundation | ST-NDT-004 | Rebar scan / cover test (FerroScan) | Cover meets design; locations logged | Visual Inspection | STR-B1-B-347 | Roof - Mechanical Area | PHOTO-STR-0347 | Photo | 0 | 0% | 2.61 | 0 | 3 | Specialist Vendor |  | - |  | N/A | Not applicable for this building / scope. | .
Structural | Foundations | Foundation | ST-CORE-005 | Concrete core/compression test (if required) | Lab results meet strength | Visual Inspection | STR-B1-C-348 | Staircase Core |  | Photo | 4 | 80% | 2.61 | 2.088 | 3 | MEP Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Structural | Foundations | Foundation | ST-CHL-006 | Carbonation/chloride test (if required) | Results recorded; risk assessed | Visual Inspection | STR-G-C-349 | Roof - Mechanical Area | PHOTO-STR-0349 | Photo | 3 | 60% | 2.61 | 1.566 | 3 | FM Contractor | CAPA-0111 | P2 | 2024-05-09 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Structural | Foundations | Foundation | ST-DEF-007 | Deflection/levelness checks | Within tolerance | Visual Inspection | STR-B1-C-350 | Parking - Basement |  | Photo | 4 | 80% | 2.61 | 2.088 | 3 | MEP Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Structural | Foundations | Foundation | ST-LDT-008 | Structural load test (if required) | Test protocol & results attached | Visual Inspection | STR-02-A-351 | Level 03 - Office Area | PHOTO-STR-0351 | Photo | 0 | 0% | 4.35 | 0 | 5 | MEP Contractor |  | - |  | N/A | Not applicable for this building / scope. | .
Structural | Foundations | Foundation | ST-VIB-009 | Structural vibration test (if required) | Results within limits | Visual Inspection | STR-B1-B-352 | Staircase Core |  | Test Report | 4 | 80% | 2.61 | 2.088 | 3 | FM Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Structural | Foundations | Foundation | ST-JNT-010 | Expansion joints condition | Intact; movement accommodated | Visual Inspection | STR-03-D-353 | Ground Floor - Lobby |  | Test Report | 4 | 80% | 2.61 | 2.088 | 3 | Specialist Vendor |  | P3 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Structural | Foundations | Foundation | ST-WP-011 | Roof waterproofing test (flood) | Duration/observations recorded | Visual Inspection | STR-G-C-354 | Staircase Core | PHOTO-STR-0354 | Photo | 2 | 40% | 2.61 | 1.044 | 3 | FM Contractor | CAPA-0112 | P2 | 2024-05-09 | Open | Non-compliance / degraded condition observed; corrective action required. Housekeeping and labeling improvements required. | .
Structural | Foundations | Foundation | ST-MOI-012 | Moisture intrusion assessment | Sources identified; mapping done | Visual Inspection | STR-03-A-355 | External - Service Yard | PHOTO-STR-0355 | Photo | 3 | 60% | 2.61 | 1.566 | 3 | FM Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Structural | Foundations | Foundation | ST-FAÇ-013 | Facade anchorage visual check | No loose panels; fixings sound | Visual Inspection | STR-01-C-356 | External - Service Yard |  | Photo | 4 | 80% | 3.48 | 2.784 | 4 | FM Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Structural | Foundations | Foundation | ST-COR-014 | Rebar corrosion signs | No exposed/rebar staining | Visual Inspection | STR-G-D-357 | Staircase Core | PHOTO-STR-0357 | Photo | 3 | 60% | 2.61 | 1.566 | 3 | FM Contractor | CAPA-0113 | P2 | 2024-05-09 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
Structural | Foundations | Foundation | ST-RST-015 | Retaining walls condition (if any) | No movement; drainage OK | Visual Inspection | STR-03-B-358 | Ground Floor - Lobby |  | Photo | 4 | 80% | 2.61 | 2.088 | 3 | Owner |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Structural | Foundations | Foundation | ST-SLB-016 | Slab cracks and joints | Documented; no safety risk | Visual Inspection | STR-G-B-359 | Level 02 - Office Area |  | Test Report | 4 | 80% | 3.48 | 2.784 | 4 | FM Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Structural | Foundations | Foundation | ST-COL-017 | Columns/beams condition | No major defects | Visual Inspection | STR-04-A-360 | Level 03 - Office Area |  | Test Report | 4 | 80% | 2.61 | 2.088 | 3 | Main Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Structural | Foundations | Foundation | ST-BSM-018 | Basement water ingress (if any) | No seepage; sump ok | Visual Inspection | STR-B1-C-361 | External - Service Yard | PHOTO-STR-0361 | Photo | 3 | 60% | 3.48 | 2.088 | 4 | MEP Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Housekeeping and labeling improvements required. | .
Structural | Foundations | Foundation | ST-TRC-019 | Thermal movement check (if required) | Observations on joints/cracks | Visual Inspection | STR-04-B-362 | External - Service Yard |  | Test Report | 4 | 80% | 2.61 | 2.088 | 3 | MEP Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Structural | Foundations | Foundation | ST-SOI-020 | Soil reports review (if applicable) | Bearing/proctor docs available | Visual Inspection | STR-01-C-363 | Level 01 - Office Area |  | Test Report | 4 | 80% | 2.61 | 2.088 | 3 | Specialist Vendor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Structural | Foundations | Foundation | ST-DOC-021 | Structural as-built drawings | Up-to-date revision | Visual Inspection | STR-03-A-364 | Level 01 - Office Area |  | Test Report | 4 | 80% | 2.61 | 2.088 | 3 | Specialist Vendor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Structural | Foundations | Foundation | ST-QA-022 | Previous defect history review | Recurring defects flagged | Visual Inspection | STR-04-A-365 | Basement B1 - Plantroom |  | Test Report | 4 | 80% | 2.61 | 2.088 | 3 | Specialist Vendor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Structural | Foundations | Foundation | ST-SAF-023 | Structural safety hazards | None present; barricades where needed | Visual Inspection | STR-03-D-366 | Level 01 - Office Area |  | Checklist | 4 | 80% | 4.35 | 3.48 | 5 | Main Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Structural | Foundations | Foundation | ST-RSK-024 | Risk classification per finding | P1–P4 assigned | Visual Inspection | STR-05-B-367 | Staircase Core | PHOTO-STR-0367 | Photo | 3 | 60% | 2.61 | 1.566 | 3 | MEP Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Structural | Foundations | Foundation | ST-REH-025 | Repair vs replace recommendation | For major defects where relevant | Visual Inspection | STR-01-A-368 | Level 02 - Office Area |  | Checklist | 4 | 80% | 2.61 | 2.088 | 3 | Specialist Vendor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Structural | Foundations | Foundation | ST-ENV-026 | Environmental exposure classification | Coastal/industrial considerations | Visual Inspection | STR-B1-A-369 | Roof - Mechanical Area | PHOTO-STR-0369 | Photo | 3 | 60% | 2.61 | 1.566 | 3 | FM Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Structural | Foundations | Foundation | ST-DRN-027 | Site drainage impact on structure | No undermining/erosion | Visual Inspection | STR-03-B-370 | Parking - Basement | PHOTO-STR-0370 | Photo | 3 | 60% | 2.61 | 1.566 | 3 | Specialist Vendor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Structural | Foundations | Foundation | ST-INS-028 | Roof insulation condition (as relates) | Intact; no saturation | Visual Inspection | STR-02-D-371 | External - Service Yard |  | Photo | 4 | 80% | 2.61 | 2.088 | 3 | FM Contractor | CAPA-0114 | P3 | 29/09/2024 | In Progress | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Structural | Foundations | Foundation | ST-BLD-029 | Building movement monitoring plan | If cracks/settlement exist | Visual Inspection | STR-G-B-372 | Level 01 - Office Area |  | Photo | 4 | 80% | 2.61 | 2.088 | 3 | FM Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Structural | Foundations | Foundation | ST-NDT2-030 | UPV/Rebound hammer (if required) | Results recorded; correlated | Visual Inspection | STR-02-B-373 | External - Service Yard | PHOTO-STR-0373 | Photo | 3 | 60% | 2.61 | 1.566 | 3 | MEP Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Evidence captured; recommend rectification and re-test. | .
Structural | Foundations | Foundation | ST-CMP-031 | Compliance with SBC structural requirements (review) | Checklist completed | Visual Inspection | STR-G-A-374 | External - Service Yard |  | Photo | 4 | 80% | 2.61 | 2.088 | 3 | MEP Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Structural | Foundations | Foundation | ST-ACC-032 | Access safety for inspection points | Safe access or noted constraints | Visual Inspection | STR-B1-B-375 | Electrical Room - LV | PHOTO-STR-0375 | Photo | 2 | 40% | 2.61 | 1.044 | 3 | Main Contractor |  | P2 |  | Closed | Non-compliance / degraded condition observed; corrective action required. Preventive maintenance records incomplete; verify PM completion. | .
Structural | Foundations | Foundation | ST-PHT-033 | Photo evidence & location grid | All defects referenced | Visual Inspection | STR-03-C-376 | Level 01 - Office Area |  | Test Report | 5 | 100% | 2.61 | 2.61 | 3 | MEP Contractor |  | P4 |  | Closed | Inspected and found fully compliant; no observations noted. | .
Structural | Foundations | Foundation | ST-SUM-034 | Structural summary conclusion | Overall structural status | Visual Inspection | STR-03-D-377 | Level 01 - Office Area |  | Test Report | 4 | 80% | 2.61 | 2.088 | 3 | FM Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Structural | Foundations | Foundation | ST-RES-035 | Structural resilience & criticality | Mission critical risks noted | Visual Inspection | STR-03-A-378 | Parking - Basement |  | Test Report | 4 | 80% | 2.61 | 2.088 | 3 | FM Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Architectural_Fabric | Internal Finishes | Tile / Paint / Gypsum / Wall Covering | AR-WAL-001 | Internal walls/partitions condition | No major cracks/stains; finishes intact | Visual Inspection | GEN-01-A-379 | Parking - Basement | PHOTO-ARC-0379 | Photo | 1 | 20% | 2.86 | 0.572 | 3 | Specialist Vendor | CAPA-0115 | P1 | 22/08/2024 | Open | Critical deficiency observed; immediate corrective action required to mitigate risk. Evidence captured; recommend rectification and re-test. | .
Architectural_Fabric | Internal Finishes | Tile / Paint / Gypsum / Wall Covering | AR-FLR-002 | Floor finishes condition | No loose/hollow tiles; levelness OK | Visual Inspection | GEN-04-A-380 | External - Service Yard |  | Test Report | 4 | 80% | 2.86 | 2.288 | 3 | FM Contractor |  | P3 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Architectural_Fabric | Internal Finishes | Tile / Paint / Gypsum / Wall Covering | AR-CLG-003 | Ceilings condition | No sagging; access panels present | Visual Inspection | GEN-04-C-381 | Level 03 - Office Area | PHOTO-ARC-0381 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | FM Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Architectural_Fabric | Internal Finishes | Tile / Paint / Gypsum / Wall Covering | AR-DRS-004 | Doors & hardware operation | Smooth; closers; seals OK | Visual Inspection | GEN-03-D-382 | Level 01 - Office Area | PHOTO-ARC-0382 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | Specialist Vendor | CAPA-0116 | P2 | 2024-05-09 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Housekeeping and labeling improvements required. | .
Architectural_Fabric | Internal Finishes | Tile / Paint / Gypsum / Wall Covering | AR-WIN-005 | Windows & glazing integrity | Seals intact; no infiltration | Visual Inspection | GEN-04-B-383 | Electrical Room - LV | PHOTO-ARC-0383 | Photo | 2 | 40% | 2.86 | 1.144 | 3 | Specialist Vendor | CAPA-0117 | P1 | 22/08/2024 | In Progress | Non-compliance / degraded condition observed; corrective action required. Housekeeping and labeling improvements required. | .
Architectural_Fabric | Internal Finishes | Tile / Paint / Gypsum / Wall Covering | AR-WET-006 | Wet areas waterproofing indicators | No leakage; slopes to drains | Visual Inspection | GEN-05-A-384 | Level 01 - Office Area | PHOTO-ARC-0384 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | FM Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | .
Architectural_Fabric | Internal Finishes | Tile / Paint / Gypsum / Wall Covering | AR-PNT-007 | Paint/coatings condition | No peeling/blistering | Visual Inspection | GEN-03-C-385 | External - Service Yard | PHOTO-ARC-0385 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | Specialist Vendor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
Architectural_Fabric | Internal Finishes | Tile / Paint / Gypsum / Wall Covering | AR-EXT-008 | Facade finishes condition | No detachment; discoloration noted | Visual Inspection | GEN-G-A-386 | External - Service Yard |  | Test Report | 4 | 80% | 2.86 | 2.288 | 3 | FM Contractor | CAPA-0118 | P3 | 29/09/2024 | In Progress | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Architectural_Fabric | Internal Finishes | Tile / Paint / Gypsum / Wall Covering | AR-RMP-009 | Accessibility ramps/handrails | Compliant; safe | Visual Inspection | GEN-01-D-387 | Roof - Mechanical Area | PHOTO-ARC-0387 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | Owner |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Architectural_Fabric | Internal Finishes | Tile / Paint / Gypsum / Wall Covering | AR-SGN-010 | Wayfinding/signage (non-fire) | Clear, consistent | Visual Inspection | GEN-04-C-388 | Roof - Mechanical Area | PHOTO-ARC-0388 | Photo | 0 | 0% | 2.86 | 0 | 3 | Main Contractor |  | - |  | N/A | Not applicable for this building / scope. | .
Architectural_Fabric | Internal Finishes | Tile / Paint / Gypsum / Wall Covering | AR-ROF-011 | Roof finishes & penetrations | Sealed; no gaps | Visual Inspection | GEN-02-D-389 | External - Service Yard | PHOTO-ARC-0389 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | FM Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Architectural_Fabric | Internal Finishes | Tile / Paint / Gypsum / Wall Covering | AR-INS-012 | Thermal insulation envelope condition | No missing insulation visible | Visual Inspection | GEN-03-C-390 | Electrical Room - LV |  | Checklist | 4 | 80% | 2.86 | 2.288 | 3 | Specialist Vendor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Architectural_Fabric | Internal Finishes | Tile / Paint / Gypsum / Wall Covering | AR-MOI-013 | Moisture mapping (walls/ceilings) | No damp; if damp mapped | Visual Inspection | GEN-02-A-391 | Level 03 - Office Area |  | Photo | 4 | 80% | 2.86 | 2.288 | 3 | MEP Contractor |  | P3 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Architectural_Fabric | Internal Finishes | Tile / Paint / Gypsum / Wall Covering | AR-GLZ-014 | Sealants/caulking condition | No gaps; elastic | Visual Inspection | GEN-04-C-392 | Level 02 - Office Area | PHOTO-ARC-0392 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | MEP Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Evidence captured; recommend rectification and re-test. | .
Architectural_Fabric | Internal Finishes | Tile / Paint / Gypsum / Wall Covering | AR-PLN-015 | Plaster/gypsum board integrity | No delamination | Visual Inspection | GEN-G-C-393 | Level 01 - Office Area |  | Test Report | 4 | 80% | 2.86 | 2.288 | 3 | MEP Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Architectural_Fabric | Internal Finishes | Tile / Paint / Gypsum / Wall Covering | AR-STP-016 | Staircases (architectural only) | Finishes; slip resistance | Visual Inspection | GEN-05-C-394 | Level 01 - Office Area | PHOTO-ARC-0394 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | FM Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | .
Architectural_Fabric | Internal Finishes | Tile / Paint / Gypsum / Wall Covering | AR-HND-017 | Handrails safety (non-fire) | Secure; no sharp edges | Visual Inspection | GEN-03-C-395 | Electrical Room - LV |  | Test Report | 4 | 80% | 2.86 | 2.288 | 3 | Specialist Vendor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Architectural_Fabric | Internal Finishes | Tile / Paint / Gypsum / Wall Covering | AR-DRN-018 | Balcony/terrace drainage | No ponding | Visual Inspection | GEN-03-C-396 | Parking - Basement | PHOTO-ARC-0396 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | MEP Contractor |  | P2 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | .
Architectural_Fabric | Internal Finishes | Tile / Paint / Gypsum / Wall Covering | AR-JNT-019 | Expansion joint covers | Intact; trip hazards none | Visual Inspection | GEN-B1-B-397 | Parking - Basement | PHOTO-ARC-0397 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | FM Contractor | CAPA-0119 | P2 | 2024-05-09 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Architectural_Fabric | Internal Finishes | Tile / Paint / Gypsum / Wall Covering | AR-FIX-020 | Fittings/fixtures in public areas | Secure; undamaged | Visual Inspection | GEN-01-B-398 | Electrical Room - LV |  | Checklist | 4 | 80% | 2.86 | 2.288 | 3 | MEP Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Architectural_Fabric | Internal Finishes | Tile / Paint / Gypsum / Wall Covering | AR-CLN-021 | Cleanliness condition at handover | Snag cleanliness acceptable | Visual Inspection | GEN-03-B-399 | External - Service Yard |  | Test Report | 4 | 80% | 2.86 | 2.288 | 3 | FM Contractor |  | P3 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Architectural_Fabric | Internal Finishes | Tile / Paint / Gypsum / Wall Covering | AR-GLS-022 | Glazing safety marking (if required) | Compliant markings | Visual Inspection | GEN-02-A-400 | Level 01 - Office Area |  | Checklist | 4 | 80% | 2.86 | 2.288 | 3 | FM Contractor |  | P3 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Architectural_Fabric | Internal Finishes | Tile / Paint / Gypsum / Wall Covering | AR-ACU-023 | Acoustic issues (if applicable) | No severe complaints; checks | Visual Inspection | GEN-02-A-401 | Level 01 - Office Area | PHOTO-ARC-0401 | Photo | 2 | 40% | 2.86 | 1.144 | 3 | FM Contractor | CAPA-0120 | P2 | 2024-05-09 | In Progress | Non-compliance / degraded condition observed; corrective action required. Preventive maintenance records incomplete; verify PM completion. | .
Architectural_Fabric | Internal Finishes | Tile / Paint / Gypsum / Wall Covering | AR-LGT-024 | Daylight/visual comfort check | No glare hotspots flagged | Visual Inspection | GEN-01-A-402 | Parking - Basement |  | Photo | 4 | 80% | 2.86 | 2.288 | 3 | FM Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Architectural_Fabric | Internal Finishes | Tile / Paint / Gypsum / Wall Covering | AR-SEC-025 | Perimeter doors/windows security | Locks functional | Visual Inspection | GEN-05-C-403 | Roof - Mechanical Area |  | Checklist | 4 | 80% | 2.86 | 2.288 | 3 | MEP Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Architectural_Fabric | Internal Finishes | Tile / Paint / Gypsum / Wall Covering | AR-EXC-026 | External cracks in finishes | Mapped and rated | Visual Inspection | GEN-05-B-404 | Roof - Mechanical Area |  | Checklist | 4 | 80% | 2.86 | 2.288 | 3 | MEP Contractor |  | P3 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Architectural_Fabric | Internal Finishes | Tile / Paint / Gypsum / Wall Covering | AR-PAT-027 | Pattern/tiling workmanship | Uniform; grout intact | Visual Inspection | GEN-G-C-405 | Roof - Mechanical Area |  | Test Report | 4 | 80% | 2.86 | 2.288 | 3 | FM Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Architectural_Fabric | Internal Finishes | Tile / Paint / Gypsum / Wall Covering | AR-SLF-028 | Shelf-life defects (sealants etc.) | Ageing noted | Visual Inspection | GEN-02-B-406 | Level 01 - Office Area | PHOTO-ARC-0406 | Photo | 2 | 40% | 2.86 | 1.144 | 3 | Specialist Vendor | CAPA-0121 | P2 | 2024-05-09 | Open | Non-compliance / degraded condition observed; corrective action required. Housekeeping and labeling improvements required. | .
Architectural_Fabric | Internal Finishes | Tile / Paint / Gypsum / Wall Covering | AR-DOC-029 | Architectural as-builts complete | Up-to-date revision | Visual Inspection | GEN-B1-A-407 | Ground Floor - Lobby |  | Checklist | 4 | 80% | 2.86 | 2.288 | 3 | FM Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Architectural_Fabric | Internal Finishes | Tile / Paint / Gypsum / Wall Covering | AR-SUM-030 | Architectural condition summary | Overall status | Visual Inspection | GEN-01-B-408 | Level 02 - Office Area |  | Test Report | 4 | 80% | 2.86 | 2.288 | 3 | FM Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Architectural_Fabric | Internal Finishes | Tile / Paint / Gypsum / Wall Covering | AR-RSK-031 | Risk classification per finding | P1–P4 | Visual Inspection | GEN-05-C-409 | Electrical Room - LV | PHOTO-ARC-0409 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | FM Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Architectural_Fabric | Internal Finishes | Tile / Paint / Gypsum / Wall Covering | AR-REC-032 | Recommended corrective actions | Actions logged | Visual Inspection | GEN-04-D-410 | Staircase Core | PHOTO-ARC-0410 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | MEP Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Housekeeping and labeling improvements required. | .
Architectural_Fabric | Internal Finishes | Tile / Paint / Gypsum / Wall Covering | AR-PHT-033 | Photo references for snags | IDs used | Visual Inspection | GEN-01-C-411 | Parking - Basement | PHOTO-ARC-0411 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | Specialist Vendor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Evidence captured; recommend rectification and re-test. | .
Architectural_Fabric | Internal Finishes | Tile / Paint / Gypsum / Wall Covering | AR-ACC-034 | Access constraints noted | Areas not accessible | Visual Inspection | GEN-04-D-412 | Electrical Room - LV | PHOTO-ARC-0412 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | MEP Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Housekeeping and labeling improvements required. | .
Architectural_Fabric | Internal Finishes | Tile / Paint / Gypsum / Wall Covering | AR-RES-035 | Maintainability assessment | Access panels/clearances | Visual Inspection | GEN-02-D-413 | Parking - Basement | PHOTO-ARC-0413 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | MEP Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | .
External_Parking | Pavement | Pavement / Markings | EX-SLP-001 | Floor slopes & drainage performance | No ponding; slopes verified | Visual Inspection | GEN-02-B-414 | Ground Floor - Lobby |  | Photo | 4 | 80% | 2.86 | 2.288 | 3 | FM Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
External_Parking | Pavement | Pavement / Markings | EX-DRN-002 | Stormwater drainage test/inspection | Inlets clear; discharge OK | Visual Inspection | GEN-G-C-415 | Basement B1 - Plantroom |  | Photo | 4 | 80% | 2.86 | 2.288 | 3 | Specialist Vendor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
External_Parking | Pavement | Pavement / Markings | EX-PAV-003 | Pavement stability/settlement check | No severe rutting/cracking | Visual Inspection | GEN-04-D-416 | Basement B1 - Plantroom | PHOTO-EXT-0416 | Photo | 0 | 0% | 2.86 | 0 | 3 | FM Contractor |  | - |  | N/A | Not applicable for this building / scope. | .
External_Parking | Pavement | Pavement / Markings | EX-MRK-004 | Markings & signage | Visible; consistent | Visual Inspection | GEN-01-D-417 | Basement B1 - Plantroom |  | Checklist | 4 | 80% | 2.86 | 2.288 | 3 | MEP Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
External_Parking | Pavement | Pavement / Markings | EX-LUX-005 | External/parking lux coverage | Meets minimum; uniformity | Visual Inspection | GEN-B1-D-418 | Level 01 - Office Area |  | Photo | 4 | 80% | 2.86 | 2.288 | 3 | FM Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
External_Parking | Pavement | Pavement / Markings | EX-GAT-006 | Entry/exit barriers operation | Reliable; safety sensors OK | Visual Inspection | GEN-G-A-419 | Level 02 - Office Area |  | Checklist | 4 | 80% | 2.86 | 2.288 | 3 | FM Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
External_Parking | Pavement | Pavement / Markings | EX-RFD-007 | RFID/access integration (if any) | Reads properly; logs ok | Visual Inspection | GEN-04-A-420 | Staircase Core |  | Test Report | 4 | 80% | 2.86 | 2.288 | 3 | Main Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
External_Parking | Pavement | Pavement / Markings | EX-CCTV-008 | CCTV coverage (parking) | Blind spots identified/none | Visual Inspection | GEN-04-D-421 | Roof - Mechanical Area |  | Photo | 5 | 100% | 2.86 | 2.86 | 3 | Owner |  | P4 |  | Verified | Inspected and found fully compliant; no observations noted. | .
External_Parking | Pavement | Pavement / Markings | EX-PRK-009 | Parking ventilation (if enclosed) | Operational; CO monitoring if any | Visual Inspection | GEN-B1-D-422 | External - Service Yard | PHOTO-EXT-0422 | Photo | 2 | 40% | 2.86 | 1.144 | 3 | Specialist Vendor | CAPA-0122 | P1 | 22/08/2024 | Open | Non-compliance / degraded condition observed; corrective action required. Trend indicates aging components; prioritize within next maintenance cycle. | .
External_Parking | Pavement | Pavement / Markings | EX-STR-010 | External structures (canopies) | Secure; corrosion minimal | Visual Inspection | GEN-04-A-423 | Level 01 - Office Area |  | Checklist | 4 | 80% | 2.86 | 2.288 | 3 | FM Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
External_Parking | Pavement | Pavement / Markings | EX-WLK-011 | Walkways/paving condition | No trip hazards | Visual Inspection | GEN-04-D-424 | Roof - Mechanical Area |  | Test Report | 4 | 80% | 2.86 | 2.288 | 3 | Specialist Vendor |  | P3 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
External_Parking | Pavement | Pavement / Markings | EX-ADA-012 | Accessible parking compliance | Marked; clear | Visual Inspection | GEN-03-C-425 | Roof - Mechanical Area | PHOTO-EXT-0425 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | FM Contractor | CAPA-0123 | P2 | 2024-05-09 | Open | Condition acceptable but requires attention; minor deficiencies observed. Evidence captured; recommend rectification and re-test. | .
External_Parking | Pavement | Pavement / Markings | EX-BOL-013 | Bollards/guardrails condition | Secure; reflective | Visual Inspection | GEN-03-C-426 | Electrical Room - LV |  | Photo | 4 | 80% | 2.86 | 2.288 | 3 | FM Contractor |  | P3 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
External_Parking | Pavement | Pavement / Markings | EX-LGT-014 | Pole/fixture condition | No corrosion; stable | Visual Inspection | GEN-04-D-427 | Level 02 - Office Area | PHOTO-EXT-0427 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | FM Contractor | CAPA-0124 | P3 | 29/09/2024 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
External_Parking | Pavement | Pavement / Markings | EX-POW-015 | Outdoor power points/IP rating | Safe; weatherproof | Visual Inspection | GEN-B1-A-428 | Staircase Core | PHOTO-EXT-0428 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | FM Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
External_Parking | Pavement | Pavement / Markings | EX-GRD-016 | Site grading & erosion | No erosion undermining | Visual Inspection | GEN-04-D-429 | Staircase Core |  | Test Report | 4 | 80% | 2.86 | 2.288 | 3 | FM Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
External_Parking | Pavement | Pavement / Markings | EX-FNC-017 | Perimeter fence/gates | Intact; locks functional | Visual Inspection | GEN-04-D-430 | Ground Floor - Lobby |  | Checklist | 4 | 80% | 2.86 | 2.288 | 3 | FM Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
External_Parking | Pavement | Pavement / Markings | EX-WST-018 | Waste area condition | Clean; access controlled | Visual Inspection | GEN-05-C-431 | Ground Floor - Lobby | PHOTO-EXT-0431 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | MEP Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Evidence captured; recommend rectification and re-test. | .
External_Parking | Pavement | Pavement / Markings | EX-SAF-019 | General safety hazards | No exposed edges; covers intact | Visual Inspection | GEN-G-B-432 | External - Service Yard | PHOTO-EXT-0432 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | MEP Contractor | CAPA-0125 | P3 | 29/09/2024 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
External_Parking | Pavement | Pavement / Markings | EX-DOC-020 | As-built external works drawings | Available | Visual Inspection | GEN-B1-B-433 | Level 01 - Office Area | PHOTO-EXT-0433 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | MEP Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
External_Parking | Pavement | Pavement / Markings | EX-SUM-021 | External works summary | Overall status | Visual Inspection | GEN-03-C-434 | Roof - Mechanical Area |  | Checklist | 4 | 80% | 2.86 | 2.288 | 3 | Main Contractor |  | P3 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
External_Parking | Pavement | Pavement / Markings | EX-RSK-022 | Risk classification per finding | P1–P4 | Visual Inspection | GEN-02-D-435 | Basement B1 - Plantroom | PHOTO-EXT-0435 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | FM Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
External_Parking | Pavement | Pavement / Markings | EX-REC-023 | Corrective actions logged | CAPA linked | Visual Inspection | GEN-B1-C-436 | Level 02 - Office Area | PHOTO-EXT-0436 | Photo | 0 | 0% | 2.86 | 0 | 3 | Owner |  | - |  | N/A | Not applicable for this building / scope. | .
External_Parking | Pavement | Pavement / Markings | EX-PHT-024 | Photo evidence & mapping | IDs | Visual Inspection | GEN-03-B-437 | Ground Floor - Lobby | PHOTO-EXT-0437 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | FM Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
External_Parking | Pavement | Pavement / Markings | EX-RES-025 | Maintainability & access | Access for cleaning/repairs | Visual Inspection | GEN-03-D-438 | External - Service Yard |  | Photo | 4 | 80% | 2.86 | 2.288 | 3 | Specialist Vendor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
External_Parking | Pavement | Pavement / Markings | EX-DSP-026 | Drain sump/pump (if any) | Operational; alarms ok | Visual Inspection | GEN-03-C-439 | Basement B1 - Plantroom | PHOTO-EXT-0439 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | MEP Contractor | CAPA-0126 | P3 | 29/09/2024 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | .
External_Parking | Pavement | Pavement / Markings | EX-CNT-027 | Parking control system (if any) | Functional; reports ok | Visual Inspection | GEN-02-A-440 | Level 02 - Office Area |  | Test Report | 5 | 100% | 2.86 | 2.86 | 3 | Main Contractor |  | P4 |  | Verified | Inspected and found fully compliant; no observations noted. | .
External_Parking | Pavement | Pavement / Markings | EX-PAY-028 | Payment system (if any) | Functional; reconciliation ok | Visual Inspection | GEN-01-B-441 | Level 01 - Office Area |  | Photo | 4 | 80% | 2.86 | 2.288 | 3 | FM Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
External_Parking | Pavement | Pavement / Markings | EX-TRF-029 | Traffic flow & signage | Clear; no conflict | Visual Inspection | GEN-G-B-442 | Roof - Mechanical Area | PHOTO-EXT-0442 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | FM Contractor | CAPA-0127 | P2 | 2024-05-09 | Open | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
External_Parking | Pavement | Pavement / Markings | EX-PRT-030 | Protective coatings (steelwork) | No peeling; touch-up needed | Visual Inspection | GEN-05-B-443 | Level 01 - Office Area | PHOTO-EXT-0443 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | FM Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | .
External_Parking | Pavement | Pavement / Markings | EX-LND-031 | Interface with landscape drainage | No conflicts | Visual Inspection | GEN-05-D-444 | Roof - Mechanical Area |  | Test Report | 4 | 80% | 2.86 | 2.288 | 3 | FM Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
External_Parking | Pavement | Pavement / Markings | EX-LUX2-032 | Emergency route lighting (non-fire) | Adequate for safe egress | Visual Inspection | GEN-03-A-445 | Level 03 - Office Area |  | Photo | 4 | 80% | 2.86 | 2.288 | 3 | FM Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
External_Parking | Pavement | Pavement / Markings | EX-ENV-033 | Environmental compliance (wastewater) | No discharge issues | Visual Inspection | GEN-G-A-446 | Ground Floor - Lobby | PHOTO-EXT-0446 | Photo | 2 | 40% | 2.86 | 1.144 | 3 | FM Contractor | CAPA-0128 | P2 | 2024-05-09 | Open | Non-compliance / degraded condition observed; corrective action required. Housekeeping and labeling improvements required. | .
External_Parking | Pavement | Pavement / Markings | EX-ACC-034 | Access constraints | Noted | Visual Inspection | GEN-B1-C-447 | Level 02 - Office Area | PHOTO-EXT-0447 | Photo | 0 | 0% | 2.86 | 0 | 3 | FM Contractor |  | - |  | N/A | Not applicable for this building / scope. | .
External_Parking | Pavement | Pavement / Markings | EX-KPI-035 | Service provider performance on externals | Quality/response | Visual Inspection | GEN-03-D-448 | External - Service Yard |  | Test Report | 4 | 80% | 2.86 | 2.288 | 3 | FM Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Landscape | Irrigation | Sprinkler / Drip Line / Valve / Controller / Pump | LA-IRR-001 | Irrigation flow/pressure | Within design; no leaks | Visual Inspection | GEN-01-B-449 | External - Service Yard | PHOTO-LAN-0449 | Photo | 2 | 40% | 2.86 | 1.144 | 3 | FM Contractor | CAPA-0129 | P2 | 2024-05-09 | Open | Non-compliance / degraded condition observed; corrective action required. Evidence captured; recommend rectification and re-test. | .
Landscape | Irrigation | Sprinkler / Drip Line / Valve / Controller / Pump | LA-COV-002 | Irrigation coverage uniformity | No dry patches; coverage adequate | Visual Inspection | GEN-05-A-450 | Basement B1 - Plantroom |  | Checklist | 5 | 100% | 2.86 | 2.86 | 3 | MEP Contractor |  | P4 |  | Verified | Inspected and found fully compliant; no observations noted. | .
Landscape | Irrigation | Sprinkler / Drip Line / Valve / Controller / Pump | LA-VLV-003 | Irrigation valves/controllers | Operational; schedules set | Visual Inspection | GEN-G-B-451 | Staircase Core | PHOTO-LAN-0451 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | Main Contractor | CAPA-0130 | P2 | 2024-05-09 | Open | Condition acceptable but requires attention; minor deficiencies observed. Evidence captured; recommend rectification and re-test. | .
Landscape | Irrigation | Sprinkler / Drip Line / Valve / Controller / Pump | LA-SOI-004 | Soil pH/salinity/fertility (if tested) | Within target range | Visual Inspection | GEN-04-B-452 | Basement B1 - Plantroom | PHOTO-LAN-0452 | Photo | 2 | 40% | 2.86 | 1.144 | 3 | FM Contractor | CAPA-0131 | P2 | 2024-05-09 | In Progress | Non-compliance / degraded condition observed; corrective action required. Housekeeping and labeling improvements required. | .
Landscape | Irrigation | Sprinkler / Drip Line / Valve / Controller / Pump | LA-PLT-005 | Plant health assessment | No major pests/disease | Visual Inspection | GEN-05-A-453 | Staircase Core |  | Checklist | 4 | 80% | 2.86 | 2.288 | 3 | MEP Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Landscape | Irrigation | Sprinkler / Drip Line / Valve / Controller / Pump | LA-PST-006 | Pest control effectiveness | Evidence/logs available | Visual Inspection | GEN-02-B-454 | External - Service Yard | PHOTO-LAN-0454 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | Specialist Vendor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Landscape | Irrigation | Sprinkler / Drip Line / Valve / Controller / Pump | LA-DRN-007 | Landscape drainage | No ponding | Visual Inspection | GEN-05-B-455 | Level 03 - Office Area | PHOTO-LAN-0455 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | MEP Contractor | CAPA-0132 | P3 | 29/09/2024 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Landscape | Irrigation | Sprinkler / Drip Line / Valve / Controller / Pump | LA-PTH-008 | Paths/hardscape condition | Stable; no trip hazards | Visual Inspection | GEN-04-B-456 | Roof - Mechanical Area | PHOTO-LAN-0456 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | Owner | CAPA-0133 | P2 | 2024-05-09 | Open | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
Landscape | Irrigation | Sprinkler / Drip Line / Valve / Controller / Pump | LA-EDG-009 | Edging/borders condition | Intact | Visual Inspection | GEN-02-C-457 | Electrical Room - LV |  | Test Report | 4 | 80% | 2.86 | 2.288 | 3 | Main Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Landscape | Irrigation | Sprinkler / Drip Line / Valve / Controller / Pump | LA-LUX-010 | Landscape lighting coverage | Adequate; no dark zones | Visual Inspection | GEN-03-B-458 | External - Service Yard | PHOTO-LAN-0458 | Photo | 2 | 40% | 2.86 | 1.144 | 3 | FM Contractor | CAPA-0134 | P2 | 2024-05-09 | Open | Non-compliance / degraded condition observed; corrective action required. Housekeeping and labeling improvements required. | .
Landscape | Irrigation | Sprinkler / Drip Line / Valve / Controller / Pump | LA-LMP-011 | Light fixtures condition | Weatherproof; clean | Visual Inspection | GEN-G-D-459 | Electrical Room - LV | PHOTO-LAN-0459 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | Specialist Vendor | CAPA-0135 | P2 | 2024-05-09 | Open | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
Landscape | Irrigation | Sprinkler / Drip Line / Valve / Controller / Pump | LA-WTR-012 | Watering schedule efficiency | No overwatering; optimized | Visual Inspection | GEN-G-B-460 | Level 02 - Office Area | PHOTO-LAN-0460 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | Main Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Landscape | Irrigation | Sprinkler / Drip Line / Valve / Controller / Pump | LA-ENV-013 | Environmental compliance (fertilizers) | Proper storage/use | Visual Inspection | GEN-03-D-461 | Roof - Mechanical Area | PHOTO-LAN-0461 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | MEP Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Landscape | Irrigation | Sprinkler / Drip Line / Valve / Controller / Pump | LA-DOC-014 | Landscape as-built/irrigation plans | Available | Visual Inspection | GEN-G-D-462 | Basement B1 - Plantroom |  | Test Report | 4 | 80% | 2.86 | 2.288 | 3 | Specialist Vendor |  | P3 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Landscape | Irrigation | Sprinkler / Drip Line / Valve / Controller / Pump | LA-SUM-015 | Landscape summary | Overall status | Visual Inspection | GEN-01-A-463 | Staircase Core | PHOTO-LAN-0463 | Photo | 2 | 40% | 2.86 | 1.144 | 3 | MEP Contractor | CAPA-0136 | P2 | 2024-05-09 | In Progress | Non-compliance / degraded condition observed; corrective action required. Evidence captured; recommend rectification and re-test. | .
Landscape | Irrigation | Sprinkler / Drip Line / Valve / Controller / Pump | LA-RSK-016 | Risk classification per finding | P1–P4 | Visual Inspection | GEN-02-D-464 | Roof - Mechanical Area |  | Checklist | 4 | 80% | 2.86 | 2.288 | 3 | FM Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Landscape | Irrigation | Sprinkler / Drip Line / Valve / Controller / Pump | LA-REC-017 | Corrective actions logged | CAPA linked | Visual Inspection | GEN-B1-A-465 | Electrical Room - LV |  | Test Report | 4 | 80% | 2.86 | 2.288 | 3 | Specialist Vendor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Landscape | Irrigation | Sprinkler / Drip Line / Valve / Controller / Pump | LA-PHT-018 | Photo evidence | IDs | Visual Inspection | GEN-B1-B-466 | Roof - Mechanical Area |  | Test Report | 4 | 80% | 2.86 | 2.288 | 3 | FM Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Landscape | Irrigation | Sprinkler / Drip Line / Valve / Controller / Pump | LA-ACC-019 | Access constraints | Noted | Visual Inspection | GEN-01-B-467 | Ground Floor - Lobby | PHOTO-LAN-0467 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | Specialist Vendor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Evidence captured; recommend rectification and re-test. | .
Landscape | Irrigation | Sprinkler / Drip Line / Valve / Controller / Pump | LA-ESG-020 | ESG/Water conservation alignment | Practices reviewed | Visual Inspection | GEN-05-D-468 | Staircase Core | PHOTO-LAN-0468 | Photo | 2 | 40% | 2.86 | 1.144 | 3 | FM Contractor | CAPA-0137 | P2 | 2024-05-09 | In Progress | Non-compliance / degraded condition observed; corrective action required. Trend indicates aging components; prioritize within next maintenance cycle. | .
Landscape | Irrigation | Sprinkler / Drip Line / Valve / Controller / Pump | LA-QLT-021 | Service quality (contractor) | Performance rating | Visual Inspection | GEN-G-C-469 | External - Service Yard | PHOTO-LAN-0469 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | FM Contractor | CAPA-0138 | P2 | 2024-05-09 | Open | Condition acceptable but requires attention; minor deficiencies observed. Evidence captured; recommend rectification and re-test. | .
Landscape | Irrigation | Sprinkler / Drip Line / Valve / Controller / Pump | LA-IRR2-022 | Irrigation leak test | No hidden leaks | Visual Inspection | GEN-G-A-470 | External - Service Yard | PHOTO-LAN-0470 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | MEP Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Evidence captured; recommend rectification and re-test. | .
Landscape | Irrigation | Sprinkler / Drip Line / Valve / Controller / Pump | LA-MTR-023 | Irrigation sub-metering | Reads/logs | Visual Inspection | GEN-02-C-471 | Basement B1 - Plantroom |  | Photo | 4 | 80% | 2.86 | 2.288 | 3 | MEP Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Landscape | Irrigation | Sprinkler / Drip Line / Valve / Controller / Pump | LA-TRE-024 | Tree support/stability | Safe; no hazards | Visual Inspection | GEN-01-D-472 | Level 01 - Office Area | PHOTO-LAN-0472 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | Specialist Vendor | CAPA-0139 | P2 | 2024-05-09 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Housekeeping and labeling improvements required. | .
Landscape | Irrigation | Sprinkler / Drip Line / Valve / Controller / Pump | LA-MUL-025 | Mulch/ground cover condition | Adequate | Visual Inspection | GEN-02-C-473 | Parking - Basement | PHOTO-LAN-0473 | Photo | 2 | 40% | 2.86 | 1.144 | 3 | FM Contractor |  | P2 |  | Closed | Non-compliance / degraded condition observed; corrective action required. Housekeeping and labeling improvements required. | .
Landscape | Irrigation | Sprinkler / Drip Line / Valve / Controller / Pump | LA-WST-026 | Green waste handling | Proper disposal | Visual Inspection | GEN-03-D-474 | Electrical Room - LV | PHOTO-LAN-0474 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | Main Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
Landscape | Irrigation | Sprinkler / Drip Line / Valve / Controller / Pump | LA-DRP-027 | Drip lines condition | No clogging | Visual Inspection | GEN-04-B-475 | External - Service Yard | PHOTO-LAN-0475 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | MEP Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Housekeeping and labeling improvements required. | .
Landscape | Irrigation | Sprinkler / Drip Line / Valve / Controller / Pump | LA-SPR-028 | Sprinkler heads condition | Aligned; not broken | Visual Inspection | GEN-04-C-476 | Level 03 - Office Area | PHOTO-LAN-0476 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | FM Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Evidence captured; recommend rectification and re-test. | .
Landscape | Irrigation | Sprinkler / Drip Line / Valve / Controller / Pump | LA-PRN-029 | Pruning status | Good | Visual Inspection | GEN-01-C-477 | Electrical Room - LV | PHOTO-LAN-0477 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | Specialist Vendor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
Landscape | Irrigation | Sprinkler / Drip Line / Valve / Controller / Pump | LA-INV-030 | Inventory list (species/qty) | Documented | Visual Inspection | GEN-02-D-478 | Basement B1 - Plantroom |  | Test Report | 4 | 80% | 2.86 | 2.288 | 3 | Main Contractor |  | P3 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Landscape | Irrigation | Sprinkler / Drip Line / Valve / Controller / Pump | LA-PRT-031 | Protection measures | Guards/fencing for plants | Visual Inspection | GEN-B1-B-479 | Level 03 - Office Area |  | Photo | 4 | 80% | 2.86 | 2.288 | 3 | Specialist Vendor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Landscape | Irrigation | Sprinkler / Drip Line / Valve / Controller / Pump | LA-STD-032 | Standards compliance (municipal) | Checklist | Visual Inspection | GEN-G-A-480 | Level 03 - Office Area | PHOTO-LAN-0480 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | MEP Contractor | CAPA-0140 | P3 | 29/09/2024 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Evidence captured; recommend rectification and re-test. | .
Landscape | Irrigation | Sprinkler / Drip Line / Valve / Controller / Pump | LA-HSE-033 | Safety hazards | Checklist | Visual Inspection | GEN-G-C-481 | Level 01 - Office Area |  | Photo | 5 | 100% | 2.86 | 2.86 | 3 | MEP Contractor |  | P4 |  | Closed | Inspected and found fully compliant; no observations noted. | .
Landscape | Irrigation | Sprinkler / Drip Line / Valve / Controller / Pump | LA-RES-034 | Maintainability | None | Visual Inspection | GEN-05-D-482 | Staircase Core |  | Photo | 4 | 80% | 2.86 | 2.288 | 3 | MEP Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Landscape | Irrigation | Sprinkler / Drip Line / Valve / Controller / Pump | LA-KPI-035 | SLA adherence | Access for upkeep | Visual Inspection | GEN-05-B-483 | Level 02 - Office Area | PHOTO-LAN-0483 | Photo | 2 | 40% | 2.86 | 1.144 | 3 | Specialist Vendor | CAPA-0141 | P2 | 2024-05-09 | In Progress | Non-compliance / degraded condition observed; corrective action required. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Pools_WaterFeatures | Filtration | Pool Pump / Filter | PO-WQ-001 | Water quality test (chlorine/pH) | Response/quality | Visual Inspection | GEN-01-D-484 | Basement B1 - Plantroom | PHOTO-POO-0484 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | Main Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Evidence captured; recommend rectification and re-test. | .
Pools_WaterFeatures | Filtration | Pool Pump / Filter | PO-BAC-002 | Bacteria/microbial test (if required) | Within safe range | Visual Inspection | GEN-01-C-485 | Electrical Room - LV | PHOTO-POO-0485 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | FM Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
Pools_WaterFeatures | Filtration | Pool Pump / Filter | PO-LK-003 | Pool leakage test | Lab compliant | Visual Inspection | GEN-G-C-486 | Staircase Core |  | Checklist | 5 | 100% | 2.86 | 2.86 | 3 | Owner |  | P4 |  | Verified | Inspected and found fully compliant; no observations noted. | .
Pools_WaterFeatures | Filtration | Pool Pump / Filter | PO-FLT-004 | Filtration system performance | No leakage detected | Visual Inspection | GEN-G-A-487 | Electrical Room - LV |  | Test Report | 4 | 80% | 2.86 | 2.288 | 3 | MEP Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Pools_WaterFeatures | Filtration | Pool Pump / Filter | PO-PMP-005 | Pump duty point | Pressure differential acceptable | Visual Inspection | GEN-03-C-488 | Level 03 - Office Area |  | Checklist | 4 | 80% | 2.86 | 2.288 | 3 | FM Contractor |  | P3 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Pools_WaterFeatures | Filtration | Pool Pump / Filter | PO-HTR-006 | Temperature control performance | Within ±10% of curve | Visual Inspection | GEN-05-D-489 | Ground Floor - Lobby | PHOTO-POO-0489 | Photo | 1 | 20% | 2.86 | 0.572 | 3 | MEP Contractor | CAPA-0142 | P1 | 22/08/2024 | In Progress | Critical deficiency observed; immediate corrective action required to mitigate risk. Preventive maintenance records incomplete; verify PM completion. | .
Pools_WaterFeatures | Filtration | Pool Pump / Filter | PO-SAF-007 | Safety equipment availability | Stable; controls working | Visual Inspection | GEN-01-D-490 | Level 01 - Office Area | PHOTO-POO-0490 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | FM Contractor | CAPA-0143 | P3 | 29/09/2024 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Housekeeping and labeling improvements required. | .
Pools_WaterFeatures | Filtration | Pool Pump / Filter | PO-LUX-008 | Pool lighting/night safety | Rescue kits present | Visual Inspection | GEN-01-D-491 | Electrical Room - LV |  | Photo | 4 | 80% | 2.86 | 2.288 | 3 | FM Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Pools_WaterFeatures | Filtration | Pool Pump / Filter | PO-DRN-009 | Backwash/drainage handling | Adequate; IP rating | Visual Inspection | GEN-05-A-492 | Roof - Mechanical Area | PHOTO-POO-0492 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | MEP Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Pools_WaterFeatures | Filtration | Pool Pump / Filter | PO-DOC-010 | O&M manuals & chemical logs | Proper discharge | Visual Inspection | GEN-02-A-493 | Roof - Mechanical Area | PHOTO-POO-0493 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | MEP Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Pools_WaterFeatures | Filtration | Pool Pump / Filter | PO-REC-011 | Corrective actions logged | Complete | Visual Inspection | GEN-03-B-494 | Level 01 - Office Area | PHOTO-POO-0494 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | MEP Contractor | CAPA-0144 | P2 | 2024-05-09 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Evidence captured; recommend rectification and re-test. | .
Pools_WaterFeatures | Filtration | Pool Pump / Filter | PO-RSK-012 | Risk classification | CAPA linked | Visual Inspection | GEN-B1-A-495 | External - Service Yard | PHOTO-POO-0495 | Photo | 2 | 40% | 2.86 | 1.144 | 3 | FM Contractor | CAPA-0145 | P1 | 22/08/2024 | Open | Non-compliance / degraded condition observed; corrective action required. Evidence captured; recommend rectification and re-test. | .
Pools_WaterFeatures | Filtration | Pool Pump / Filter | PO-PHT-013 | Photo evidence | P1–P4 | Visual Inspection | GEN-05-B-496 | Level 01 - Office Area |  | Checklist | 4 | 80% | 2.86 | 2.288 | 3 | Main Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Pools_WaterFeatures | Filtration | Pool Pump / Filter | PO-ACC-014 | Access safety (slips) | IDs | Visual Inspection | GEN-04-C-497 | Ground Floor - Lobby | PHOTO-POO-0497 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | Main Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
Pools_WaterFeatures | Filtration | Pool Pump / Filter | PO-CHM-015 | Chemical storage compliance | Non-slip surfaces | Visual Inspection | GEN-B1-C-498 | Ground Floor - Lobby | PHOTO-POO-0498 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | FM Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
Pools_WaterFeatures | Filtration | Pool Pump / Filter | PO-ALM-016 | Alarms/interlocks (if any) | Safe; ventilated | Visual Inspection | GEN-03-B-499 | Level 01 - Office Area | PHOTO-POO-0499 | Photo | 2 | 40% | 2.86 | 1.144 | 3 | MEP Contractor | CAPA-0146 | P1 | 22/08/2024 | In Progress | Non-compliance / degraded condition observed; corrective action required. Housekeeping and labeling improvements required. | .
Pools_WaterFeatures | Filtration | Pool Pump / Filter | PO-CLN-017 | Pool cleanliness | Functional | Visual Inspection | GEN-G-A-500 | Ground Floor - Lobby | PHOTO-POO-0500 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | FM Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | .
Pools_WaterFeatures | Filtration | Pool Pump / Filter | PO-KPI-018 | Service provider performance | Good | Visual Inspection | GEN-03-B-501 | Electrical Room - LV |  | Test Report | 4 | 80% | 2.86 | 2.288 | 3 | Main Contractor |  | P3 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Pools_WaterFeatures | Filtration | Pool Pump / Filter | PO-INS-019 | Pool structure/tiles | SLA met | Visual Inspection | GEN-03-D-502 | Level 02 - Office Area |  | Test Report | 4 | 80% | 2.86 | 2.288 | 3 | FM Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Pools_WaterFeatures | Filtration | Pool Pump / Filter | PO-SKD-020 | Maintenance schedule compliance | No cracks/loose tiles | Visual Inspection | GEN-04-A-503 | Level 01 - Office Area |  | Test Report | 4 | 80% | 2.86 | 2.288 | 3 | FM Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Pools_WaterFeatures | Filtration | Pool Pump / Filter | PO-WTR-021 | Make-up water and metering | PM completed | Visual Inspection | GEN-04-C-504 | External - Service Yard |  | Photo | 4 | 80% | 2.86 | 2.288 | 3 | FM Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Pools_WaterFeatures | Filtration | Pool Pump / Filter | PO-FNC-022 | Perimeter safety barriers | Functional | Visual Inspection | GEN-01-B-505 | Basement B1 - Plantroom | PHOTO-POO-0505 | Photo | 2 | 40% | 2.86 | 1.144 | 3 | MEP Contractor |  | P2 |  | Closed | Non-compliance / degraded condition observed; corrective action required. Housekeeping and labeling improvements required. | .
Pools_WaterFeatures | Filtration | Pool Pump / Filter | PO-SGN-023 | User signage (rules) | Compliant | Visual Inspection | GEN-03-B-506 | External - Service Yard | PHOTO-POO-0506 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | FM Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Housekeeping and labeling improvements required. | .
Pools_WaterFeatures | Filtration | Pool Pump / Filter | PO-SUM-024 | Pool summary | Clear | Visual Inspection | GEN-05-C-507 | Level 03 - Office Area | PHOTO-POO-0507 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | FM Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Housekeeping and labeling improvements required. | .
Pools_WaterFeatures | Filtration | Pool Pump / Filter | PO-RES-025 | Resilience/backup (if any) | Overall status | Visual Inspection | GEN-04-D-508 | Roof - Mechanical Area | PHOTO-POO-0508 | Photo | 0 | 0% | 2.86 | 0 | 3 | MEP Contractor |  | - |  | N/A | Not applicable for this building / scope. | .
Pools_WaterFeatures | Filtration | Pool Pump / Filter | PO-ENV-026 | Environmental compliance | Verified | Visual Inspection | GEN-02-B-509 | Staircase Core | PHOTO-POO-0509 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | Specialist Vendor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
Pools_WaterFeatures | Filtration | Pool Pump / Filter | PO-PRF-027 | Energy efficiency (pumps/heaters) | Waste handling OK | Visual Inspection | GEN-04-D-510 | Level 01 - Office Area |  | Photo | 4 | 80% | 2.86 | 2.288 | 3 | Specialist Vendor | CAPA-0147 | P3 | 29/09/2024 | In Progress | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Pools_WaterFeatures | Filtration | Pool Pump / Filter | PO-IAQ-028 | Indoor pool ventilation (if any) | Optimization opportunities | Visual Inspection | GEN-B1-B-511 | Electrical Room - LV | PHOTO-POO-0511 | Photo | 2 | 40% | 2.86 | 1.144 | 3 | Specialist Vendor | CAPA-0148 | P2 | 2024-05-09 | In Progress | Non-compliance / degraded condition observed; corrective action required. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Pools_WaterFeatures | Filtration | Pool Pump / Filter | PO-DRS-029 | Drain covers safety | Adequate | Visual Inspection | GEN-B1-C-512 | Electrical Room - LV | PHOTO-POO-0512 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | FM Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Pools_WaterFeatures | Filtration | Pool Pump / Filter | PO-TRN-030 | FM training on pool systems | Secure | Visual Inspection | GEN-05-D-513 | External - Service Yard | PHOTO-POO-0513 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | FM Contractor | CAPA-0149 | P3 | 29/09/2024 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Housekeeping and labeling improvements required. | .
Pools_WaterFeatures | Filtration | Pool Pump / Filter | PO-TST-031 | Test certificates present | Evidence | Visual Inspection | GEN-04-B-514 | Staircase Core |  | Checklist | 4 | 80% | 2.86 | 2.288 | 3 | MEP Contractor | CAPA-0150 | P3 | 29/09/2024 | In Progress | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Pools_WaterFeatures | Filtration | Pool Pump / Filter | PO-EXT-032 | Water features pumps/nozzles | Attached | Visual Inspection | GEN-B1-D-515 | Ground Floor - Lobby | PHOTO-POO-0515 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | MEP Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Housekeeping and labeling improvements required. | .
Pools_WaterFeatures | Filtration | Pool Pump / Filter | PO-LND-033 | Integration with landscape drainage | Operational | Visual Inspection | GEN-03-B-516 | External - Service Yard | PHOTO-POO-0516 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | MEP Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Evidence captured; recommend rectification and re-test. | .
Pools_WaterFeatures | Filtration | Pool Pump / Filter | PO-HSE-034 | HSE hazards & controls | No issues | Visual Inspection | GEN-B1-B-517 | Level 03 - Office Area |  | Checklist | 4 | 80% | 2.86 | 2.288 | 3 | FM Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Pools_WaterFeatures | Filtration | Pool Pump / Filter | PO-KPI-035 | Monthly performance reporting | OK | Visual Inspection | GEN-01-B-518 | Ground Floor - Lobby | PHOTO-POO-0518 | Photo | 1 | 20% | 2.86 | 0.572 | 3 | MEP Contractor | CAPA-0151 | P1 | 22/08/2024 | In Progress | Critical deficiency observed; immediate corrective action required to mitigate risk. Preventive maintenance records incomplete; verify PM completion. | .
Waste_Management | Infrastructure | Waste Room / Chute / Compactor / Baler / Bins | WM-WR-001 | Waste room condition | Available | Visual Inspection | GEN-G-D-519 | Ground Floor - Lobby |  | Checklist | 4 | 80% | 2.86 | 2.288 | 3 | FM Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Waste_Management | Infrastructure | Waste Room / Chute / Compactor / Baler / Bins | WM-WC-002 | Waste chute operation | Clean; ventilated; no pest evidence | Visual Inspection | GEN-02-C-520 | Ground Floor - Lobby |  | Photo | 4 | 80% | 2.86 | 2.288 | 3 | FM Contractor |  | P3 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Waste_Management | Infrastructure | Waste Room / Chute / Compactor / Baler / Bins | WM-CB-003 | Compactor/baler operation | Smooth operation; doors seal properly | Visual Inspection | GEN-04-A-521 | Basement B1 - Plantroom |  | Test Report | 4 | 80% | 2.86 | 2.288 | 3 | Main Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Waste_Management | Infrastructure | Waste Room / Chute / Compactor / Baler / Bins | WM-BS-004 | Bin station adequacy | Operational; safety interlocks work | Visual Inspection | GEN-05-A-522 | Staircase Core | PHOTO-WAS-0522 | Photo | 2 | 40% | 2.86 | 1.144 | 3 | MEP Contractor | CAPA-0152 | P1 | 22/08/2024 | In Progress | Non-compliance / degraded condition observed; corrective action required. Evidence captured; recommend rectification and re-test. | .
Waste_Management | Infrastructure | Waste Room / Chute / Compactor / Baler / Bins | WM-WC-005 | Waste contract verification | Sufficient capacity; accessible for collection | Visual Inspection | GEN-02-A-523 | Ground Floor - Lobby | PHOTO-WAS-0523 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | FM Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Evidence captured; recommend rectification and re-test. | .
Waste_Management | Infrastructure | Waste Room / Chute / Compactor / Baler / Bins | WM-RP-006 | Recycling program effectiveness | Contract in place; collection schedule | Visual Inspection | GEN-02-B-524 | Level 03 - Office Area | PHOTO-WAS-0524 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | FM Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Housekeeping and labeling improvements required. | .
Waste_Management | Infrastructure | Waste Room / Chute / Compactor / Baler / Bins | WM-HS-007 | Hazardous waste storage | Adequate segregation; diversion rate tracked | Visual Inspection | GEN-B1-B-525 | Basement B1 - Plantroom | PHOTO-WAS-0525 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | Specialist Vendor |  | P2 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
Waste_Management | Infrastructure | Waste Room / Chute / Compactor / Baler / Bins | WM-SK-008 | Spill kit availability | Secure; labeled; spill containment | Visual Inspection | GEN-B1-A-526 | Roof - Mechanical Area |  | Photo | 4 | 80% | 2.86 | 2.288 | 3 | MEP Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Waste_Management | Infrastructure | Waste Room / Chute / Compactor / Baler / Bins | WM-VS-009 | Waste area ventilation | Kits available; stocked; accessible | Visual Inspection | GEN-04-B-527 | External - Service Yard |  | Photo | 4 | 80% | 2.86 | 2.288 | 3 | FM Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Waste_Management | Infrastructure | Waste Room / Chute / Compactor / Baler / Bins | WM-PC-010 | Pest control measures | Adequate air changes; odors controlled | Visual Inspection | GEN-B1-B-528 | Basement B1 - Plantroom |  | Checklist | 5 | 100% | 2.86 | 2.86 | 3 | FM Contractor |  | P4 |  | Closed | Inspected and found fully compliant; no observations noted. | .
Waste_Management | Infrastructure | Waste Room / Chute / Compactor / Baler / Bins | WM-FI-011 | Fire protection | Effective; no infestation evidence | Visual Inspection | GEN-B1-D-529 | External - Service Yard |  | Test Report | 4 | 80% | 2.86 | 2.288 | 3 | Specialist Vendor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Waste_Management | Infrastructure | Waste Room / Chute / Compactor / Baler / Bins | WM-SO-012 | Chute cleaning access | Fire extinguishers; no combustible accumulation | Visual Inspection | GEN-01-B-530 | Basement B1 - Plantroom |  | Test Report | 4 | 80% | 2.86 | 2.288 | 3 | FM Contractor |  | P3 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Waste_Management | Infrastructure | Waste Room / Chute / Compactor / Baler / Bins | WM-MA-013 | Maintenance records | Access panels available; cleanable | Visual Inspection | GEN-03-B-531 | Electrical Room - LV | PHOTO-WAS-0531 | Photo | 1 | 20% | 2.86 | 0.572 | 3 | FM Contractor | CAPA-0153 | P1 | 22/08/2024 | Open | Critical deficiency observed; immediate corrective action required to mitigate risk. Evidence captured; recommend rectification and re-test. | .
Waste_Management | Infrastructure | Waste Room / Chute / Compactor / Baler / Bins | WM-WA-014 | Washdown facility | Regular maintenance documented | Visual Inspection | GEN-02-A-532 | Basement B1 - Plantroom |  | Photo | 4 | 80% | 2.86 | 2.288 | 3 | Specialist Vendor |  | P3 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Waste_Management | Infrastructure | Waste Room / Chute / Compactor / Baler / Bins | WM-DO-015 | Documentation | Area can be cleaned; drainage works | Visual Inspection | GEN-04-B-533 | Level 02 - Office Area | PHOTO-WAS-0533 | Photo | 2 | 40% | 2.86 | 1.144 | 3 | MEP Contractor | CAPA-0154 | P2 | 2024-05-09 | In Progress | Non-compliance / degraded condition observed; corrective action required. Preventive maintenance records incomplete; verify PM completion. | .
Waste_Management | Infrastructure | Waste Room / Chute / Compactor / Baler / Bins | WM-ED-016 | Education/signage | Waste transfer notes; manifests available | Visual Inspection | GEN-04-C-534 | Roof - Mechanical Area |  | Checklist | 4 | 80% | 2.86 | 2.288 | 3 | Specialist Vendor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Waste_Management | Infrastructure | Waste Room / Chute / Compactor / Baler / Bins | WM-TR-017 | Training on hazardous waste | Clear signage; user awareness | Visual Inspection | GEN-02-B-535 | Level 03 - Office Area |  | Photo | 4 | 80% | 2.86 | 2.288 | 3 | MEP Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Waste_Management | Infrastructure | Waste Room / Chute / Compactor / Baler / Bins | WM-DR-018 | Drill/spill response test | Staff trained; records available | Visual Inspection | GEN-B1-C-536 | Level 03 - Office Area |  | Photo | 4 | 80% | 2.86 | 2.288 | 3 | FM Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Waste_Management | Infrastructure | Waste Room / Chute / Compactor / Baler / Bins | WM-FA-019 | Fan maintenance | Response procedure tested | Visual Inspection | GEN-G-A-537 | Electrical Room - LV | PHOTO-WAS-0537 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | Main Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | .
Waste_Management | Infrastructure | Waste Room / Chute / Compactor / Baler / Bins | WM-MO-020 | Monitoring records | Fans operational; filters clean | Visual Inspection | GEN-01-B-538 | Ground Floor - Lobby | PHOTO-WAS-0538 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | FM Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
Waste_Management | Infrastructure | Waste Room / Chute / Compactor / Baler / Bins | WM-LO-021 | Location suitability | Pest activity logs maintained | Visual Inspection | GEN-B1-D-539 | Level 01 - Office Area |  | Photo | 4 | 80% | 2.86 | 2.288 | 3 | FM Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Waste_Management | Infrastructure | Waste Room / Chute / Compactor / Baler / Bins | WM-NO-022 | Noise levels | Away from food areas; proper access | Visual Inspection | GEN-B1-A-540 | Level 03 - Office Area | PHOTO-WAS-0540 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | FM Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | .
Waste_Management | Infrastructure | Waste Room / Chute / Compactor / Baler / Bins | WM-EN-023 | Energy consumption | Chute operation not excessive | Visual Inspection | GEN-03-B-541 | External - Service Yard | PHOTO-WAS-0541 | Photo | 2 | 40% | 2.86 | 1.144 | 3 | FM Contractor | CAPA-0155 | P2 | 2024-05-09 | Open | Non-compliance / degraded condition observed; corrective action required. Evidence captured; recommend rectification and re-test. | .
Waste_Management | Infrastructure | Waste Room / Chute / Compactor / Baler / Bins | WM-OD-024 | Odor control | Within expected range | Visual Inspection | GEN-01-A-542 | Parking - Basement | PHOTO-WAS-0542 | Photo | 2 | 40% | 2.86 | 1.144 | 3 | MEP Contractor |  | P2 |  | Closed | Non-compliance / degraded condition observed; corrective action required. Trend indicates aging components; prioritize within next maintenance cycle. | .
Waste_Management | Infrastructure | Waste Room / Chute / Compactor / Baler / Bins | WM-CO-025 | Contractor performance | Effective; no complaints | Visual Inspection | GEN-03-A-543 | Parking - Basement | PHOTO-WAS-0543 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | Main Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Waste_Management | Infrastructure | Waste Room / Chute / Compactor / Baler / Bins | WM-AU-026 | Audit of waste streams | KPIs met; service quality good | Visual Inspection | GEN-B1-A-544 | Parking - Basement | PHOTO-WAS-0544 | Photo | 2 | 40% | 2.86 | 1.144 | 3 | MEP Contractor | CAPA-0156 | P2 | 2024-05-09 | In Progress | Non-compliance / degraded condition observed; corrective action required. Trend indicates aging components; prioritize within next maintenance cycle. | .
Waste_Management | Infrastructure | Waste Room / Chute / Compactor / Baler / Bins | WM-TE-027 | Temperature control (if required) | Regular audits conducted | Visual Inspection | GEN-G-D-545 | External - Service Yard | PHOTO-WAS-0545 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | FM Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | .
Waste_Management | Infrastructure | Waste Room / Chute / Compactor / Baler / Bins | WM-RE-028 | Replenishment process | Within specified range | Visual Inspection | GEN-05-A-546 | Parking - Basement |  | Test Report | 4 | 80% | 2.86 | 2.288 | 3 | MEP Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Waste_Management | Infrastructure | Waste Room / Chute / Compactor / Baler / Bins | WM-AL-029 | Alarm for fan failure | Kits replenished after use | Visual Inspection | GEN-05-A-547 | External - Service Yard | PHOTO-WAS-0547 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | MEP Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Evidence captured; recommend rectification and re-test. | .
Waste_Management | Infrastructure | Waste Room / Chute / Compactor / Baler / Bins | WM-CH-030 | Chemical usage records | Alarm if ventilation fails | Visual Inspection | GEN-02-A-548 | Roof - Mechanical Area |  | Checklist | 4 | 80% | 2.86 | 2.288 | 3 | FM Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Waste_Management | Infrastructure | Waste Room / Chute / Compactor / Baler / Bins | WM-SI-031 | Signage | Pesticide use documented | Visual Inspection | GEN-G-A-549 | Electrical Room - LV | PHOTO-WAS-0549 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | FM Contractor | CAPA-0157 | P3 | 29/09/2024 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Waste_Management | Infrastructure | Waste Room / Chute / Compactor / Baler / Bins | WM-FL-032 | Flow test | All required safety signs present | Visual Inspection | GEN-03-D-550 | Level 03 - Office Area | PHOTO-WAS-0550 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | FM Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | .
Waste_Management | Infrastructure | Waste Room / Chute / Compactor / Baler / Bins | WM-SA-033 | Safety training | Waste flows freely; no blockages | Visual Inspection | GEN-02-C-551 | Ground Floor - Lobby | PHOTO-WAS-0551 | Photo | 2 | 40% | 2.86 | 1.144 | 3 | MEP Contractor | CAPA-0158 | P2 | 2024-05-09 | Open | Non-compliance / degraded condition observed; corrective action required. Preventive maintenance records incomplete; verify PM completion. | .
Waste_Management | Infrastructure | Waste Room / Chute / Compactor / Baler / Bins | WM-CA-034 | Capacity planning | Operators trained; certificates available | Visual Inspection | GEN-B1-B-552 | Electrical Room - LV | PHOTO-WAS-0552 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | FM Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Waste_Management | Infrastructure | Waste Room / Chute / Compactor / Baler / Bins | WM-RT-035 | Reporting | Adequate for building occupancy | Visual Inspection | GEN-02-C-553 | Parking - Basement |  | Checklist | 4 | 80% | 2.86 | 2.288 | 3 | FM Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Sustainability | Energy | Energy Meter / Submeter | SU-EN-001 | Energy audit readiness (ISO 50001 aligned) | Regular waste reports generated | Visual Inspection | SUS-02-C-554 | Roof - Mechanical Area | PHOTO-SUS-0554 | Photo | 0 | 0% | 2.86 | 0 | 3 | Specialist Vendor |  | - |  | N/A | Not applicable for this building / scope. | .
Sustainability | Energy | Energy Meter / Submeter | SU-LP-002 | Load profiling analysis | Baseline established | Visual Inspection | SUS-05-C-555 | Level 01 - Office Area | PHOTO-SUS-0555 | Photo | 2 | 40% | 2.86 | 1.144 | 3 | MEP Contractor | CAPA-0159 | P1 | 22/08/2024 | In Progress | Non-compliance / degraded condition observed; corrective action required. Housekeeping and labeling improvements required. | .
Sustainability | Energy | Energy Meter / Submeter | SU-LOSS-003 | Energy leakage/loss assessment | Peak/off-peak patterns known | Visual Inspection | SUS-02-B-556 | External - Service Yard | PHOTO-SUS-0556 | Photo | 2 | 40% | 2.86 | 1.144 | 3 | FM Contractor | CAPA-0160 | P2 | 2024-05-09 | Open | Non-compliance / degraded condition observed; corrective action required. Housekeeping and labeling improvements required. | .
Sustainability | Energy | Energy Meter / Submeter | SU-IAQ-004 | Indoor air quality test (CO₂/PM/VOC) | Loss points identified | Visual Inspection | SUS-B1-C-557 | External - Service Yard |  | Photo | 4 | 80% | 2.86 | 2.288 | 3 | FM Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Sustainability | Energy | Energy Meter / Submeter | SU-TH-005 | Thermal enclosure assessment | Within target | Visual Inspection | SUS-G-C-558 | Electrical Room - LV |  | Test Report | 4 | 80% | 2.86 | 2.288 | 3 | MEP Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Sustainability | Energy | Energy Meter / Submeter | SU-WA-006 | Water conservation assessment | Insulation/bridges reviewed | Visual Inspection | SUS-G-A-559 | Staircase Core | PHOTO-SUS-0559 | Photo | 2 | 40% | 2.86 | 1.144 | 3 | Main Contractor | CAPA-0161 | P2 | 2024-05-09 | In Progress | Non-compliance / degraded condition observed; corrective action required. Preventive maintenance records incomplete; verify PM completion. | .
Sustainability | Energy | Energy Meter / Submeter | SU-LEED-007 | Green certification readiness (optional) | Savings opportunities | Visual Inspection | SUS-01-A-560 | Electrical Room - LV |  | Photo | 4 | 80% | 2.86 | 2.288 | 3 | Specialist Vendor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Sustainability | Energy | Energy Meter / Submeter | SU-MTR-008 | Energy/water metering completeness | Gap assessment | Visual Inspection | SUS-01-A-561 | External - Service Yard |  | Test Report | 4 | 80% | 2.86 | 2.288 | 3 | MEP Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Sustainability | Energy | Energy Meter / Submeter | SU-KPI-009 | Sustainability KPIs reporting | Submetering adequate | Visual Inspection | SUS-03-D-562 | Ground Floor - Lobby | PHOTO-SUS-0562 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | FM Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Housekeeping and labeling improvements required. | .
Sustainability | Energy | Energy Meter / Submeter | SU-WST-010 | Waste handling compliance (non-fire) | Available | Visual Inspection | SUS-01-D-563 | Roof - Mechanical Area | PHOTO-SUS-0563 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | FM Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Housekeeping and labeling improvements required. | .
Sustainability | Energy | Energy Meter / Submeter | SU-EMS-011 | Environmental management practices | Segregation and logs | Visual Inspection | SUS-04-D-564 | Electrical Room - LV | PHOTO-SUS-0564 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | FM Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | .
Sustainability | Energy | Energy Meter / Submeter | SU-NM-012 | Noise mapping (if required) | Controls in place | Visual Inspection | SUS-B1-D-565 | Ground Floor - Lobby | PHOTO-SUS-0565 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | FM Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | .
Sustainability | Energy | Energy Meter / Submeter | SU-LGT-013 | Lighting energy efficiency | Results within limits | Visual Inspection | SUS-G-B-566 | Parking - Basement | PHOTO-SUS-0566 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | Specialist Vendor | CAPA-0162 | P2 | 2024-05-09 | Open | Condition acceptable but requires attention; minor deficiencies observed. Housekeeping and labeling improvements required. | .
Sustainability | Energy | Energy Meter / Submeter | SU-HVAC-014 | HVAC energy optimization review | LED/controls optimized | Visual Inspection | SUS-G-C-567 | Level 03 - Office Area | PHOTO-SUS-0567 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | FM Contractor |  | P2 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | .
Sustainability | Energy | Energy Meter / Submeter | SU-PMP-015 | Pump efficiency review | Schedules/setpoints | Visual Inspection | SUS-04-B-568 | Basement B1 - Plantroom |  | Photo | 4 | 80% | 2.86 | 2.288 | 3 | MEP Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Sustainability | Energy | Energy Meter / Submeter | SU-CLM-016 | Climate resilience considerations | VFD/curve match | Visual Inspection | SUS-04-A-569 | Roof - Mechanical Area | PHOTO-SUS-0569 | Photo | 2 | 40% | 2.86 | 1.144 | 3 | Main Contractor | CAPA-0163 | P1 | 22/08/2024 | Open | Non-compliance / degraded condition observed; corrective action required. Trend indicates aging components; prioritize within next maintenance cycle. | .
Sustainability | Energy | Energy Meter / Submeter | SU-DOC-017 | Sustainability documentation | Heat load management | Visual Inspection | SUS-01-B-570 | Basement B1 - Plantroom |  | Checklist | 4 | 80% | 2.86 | 2.288 | 3 | FM Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Sustainability | Energy | Energy Meter / Submeter | SU-TRN-018 | Staff awareness/training | Reports and records | Visual Inspection | SUS-05-A-571 | External - Service Yard | PHOTO-SUS-0571 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | MEP Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Housekeeping and labeling improvements required. | .
Sustainability | Energy | Energy Meter / Submeter | SU-RSK-019 | Risk classification | Records | Visual Inspection | SUS-05-B-572 | Basement B1 - Plantroom |  | Photo | 4 | 80% | 2.86 | 2.288 | 3 | FM Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Sustainability | Energy | Energy Meter / Submeter | SU-REC-020 | Corrective actions logged | P1–P4 | Visual Inspection | SUS-05-B-573 | Staircase Core | PHOTO-SUS-0573 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | FM Contractor | CAPA-0164 | P3 | 29/09/2024 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Sustainability | Energy | Energy Meter / Submeter | SU-SUM-021 | Sustainability summary | CAPA linked | Visual Inspection | SUS-B1-B-574 | Basement B1 - Plantroom | PHOTO-SUS-0574 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | MEP Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
Sustainability | Energy | Energy Meter / Submeter | SU-ESG-022 | ESG readiness review | Overall status | Visual Inspection | SUS-B1-A-575 | Level 02 - Office Area |  | Photo | 4 | 80% | 2.86 | 2.288 | 3 | FM Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Sustainability | Energy | Energy Meter / Submeter | SU-CAR-023 | Carbon footprint tracking (optional) | Reporting readiness | Visual Inspection | SUS-02-A-576 | Ground Floor - Lobby | PHOTO-SUS-0576 | Photo | 2 | 40% | 2.86 | 1.144 | 3 | FM Contractor | CAPA-0165 | P2 | 2024-05-09 | Open | Non-compliance / degraded condition observed; corrective action required. Preventive maintenance records incomplete; verify PM completion. | .
Sustainability | Energy | Energy Meter / Submeter | SU-WTR-024 | Water quality & reuse strategy | Baseline data | Visual Inspection | SUS-B1-A-577 | Level 03 - Office Area |  | Test Report | 4 | 80% | 2.86 | 2.288 | 3 | MEP Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Sustainability | Energy | Energy Meter / Submeter | SU-SMR-025 | Smart controls utilization | Plans | Visual Inspection | SUS-G-C-578 | Basement B1 - Plantroom |  | Photo | 4 | 80% | 2.86 | 2.288 | 3 | MEP Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Sustainability | Energy | Energy Meter / Submeter | SU-PRC-026 | Procurement sustainability criteria | BMS analytics | Visual Inspection | SUS-03-A-579 | Ground Floor - Lobby |  | Test Report | 4 | 80% | 2.86 | 2.288 | 3 | Main Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Sustainability | Energy | Energy Meter / Submeter | SU-MNT-027 | Maintenance sustainability | Applied | Visual Inspection | SUS-04-A-580 | Level 02 - Office Area | PHOTO-SUS-0580 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | Main Contractor | CAPA-0166 | P3 | 29/09/2024 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | .
Sustainability | Energy | Energy Meter / Submeter | SU-INS-028 | Envelope infiltration check | PM reduces waste | Visual Inspection | SUS-02-D-581 | Level 02 - Office Area | PHOTO-SUS-0581 | Photo | 2 | 40% | 2.86 | 1.144 | 3 | FM Contractor | CAPA-0167 | P2 | 2024-05-09 | Open | Non-compliance / degraded condition observed; corrective action required. Housekeeping and labeling improvements required. | .
Sustainability | Energy | Energy Meter / Submeter | SU-DRP-029 | Demand response readiness | Air leakage review | Visual Inspection | SUS-05-C-582 | Level 03 - Office Area | PHOTO-SUS-0582 | Photo | 2 | 40% | 2.86 | 1.144 | 3 | MEP Contractor |  | P2 |  | Closed | Non-compliance / degraded condition observed; corrective action required. Evidence captured; recommend rectification and re-test. | .
Sustainability | Energy | Energy Meter / Submeter | SU-BEN-030 | Benefits realization plan | Load shedding strategies | Visual Inspection | SUS-G-D-583 | Level 03 - Office Area |  | Checklist | 4 | 80% | 2.86 | 2.288 | 3 | MEP Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Sustainability | Energy | Energy Meter / Submeter | SU-LCC-031 | Life cycle costing input availability | Quantified | Visual Inspection | SUS-G-A-584 | Electrical Room - LV | PHOTO-SUS-0584 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | Main Contractor | CAPA-0168 | P2 | 2024-05-09 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Sustainability | Energy | Energy Meter / Submeter | SU-AUD-032 | Audit trail quality | Capex/opex | Visual Inspection | SUS-04-B-585 | Ground Floor - Lobby | PHOTO-SUS-0585 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | MEP Contractor | CAPA-0169 | P2 | 2024-05-09 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Housekeeping and labeling improvements required. | .
Sustainability | Energy | Energy Meter / Submeter | SU-ACC-033 | Data completeness for audits | Evidence | Visual Inspection | SUS-04-D-586 | Level 03 - Office Area | PHOTO-SUS-0586 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | FM Contractor |  | P2 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Sustainability | Energy | Energy Meter / Submeter | SU-KPI2-034 | Monthly KPI trend | Quality | Visual Inspection | SUS-02-C-587 | Level 01 - Office Area | PHOTO-SUS-0587 | Photo | 3 | 60% | 2.86 | 1.716 | 3 | FM Contractor | CAPA-0170 | P2 | 2024-05-09 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | .
Sustainability | Energy | Energy Meter / Submeter | SU-IMP-035 | Improvement roadmap | Tracked | Visual Inspection | SUS-05-A-588 | Electrical Room - LV | PHOTO-SUS-0588 | Photo | 2 | 40% | 2.86 | 1.144 | 3 | FM Contractor | CAPA-0171 | P2 | 2024-05-09 | Open | Non-compliance / degraded condition observed; corrective action required. Preventive maintenance records incomplete; verify PM completion. | .
Compliance_Documentation | Design | As-Built Drawings / O&M Manuals | CO-DOC-001 | As-built drawings completeness | Defined | Visual Inspection | GEN-05-D-589 | Level 02 - Office Area | PHOTO-COM-0589 | Photo | 3 | 60% | 2.61 | 1.566 | 3 | Specialist Vendor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | .
Compliance_Documentation | Design | As-Built Drawings / O&M Manuals | CO-OM-002 | O&M manuals completeness | Arch/Str/MEP present | Visual Inspection | GEN-05-A-590 | Parking - Basement |  | Photo | 4 | 80% | 2.61 | 2.088 | 3 | Specialist Vendor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Compliance_Documentation | Design | As-Built Drawings / O&M Manuals | CO-WAR-003 | Warranties & guarantees | Per system; indexed | Visual Inspection | GEN-02-D-591 | Level 01 - Office Area |  | Checklist | 4 | 80% | 2.61 | 2.088 | 3 | Main Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Compliance_Documentation | Design | As-Built Drawings / O&M Manuals | CO-TST-004 | Test reports availability | Valid; start dates defined | Visual Inspection | GEN-02-B-592 | Staircase Core | PHOTO-COM-0592 | Photo | 3 | 60% | 3.48 | 2.088 | 4 | MEP Contractor | CAPA-0172 | P2 | 2024-05-09 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Compliance_Documentation | Design | As-Built Drawings / O&M Manuals | CO-COM-005 | Commissioning documentation | Electrical/mechanical/plumbing | Visual Inspection | GEN-03-A-593 | Level 01 - Office Area | PHOTO-COM-0593 | Photo | 3 | 60% | 3.48 | 2.088 | 4 | FM Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Housekeeping and labeling improvements required. | .
Compliance_Documentation | Design | As-Built Drawings / O&M Manuals | CO-INS-006 | Inspection records & logs | Final, signed | Visual Inspection | GEN-02-C-594 | Basement B1 - Plantroom | PHOTO-COM-0594 | Photo | 3 | 60% | 2.61 | 1.566 | 3 | FM Contractor | CAPA-0173 | P2 | 2024-05-09 | Open | Condition acceptable but requires attention; minor deficiencies observed. Housekeeping and labeling improvements required. | .
Compliance_Documentation | Design | As-Built Drawings / O&M Manuals | CO-SBC-007 | SBC compliance review (relevant sections) | Complete | Visual Inspection | GEN-B1-C-595 | Basement B1 - Plantroom |  | Checklist | 4 | 80% | 4.35 | 3.48 | 5 | FM Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Compliance_Documentation | Design | As-Built Drawings / O&M Manuals | CO-ZON-008 | Zoning/as-built compliance | Checklist completed | Visual Inspection | GEN-02-D-596 | Roof - Mechanical Area | PHOTO-COM-0596 | Photo | 3 | 60% | 2.61 | 1.566 | 3 | MEP Contractor | CAPA-0174 | P2 | 2024-05-09 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Evidence captured; recommend rectification and re-test. | .
Compliance_Documentation | Design | As-Built Drawings / O&M Manuals | CO-MUN-009 | Municipality permits verification | No major variances | Visual Inspection | GEN-01-D-597 | Level 02 - Office Area |  | Checklist | 4 | 80% | 4.35 | 3.48 | 5 | FM Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Compliance_Documentation | Design | As-Built Drawings / O&M Manuals | CO-EXPRO-010 | EXPRO alignment matrix (if required) | Valid where applicable | Visual Inspection | GEN-03-D-598 | Level 02 - Office Area |  | Test Report | 4 | 80% | 2.61 | 2.088 | 3 | FM Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Compliance_Documentation | Design | As-Built Drawings / O&M Manuals | CO-SLA-011 | Contracts/SLA/LOA documentation | Mapped deliverables | Visual Inspection | GEN-05-A-599 | Level 03 - Office Area | PHOTO-COM-0599 | Photo | 3 | 60% | 2.61 | 1.566 | 3 | MEP Contractor |  | P2 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | .
Compliance_Documentation | Design | As-Built Drawings / O&M Manuals | CO-TRN-012 | Training records completeness | Current; measurable | Visual Inspection | GEN-01-D-600 | Staircase Core | PHOTO-COM-0600 | Photo | 3 | 60% | 2.61 | 1.566 | 3 | FM Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Compliance_Documentation | Design | As-Built Drawings / O&M Manuals | CO-SPR-013 | Spare parts lists & inventory | FM team trained | Visual Inspection | GEN-03-A-601 | Staircase Core | PHOTO-COM-0601 | Photo | 3 | 60% | 2.61 | 1.566 | 3 | FM Contractor | CAPA-0175 | P2 | 2024-05-09 | Open | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
Compliance_Documentation | Design | As-Built Drawings / O&M Manuals | CO-AST-014 | Asset register readiness | Delivered and verified | Visual Inspection | GEN-01-A-602 | Level 02 - Office Area | PHOTO-COM-0602 | Photo | 3 | 60% | 3.48 | 2.088 | 4 | Specialist Vendor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
Compliance_Documentation | Design | As-Built Drawings / O&M Manuals | CO-CMMS-015 | CAFM/CMMS setup readiness | IDs, attributes complete | Visual Inspection | GEN-G-C-603 | Electrical Room - LV | PHOTO-COM-0603 | Photo | 3 | 60% | 3.48 | 2.088 | 4 | FM Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | .
Compliance_Documentation | Design | As-Built Drawings / O&M Manuals | CO-DQ-016 | Asset data quality assessment | Configured | Visual Inspection | GEN-G-A-604 | Level 03 - Office Area | PHOTO-COM-0604 | Photo | 3 | 60% | 2.61 | 1.566 | 3 | FM Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
Compliance_Documentation | Design | As-Built Drawings / O&M Manuals | CO-QA-017 | Quality audit trail | Accuracy/completeness | Visual Inspection | GEN-01-C-605 | Ground Floor - Lobby |  | Checklist | 5 | 100% | 2.61 | 2.61 | 3 | FM Contractor |  | P4 |  | Closed | Inspected and found fully compliant; no observations noted. | .
Compliance_Documentation | Design | As-Built Drawings / O&M Manuals | CO-RSK-018 | Risk register availability | Signatures/version control | Visual Inspection | GEN-G-A-606 | External - Service Yard |  | Test Report | 4 | 80% | 2.61 | 2.088 | 3 | Main Contractor | CAPA-0176 | P3 | 29/09/2024 | In Progress | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Compliance_Documentation | Design | As-Built Drawings / O&M Manuals | CO-BCM-019 | BCM/continuity plans (non-fire) | Open risks logged | Visual Inspection | GEN-G-A-607 | Roof - Mechanical Area |  | Checklist | 4 | 80% | 2.61 | 2.088 | 3 | MEP Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Compliance_Documentation | Design | As-Built Drawings / O&M Manuals | CO-ENV-020 | Environmental compliance docs | Plans available | Visual Inspection | GEN-G-B-608 | Level 03 - Office Area | PHOTO-COM-0608 | Photo | 1 | 20% | 2.61 | 0.522 | 3 | FM Contractor | CAPA-0177 | P1 | 22/08/2024 | Open | Critical deficiency observed; immediate corrective action required to mitigate risk. Preventive maintenance records incomplete; verify PM completion. | .
Compliance_Documentation | Design | As-Built Drawings / O&M Manuals | CO-SEC-021 | Information security policies (if applicable) | Waste/water | Visual Inspection | GEN-01-B-609 | Roof - Mechanical Area | PHOTO-COM-0609 | Photo | 3 | 60% | 2.61 | 1.566 | 3 | MEP Contractor | CAPA-0178 | P2 | 2024-05-09 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Housekeeping and labeling improvements required. | .
Compliance_Documentation | Design | As-Built Drawings / O&M Manuals | CO-HSE-022 | HSE documentation (general) | In place | Visual Inspection | GEN-04-B-610 | Level 03 - Office Area | PHOTO-COM-0610 | Photo | 0 | 0% | 2.61 | 0 | 3 | Specialist Vendor |  | - |  | N/A | Not applicable for this building / scope. | .
Compliance_Documentation | Design | As-Built Drawings / O&M Manuals | CO-CHG-023 | Change control records | Training/records | Visual Inspection | GEN-05-A-611 | Staircase Core | PHOTO-COM-0611 | Photo | 3 | 60% | 2.61 | 1.566 | 3 | MEP Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | .
Compliance_Documentation | Design | As-Built Drawings / O&M Manuals | CO-ACC-024 | Access rights & admin controls | Tracked | Visual Inspection | GEN-01-A-612 | Level 02 - Office Area | PHOTO-COM-0612 | Photo | 0 | 0% | 2.61 | 0 | 3 | Main Contractor |  | - |  | N/A | Not applicable for this building / scope. | .
Compliance_Documentation | Design | As-Built Drawings / O&M Manuals | CO-RPT-025 | Third party reports | Documented | Visual Inspection | GEN-05-A-613 | Level 03 - Office Area |  | Photo | 4 | 80% | 2.61 | 2.088 | 3 | MEP Contractor |  | P3 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Compliance_Documentation | Design | As-Built Drawings / O&M Manuals | CO-INS2-026 | Insurance docs/latent defects (if any) | Available | Visual Inspection | GEN-05-B-614 | Level 03 - Office Area | PHOTO-COM-0614 | Photo | 3 | 60% | 2.61 | 1.566 | 3 | Specialist Vendor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Compliance_Documentation | Design | As-Built Drawings / O&M Manuals | CO-TRF-027 | Ownership/lease transfer docs | Verified | Visual Inspection | GEN-04-D-615 | Level 01 - Office Area | PHOTO-COM-0615 | Photo | 3 | 60% | 2.61 | 1.566 | 3 | Specialist Vendor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Housekeeping and labeling improvements required. | .
Compliance_Documentation | Design | As-Built Drawings / O&M Manuals | CO-REV-028 | Document revision control | Prepared | Visual Inspection | GEN-05-D-616 | Roof - Mechanical Area | PHOTO-COM-0616 | Photo | 3 | 60% | 2.61 | 1.566 | 3 | FM Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Housekeeping and labeling improvements required. | .
Compliance_Documentation | Design | As-Built Drawings / O&M Manuals | CO-RET-029 | Retention/handback conditions | Current revisions | Visual Inspection | GEN-01-B-617 | Parking - Basement | PHOTO-COM-0617 | Photo | 3 | 60% | 2.61 | 1.566 | 3 | FM Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Compliance_Documentation | Design | As-Built Drawings / O&M Manuals | CO-SUM-030 | Compliance summary | Defined | Visual Inspection | GEN-B1-D-618 | Level 02 - Office Area | PHOTO-COM-0618 | Photo | 3 | 60% | 2.61 | 1.566 | 3 | Main Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
Compliance_Documentation | Design | As-Built Drawings / O&M Manuals | CO-REC-031 | Corrective actions logged | Overall status | Visual Inspection | GEN-G-A-619 | Basement B1 - Plantroom | PHOTO-COM-0619 | Photo | 2 | 40% | 2.61 | 1.044 | 3 | FM Contractor | CAPA-0179 | P2 | 2024-05-09 | In Progress | Non-compliance / degraded condition observed; corrective action required. Preventive maintenance records incomplete; verify PM completion. | .
Compliance_Documentation | Design | As-Built Drawings / O&M Manuals | CO-PHT-032 | Evidence references | CAPA linked | Visual Inspection | GEN-01-D-620 | Parking - Basement | PHOTO-COM-0620 | Photo | 3 | 60% | 2.61 | 1.566 | 3 | FM Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Compliance_Documentation | Design | As-Built Drawings / O&M Manuals | CO-KPI-033 | Compliance KPI tracking | IDs | Visual Inspection | GEN-05-B-621 | Basement B1 - Plantroom |  | Checklist | 4 | 80% | 2.61 | 2.088 | 3 | MEP Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Compliance_Documentation | Design | As-Built Drawings / O&M Manuals | CO-AUD-034 | Audit readiness score | Trended | Visual Inspection | GEN-B1-A-622 | Electrical Room - LV | PHOTO-COM-0622 | Photo | 2 | 40% | 2.61 | 1.044 | 3 | MEP Contractor | CAPA-0180 | P2 | 2024-05-09 | Open | Non-compliance / degraded condition observed; corrective action required. Preventive maintenance records incomplete; verify PM completion. | .
Compliance_Documentation | Design | As-Built Drawings / O&M Manuals | CO-GOV-035 | Government-ready packaging | Calculated | Visual Inspection | GEN-B1-C-623 | Level 02 - Office Area | PHOTO-COM-0623 | Photo | 3 | 60% | 4.35 | 2.61 | 5 | FM Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
FM_Performance | Maintenance | Preventive / Corrective Maintenance | FM-PM-001 | Planned vs completed PM tasks | Format complete | Visual Inspection | GEN-01-D-624 | Roof - Mechanical Area | PHOTO-FM_-0624 | Photo | 2 | 40% | 3.54 | 1.416 | 4 | FM Contractor | CAPA-0181 | P2 | 2024-05-09 | Open | Non-compliance / degraded condition observed; corrective action required. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
FM_Performance | Maintenance | Preventive / Corrective Maintenance | FM-CM-002 | CM response & resolution time | >95% completion rate | Visual Inspection | GEN-G-A-625 | Roof - Mechanical Area |  | Test Report | 4 | 80% | 3.54 | 2.832 | 4 | Main Contractor |  | P3 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
FM_Performance | Maintenance | Preventive / Corrective Maintenance | FM-QLT-003 | Quality of workmanship post-PM/CM | Within SLA targets | Visual Inspection | GEN-05-C-626 | Roof - Mechanical Area |  | Checklist | 4 | 80% | 3.54 | 2.832 | 4 | Owner |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
FM_Performance | Maintenance | Preventive / Corrective Maintenance | FM-RPT-004 | FM KPI reporting timeliness & accuracy | Defect-free; signed off | Visual Inspection | GEN-01-D-627 | Level 01 - Office Area |  | Test Report | 4 | 80% | 2.65 | 2.12 | 3 | MEP Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
FM_Performance | Maintenance | Preventive / Corrective Maintenance | FM-INV-005 | Critical spare parts availability & stock | Submitted on time; data valid | Visual Inspection | GEN-G-D-628 | Parking - Basement | PHOTO-FM_-0628 | Photo | 2 | 40% | 2.65 | 1.06 | 3 | FM Contractor | CAPA-0182 | P2 | 2024-05-09 | Open | Non-compliance / degraded condition observed; corrective action required. Preventive maintenance records incomplete; verify PM completion. | .
FM_Performance | Maintenance | Preventive / Corrective Maintenance | FM-HKP-006 | Plantroom & facility housekeeping | Stock levels maintained | Visual Inspection | GEN-05-B-629 | Ground Floor - Lobby | PHOTO-FM_-0629 | Photo | 2 | 40% | 2.65 | 1.06 | 3 | MEP Contractor | CAPA-0183 | P1 | 22/08/2024 | In Progress | Non-compliance / degraded condition observed; corrective action required. Trend indicates aging components; prioritize within next maintenance cycle. | .
FM_Performance | Maintenance | Preventive / Corrective Maintenance | FM-TRN-007 | FM staff competency records | Clean; organized | Visual Inspection | GEN-03-A-630 | Staircase Core |  | Test Report | 4 | 80% | 2.65 | 2.12 | 3 | MEP Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
FM_Performance | Maintenance | Preventive / Corrective Maintenance | FM-CAFM-008 | CAFM/CMMS data completeness & usage | Up-to-date; role-specific | Visual Inspection | GEN-02-C-631 | External - Service Yard | PHOTO-FM_-0631 | Photo | 3 | 60% | 2.65 | 1.59 | 3 | FM Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
FM_Performance | Maintenance | Preventive / Corrective Maintenance | FM-VDR-009 | Vendor performance management | Tickets, assets updated | Visual Inspection | GEN-02-C-632 | External - Service Yard | PHOTO-FM_-0632 | Photo | 0 | 0% | 2.65 | 0 | 3 | Specialist Vendor |  | - |  | N/A | Not applicable for this building / scope. | .
FM_Performance | Maintenance | Preventive / Corrective Maintenance | FM-CST-010 | FM budget vs actual expenditure | Performance reviewed | Visual Inspection | GEN-01-B-633 | Level 02 - Office Area | PHOTO-FM_-0633 | Photo | 3 | 60% | 2.65 | 1.59 | 3 | Owner |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Housekeeping and labeling improvements required. | .
FM_Performance | Maintenance | Preventive / Corrective Maintenance | FM-EN-011 | Energy efficiency initiatives tracking | Within variance tolerance | Visual Inspection | GEN-G-B-634 | Parking - Basement |  | Photo | 4 | 80% | 2.65 | 2.12 | 3 | FM Contractor |  | P3 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
FM_Performance | Maintenance | Preventive / Corrective Maintenance | FM-RPT-012 | Repeat failure analysis & resolution | Savings verified | Visual Inspection | GEN-B1-C-635 | Electrical Room - LV | PHOTO-FM_-0635 | Photo | 3 | 60% | 2.65 | 1.59 | 3 | FM Contractor | CAPA-0184 | P2 | 2024-05-09 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Housekeeping and labeling improvements required. | .
FM_Performance | Maintenance | Preventive / Corrective Maintenance | FM-SAF-013 | Safety compliance during FM works | Root causes addressed | Visual Inspection | GEN-02-D-636 | Parking - Basement | PHOTO-FM_-0636 | Photo | 3 | 60% | 4.42 | 2.652 | 5 | Specialist Vendor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Evidence captured; recommend rectification and re-test. | .
FM_Performance | Maintenance | Preventive / Corrective Maintenance | FM-GOV-014 | Governance & audit compliance | Zero incidents; PPE used | Visual Inspection | GEN-04-D-637 | Ground Floor - Lobby | PHOTO-FM_-0637 | Photo | 3 | 60% | 2.65 | 1.59 | 3 | MEP Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
FM_Performance | Maintenance | Preventive / Corrective Maintenance | FM-LCC-015 | Lifecycle cost tracking for major assets | No major non-conformities | Visual Inspection | GEN-B1-D-638 | Level 03 - Office Area | PHOTO-FM_-0638 | Photo | 3 | 60% | 2.65 | 1.59 | 3 | FM Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Housekeeping and labeling improvements required. | .
FM_Performance | Maintenance | Preventive / Corrective Maintenance | FM-ENV-016 | Environmental compliance in FM ops | Data captured | Visual Inspection | GEN-03-A-639 | Basement B1 - Plantroom | PHOTO-FM_-0639 | Photo | 1 | 20% | 2.65 | 0.53 | 3 | FM Contractor | CAPA-0185 | P1 | 22/08/2024 | In Progress | Critical deficiency observed; immediate corrective action required to mitigate risk. Evidence captured; recommend rectification and re-test. | .
FM_Performance | Maintenance | Preventive / Corrective Maintenance | FM-DOC-017 | O&M documentation availability at point of use | Waste handled correctly | Visual Inspection | GEN-05-A-640 | Ground Floor - Lobby | PHOTO-FM_-0640 | Photo | 3 | 60% | 2.65 | 1.59 | 3 | FM Contractor | CAPA-0186 | P3 | 29/09/2024 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
FM_Performance | Maintenance | Preventive / Corrective Maintenance | FM-INT-018 | System integration for FM workflows | Easily accessible | Visual Inspection | GEN-04-C-641 | Roof - Mechanical Area | PHOTO-FM_-0641 | Photo | 2 | 40% | 2.65 | 1.06 | 3 | FM Contractor | CAPA-0187 | P1 | 22/08/2024 | In Progress | Non-compliance / degraded condition observed; corrective action required. Preventive maintenance records incomplete; verify PM completion. | .
FM_Performance | Maintenance | Preventive / Corrective Maintenance | FM-CON-019 | Contractor supervision & control | Automated where possible | Visual Inspection | GEN-04-C-642 | Ground Floor - Lobby | PHOTO-FM_-0642 | Photo | 3 | 60% | 2.65 | 1.59 | 3 | FM Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | .
FM_Performance | Maintenance | Preventive / Corrective Maintenance | FM-VAL-020 | Value added by FM activities | Site rules enforced | Visual Inspection | GEN-04-D-643 | External - Service Yard |  | Test Report | 5 | 100% | 2.65 | 2.65 | 3 | MEP Contractor |  | P4 |  | Verified | Inspected and found fully compliant; no observations noted. | .
FM_Performance | Maintenance | Preventive / Corrective Maintenance | FM-RES-021 | Resilience & business continuity support | Quantified benefits | Visual Inspection | GEN-B1-B-644 | Ground Floor - Lobby |  | Photo | 5 | 100% | 2.65 | 2.65 | 3 | FM Contractor |  | P4 |  | Verified | Inspected and found fully compliant; no observations noted. | .
FM_Performance | Maintenance | Preventive / Corrective Maintenance | FM-TEC-022 | Technical compliance with OEM guidelines | Tested plans | Visual Inspection | GEN-05-B-645 | Ground Floor - Lobby | PHOTO-FM_-0645 | Photo | 3 | 60% | 2.65 | 1.59 | 3 | MEP Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
FM_Performance | Maintenance | Preventive / Corrective Maintenance | FM-CUS-023 | Stakeholder satisfaction feedback | Followed | Visual Inspection | GEN-02-D-646 | Basement B1 - Plantroom |  | Checklist | 4 | 80% | 2.65 | 2.12 | 3 | Specialist Vendor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
FM_Performance | Maintenance | Preventive / Corrective Maintenance | FM-RSK-024 | Risk management in FM operations | Positive trends | Visual Inspection | GEN-02-D-647 | External - Service Yard | PHOTO-FM_-0647 | Photo | 3 | 60% | 2.65 | 1.59 | 3 | FM Contractor | CAPA-0188 | P3 | 29/09/2024 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Housekeeping and labeling improvements required. | .
FM_Performance | Maintenance | Preventive / Corrective Maintenance | FM-INN-025 | Innovation & continuous improvement | Risks identified & mitigated | Visual Inspection | GEN-03-A-648 | Parking - Basement | PHOTO-FM_-0648 | Photo | 2 | 40% | 2.65 | 1.06 | 3 | FM Contractor | CAPA-0189 | P1 | 22/08/2024 | In Progress | Non-compliance / degraded condition observed; corrective action required. Preventive maintenance records incomplete; verify PM completion. | .
FM_Performance | Maintenance | Preventive / Corrective Maintenance | FM-AST-026 | Asset condition & performance trending | Initiatives tracked | Visual Inspection | GEN-02-D-649 | Basement B1 - Plantroom |  | Photo | 4 | 80% | 2.65 | 2.12 | 3 | MEP Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
FM_Performance | Maintenance | Preventive / Corrective Maintenance | FM-COM-027 | Communication & coordination with other trades | Data used for decisions | Visual Inspection | GEN-G-C-650 | Parking - Basement | PHOTO-FM_-0650 | Photo | 2 | 40% | 2.65 | 1.06 | 3 | Main Contractor | CAPA-0190 | P2 | 2024-05-09 | In Progress | Non-compliance / degraded condition observed; corrective action required. Housekeeping and labeling improvements required. | .
FM_Performance | Maintenance | Preventive / Corrective Maintenance | FM-LEG-028 | Legal & regulatory awareness | Effective | Visual Inspection | GEN-04-A-651 | Electrical Room - LV |  | Photo | 4 | 80% | 4.42 | 3.536 | 5 | MEP Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
FM_Performance | Maintenance | Preventive / Corrective Maintenance | FM-DAT-029 | Data accuracy in asset registers | Compliant | Visual Inspection | GEN-B1-C-652 | Level 03 - Office Area | PHOTO-FM_-0652 | Photo | 1 | 20% | 2.65 | 0.53 | 3 | FM Contractor | CAPA-0191 | P1 | 22/08/2024 | Open | Critical deficiency observed; immediate corrective action required to mitigate risk. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
FM_Performance | Maintenance | Preventive / Corrective Maintenance | FM-SEC-030 | Security & access control during works | High confidence level | Visual Inspection | GEN-03-B-653 | Ground Floor - Lobby |  | Test Report | 5 | 100% | 2.65 | 2.65 | 3 | FM Contractor |  | P4 |  | Verified | Inspected and found fully compliant; no observations noted. | .
FM_Performance | Maintenance | Preventive / Corrective Maintenance | FM-OPT-031 | Operational efficiency metrics | Controlled | Visual Inspection | GEN-04-A-654 | Electrical Room - LV | PHOTO-FM_-0654 | Photo | 3 | 60% | 2.65 | 1.59 | 3 | Main Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Evidence captured; recommend rectification and re-test. | .
FM_Performance | Maintenance | Preventive / Corrective Maintenance | FM-SUS-032 | Sustainability integration in FM | Benchmarks met | Visual Inspection | GEN-03-A-655 | Level 01 - Office Area | PHOTO-FM_-0655 | Photo | 2 | 40% | 2.65 | 1.06 | 3 | Specialist Vendor | CAPA-0192 | P2 | 2024-05-09 | Open | Non-compliance / degraded condition observed; corrective action required. Housekeeping and labeling improvements required. | .
FM_Performance | Maintenance | Preventive / Corrective Maintenance | FM-AUD-033 | Internal audit results & actions | Goals supported | Visual Inspection | GEN-G-C-656 | Roof - Mechanical Area | PHOTO-FM_-0656 | Photo | 3 | 60% | 2.65 | 1.59 | 3 | Specialist Vendor | CAPA-0193 | P2 | 2024-05-09 | Open | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | .
FM_Performance | Maintenance | Preventive / Corrective Maintenance | FM-TTM-034 | Mean Time to Repair (MTTR) | Closed out | Visual Inspection | GEN-01-C-657 | Staircase Core |  | Photo | 4 | 80% | 3.54 | 2.832 | 4 | FM Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
FM_Performance | Maintenance | Preventive / Corrective Maintenance | FM-SUM-035 | Overall FM performance summary | Within target | Visual Inspection | GEN-05-D-658 | Parking - Basement | PHOTO-FM_-0658 | Photo | 3 | 60% | 2.65 | 1.59 | 3 | Specialist Vendor | CAPA-0194 | P2 | 2024-05-09 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Governance_Readiness | Integration | Fireâ€‘BMS / Fireâ€‘HVAC / Fireâ€‘Security / Emergency Power / Elevator Recall / SPOF | GR-FB-001 | Fire-BMS integration test | Meeting objectives | Visual Inspection | GEN-G-A-659 | Staircase Core | PHOTO-GOV-0659 | Photo | 3 | 60% | 3.4 | 2.04 | 5 | Main Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | .
Governance_Readiness | Integration | Fireâ€‘BMS / Fireâ€‘HVAC / Fireâ€‘Security / Emergency Power / Elevator Recall / SPOF | GR-FH-002 | Fire-HVAC smoke control test | Fire signals received by BMS; actions correct | Visual Inspection | GEN-03-A-660 | Staircase Core | PHOTO-GOV-0660 | Photo | 3 | 60% | 3.4 | 2.04 | 5 | MEP Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Housekeeping and labeling improvements required. | .
Governance_Readiness | Integration | Fireâ€‘BMS / Fireâ€‘HVAC / Fireâ€‘Security / Emergency Power / Elevator Recall / SPOF | GR-FS-003 | Fire-security release test | Smoke mode activates correctly | Visual Inspection | GEN-04-D-661 | Electrical Room - LV |  | Test Report | 4 | 80% | 3.4 | 2.72 | 5 | Specialist Vendor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Governance_Readiness | Integration | Fireâ€‘BMS / Fireâ€‘HVAC / Fireâ€‘Security / Emergency Power / Elevator Recall / SPOF | GR-EP-004 | Emergency power sequence test | Access doors unlock on fire signal | Visual Inspection | GEN-05-B-662 | Level 03 - Office Area | PHOTO-GOV-0662 | Photo | 3 | 60% | 2.72 | 1.632 | 4 | Main Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | .
Governance_Readiness | Integration | Fireâ€‘BMS / Fireâ€‘HVAC / Fireâ€‘Security / Emergency Power / Elevator Recall / SPOF | GR-ER-005 | Elevator recall integration | Critical loads transfer to backup | Visual Inspection | GEN-G-A-663 | Staircase Core | PHOTO-GOV-0663 | Photo | 3 | 60% | 2.72 | 1.632 | 4 | MEP Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
Governance_Readiness | Integration | Fireâ€‘BMS / Fireâ€‘HVAC / Fireâ€‘Security / Emergency Power / Elevator Recall / SPOF | GR-SP-006 | Single point of failure analysis | Elevators recall to designated floor | Visual Inspection | GEN-04-D-664 | Staircase Core | PHOTO-GOV-0664 | Photo | 0 | 0% | 2.72 | 0 | 4 | FM Contractor |  | - |  | N/A | Not applicable for this building / scope. | .
Governance_Readiness | Integration | Fireâ€‘BMS / Fireâ€‘HVAC / Fireâ€‘Security / Emergency Power / Elevator Recall / SPOF | GR-FM-007 | FM staff competency assessment | Critical SPOFs identified; mitigated | Visual Inspection | GEN-02-C-665 | External - Service Yard |  | Test Report | 4 | 80% | 2.72 | 2.176 | 4 | FM Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Governance_Readiness | Integration | Fireâ€‘BMS / Fireâ€‘HVAC / Fireâ€‘Security / Emergency Power / Elevator Recall / SPOF | GR-ER-008 | Emergency response plan verification | All roles competent; training complete | Visual Inspection | GEN-04-B-666 | Parking - Basement |  | Test Report | 4 | 80% | 2.72 | 2.176 | 4 | FM Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Governance_Readiness | Integration | Fireâ€‘BMS / Fireâ€‘HVAC / Fireâ€‘Security / Emergency Power / Elevator Recall / SPOF | GR-FD-009 | Fire drill execution | Plan complete; roles defined | Visual Inspection | GEN-B1-A-667 | Parking - Basement | PHOTO-GOV-0667 | Photo | 3 | 60% | 3.4 | 2.04 | 5 | Specialist Vendor | CAPA-0195 | P2 | 2024-05-09 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Evidence captured; recommend rectification and re-test. | .
Governance_Readiness | Integration | Fireâ€‘BMS / Fireâ€‘HVAC / Fireâ€‘Security / Emergency Power / Elevator Recall / SPOF | GR-FI-010 | First intervention equipment | Drills conducted; records available | Visual Inspection | GEN-05-C-668 | External - Service Yard |  | Checklist | 4 | 80% | 2.72 | 2.176 | 4 | MEP Contractor |  | P3 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Governance_Readiness | Integration | Fireâ€‘BMS / Fireâ€‘HVAC / Fireâ€‘Security / Emergency Power / Elevator Recall / SPOF | GR-CR-011 | Control room SOPs | Equipment available; staff trained | Visual Inspection | GEN-03-B-669 | Electrical Room - LV |  | Test Report | 5 | 100% | 2.72 | 2.72 | 4 | Specialist Vendor |  | P4 |  | Closed | Inspected and found fully compliant; no observations noted. | .
Governance_Readiness | Integration | Fireâ€‘BMS / Fireâ€‘HVAC / Fireâ€‘Security / Emergency Power / Elevator Recall / SPOF | GR-RU-012 | Remaining useful life assessment | Procedures documented; staff familiar | Visual Inspection | GEN-03-C-670 | Ground Floor - Lobby | PHOTO-GOV-0670 | Photo | 3 | 60% | 2.72 | 1.632 | 4 | MEP Contractor |  | P2 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Evidence captured; recommend rectification and re-test. | .
Governance_Readiness | Integration | Fireâ€‘BMS / Fireâ€‘HVAC / Fireâ€‘Security / Emergency Power / Elevator Recall / SPOF | GR-CM-013 | Asset criticality matrix | Major assets assessed; replacement plan | Visual Inspection | GEN-01-C-671 | Level 03 - Office Area | PHOTO-GOV-0671 | Photo | 3 | 60% | 2.72 | 1.632 | 4 | FM Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
Governance_Readiness | Integration | Fireâ€‘BMS / Fireâ€‘HVAC / Fireâ€‘Security / Emergency Power / Elevator Recall / SPOF | GR-RR-014 | Risk register completeness | Assets classified; maintenance aligned | Visual Inspection | GEN-01-B-672 | Level 01 - Office Area | PHOTO-GOV-0672 | Photo | 3 | 60% | 2.72 | 1.632 | 4 | FM Contractor | CAPA-0196 | P2 | 2024-05-09 | Open | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Governance_Readiness | Integration | Fireâ€‘BMS / Fireâ€‘HVAC / Fireâ€‘Security / Emergency Power / Elevator Recall / SPOF | GR-BC-015 | Business continuity plan | All major risks identified; mitigation plans | Visual Inspection | GEN-05-D-673 | Electrical Room - LV |  | Test Report | 4 | 80% | 3.4 | 2.72 | 5 | MEP Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Governance_Readiness | Integration | Fireâ€‘BMS / Fireâ€‘HVAC / Fireâ€‘Security / Emergency Power / Elevator Recall / SPOF | GR-DB-016 | Digital/BIM handover | BCP documented; tested | Visual Inspection | GEN-G-C-674 | Ground Floor - Lobby | PHOTO-GOV-0674 | Photo | 3 | 60% | 2.72 | 1.632 | 4 | Specialist Vendor | CAPA-0197 | P2 | 2024-05-09 | In Progress | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | .
Governance_Readiness | Integration | Fireâ€‘BMS / Fireâ€‘HVAC / Fireâ€‘Security / Emergency Power / Elevator Recall / SPOF | GR-AT-017 | Asset tagging completion | As-built BIM model delivered | Visual Inspection | GEN-05-B-675 | Basement B1 - Plantroom | PHOTO-GOV-0675 | Photo | 2 | 40% | 2.72 | 1.088 | 4 | Specialist Vendor | CAPA-0198 | P1 | 22/08/2024 | Open | Non-compliance / degraded condition observed; corrective action required. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Governance_Readiness | Integration | Fireâ€‘BMS / Fireâ€‘HVAC / Fireâ€‘Security / Emergency Power / Elevator Recall / SPOF | GR-LO-018 | Load shedding test | All critical assets tagged; database updated | Visual Inspection | GEN-05-D-676 | Staircase Core |  | Photo | 4 | 80% | 2.72 | 2.176 | 4 | Owner |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Governance_Readiness | Integration | Fireâ€‘BMS / Fireâ€‘HVAC / Fireâ€‘Security / Emergency Power / Elevator Recall / SPOF | GR-PR-019 | Pressurization test | Non-critical loads shed during emergency | Visual Inspection | GEN-B1-C-677 | Parking - Basement |  | Test Report | 4 | 80% | 3.4 | 2.72 | 5 | FM Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Governance_Readiness | Integration | Fireâ€‘BMS / Fireâ€‘HVAC / Fireâ€‘Security / Emergency Power / Elevator Recall / SPOF | GR-CCTV-020 | CCTV integration with fire | Stairwell pressurization works | Visual Inspection | GEN-02-C-678 | Ground Floor - Lobby | PHOTO-GOV-0678 | Photo | 3 | 60% | 3.4 | 2.04 | 5 | MEP Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Governance_Readiness | Integration | Fireâ€‘BMS / Fireâ€‘HVAC / Fireâ€‘Security / Emergency Power / Elevator Recall / SPOF | GR-FU-021 | Fuel supply verification | CCTV focuses on alarm location | Visual Inspection | GEN-04-B-679 | Basement B1 - Plantroom |  | Test Report | 4 | 80% | 2.72 | 2.176 | 4 | FM Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Governance_Readiness | Integration | Fireâ€‘BMS / Fireâ€‘HVAC / Fireâ€‘Security / Emergency Power / Elevator Recall / SPOF | GR-PH-022 | Phone communication test | Adequate fuel for generator runtime | Visual Inspection | GEN-01-C-680 | Parking - Basement |  | Photo | 4 | 80% | 2.72 | 2.176 | 4 | FM Contractor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Governance_Readiness | Integration | Fireâ€‘BMS / Fireâ€‘HVAC / Fireâ€‘Security / Emergency Power / Elevator Recall / SPOF | GR-DR-023 | Documented recovery procedures | Emergency phones operational | Visual Inspection | GEN-02-D-681 | Ground Floor - Lobby | PHOTO-GOV-0681 | Photo | 3 | 60% | 2.72 | 1.632 | 4 | FM Contractor |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Evidence captured; recommend rectification and re-test. | .
Governance_Readiness | Integration | Fireâ€‘BMS / Fireâ€‘HVAC / Fireâ€‘Security / Emergency Power / Elevator Recall / SPOF | GR-CE-024 | Certification verification | Recovery procedures for SPOFs exist | Visual Inspection | GEN-01-D-682 | Electrical Room - LV | PHOTO-GOV-0682 | Photo | 2 | 40% | 2.72 | 1.088 | 4 | FM Contractor | CAPA-0199 | P2 | 2024-05-09 | Open | Non-compliance / degraded condition observed; corrective action required. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Governance_Readiness | Integration | Fireâ€‘BMS / Fireâ€‘HVAC / Fireâ€‘Security / Emergency Power / Elevator Recall / SPOF | GR-CO-025 | Communication tree test | Required certifications valid | Visual Inspection | GEN-03-D-683 | Basement B1 - Plantroom |  | Photo | 4 | 80% | 2.72 | 2.176 | 4 | Specialist Vendor |  | P4 |  | Closed | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Governance_Readiness | Integration | Fireâ€‘BMS / Fireâ€‘HVAC / Fireâ€‘Security / Emergency Power / Elevator Recall / SPOF | GR-EV-026 | Evacuation time measurement | Emergency communications work | Visual Inspection | GEN-01-C-684 | Parking - Basement | PHOTO-GOV-0684 | Photo | 3 | 60% | 2.72 | 1.632 | 4 | FM Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
Governance_Readiness | Integration | Fireâ€‘BMS / Fireâ€‘HVAC / Fireâ€‘Security / Emergency Power / Elevator Recall / SPOF | GR-LO-027 | Location mapping | Evacuation within required time | Visual Inspection | GEN-04-A-685 | Level 01 - Office Area | PHOTO-GOV-0685 | Photo | 3 | 60% | 2.72 | 1.632 | 4 | FM Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | .
Governance_Readiness | Integration | Fireâ€‘BMS / Fireâ€‘HVAC / Fireâ€‘Security / Emergency Power / Elevator Recall / SPOF | GR-BA-028 | Backup control capability | Equipment locations mapped | Visual Inspection | GEN-04-C-686 | Electrical Room - LV | PHOTO-GOV-0686 | Photo | 3 | 60% | 2.72 | 1.632 | 4 | Main Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Housekeeping and labeling improvements required. | .
Governance_Readiness | Integration | Fireâ€‘BMS / Fireâ€‘HVAC / Fireâ€‘Security / Emergency Power / Elevator Recall / SPOF | GR-FO-029 | Financial forecasting | Alternative control location identified | Visual Inspection | GEN-03-D-687 | Basement B1 - Plantroom |  | Photo | 4 | 80% | 2.72 | 2.176 | 4 | MEP Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Governance_Readiness | Integration | Fireâ€‘BMS / Fireâ€‘HVAC / Fireâ€‘Security / Emergency Power / Elevator Recall / SPOF | GR-MT-030 | Maintenance strategy alignment | Budget for replacements projected | Visual Inspection | GEN-03-A-688 | Electrical Room - LV | PHOTO-GOV-0688 | Photo | 3 | 60% | 2.72 | 1.632 | 4 | Specialist Vendor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Governance_Readiness | Integration | Fireâ€‘BMS / Fireâ€‘HVAC / Fireâ€‘Security / Emergency Power / Elevator Recall / SPOF | GR-RE-031 | Review frequency | Maintenance matches criticality | Visual Inspection | GEN-G-D-689 | Basement B1 - Plantroom |  | Photo | 4 | 80% | 2.72 | 2.176 | 4 | FM Contractor |  | P4 |  | Verified | Inspected and found generally compliant; minor observations noted (no immediate impact). | .
Governance_Readiness | Integration | Fireâ€‘BMS / Fireâ€‘HVAC / Fireâ€‘Security / Emergency Power / Elevator Recall / SPOF | GR-TE-032 | BCP test results | Risks reviewed quarterly | Visual Inspection | GEN-05-B-690 | Level 02 - Office Area |  | Checklist | 5 | 100% | 2.72 | 2.72 | 4 | FM Contractor |  | P4 |  | Verified | Inspected and found fully compliant; no observations noted. | .
Governance_Readiness | Integration | Fireâ€‘BMS / Fireâ€‘HVAC / Fireâ€‘Security / Emergency Power / Elevator Recall / SPOF | GR-AC-033 | Access to digital data | Test conducted; gaps addressed | Visual Inspection | GEN-B1-C-691 | External - Service Yard | PHOTO-GOV-0691 | Photo | 3 | 60% | 2.72 | 1.632 | 4 | Owner |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | .
Governance_Readiness | Integration | Fireâ€‘BMS / Fireâ€‘HVAC / Fireâ€‘Security / Emergency Power / Elevator Recall / SPOF | GR-SC-034 | Scanning test | FM team can access/use digital assets | Visual Inspection | GEN-04-A-692 | Level 01 - Office Area | PHOTO-GOV-0692 | Photo | 3 | 60% | 2.72 | 1.632 | 4 | FM Contractor |  | P3 |  | Verified | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .
Governance_Readiness | Integration | Fireâ€‘BMS / Fireâ€‘HVAC / Fireâ€‘Security / Emergency Power / Elevator Recall / SPOF | GR-SU-035 | Summary of integration readiness | Asset tags scannable; link to data | Visual Inspection | GEN-04-D-693 | Basement B1 - Plantroom | PHOTO-GOV-0693 | Photo | 3 | 60% | 2.72 | 1.632 | 4 | Owner |  | P3 |  | Closed | Condition acceptable but requires attention; minor deficiencies observed. Housekeeping and labeling improvements required. | .
Governance_Readiness | Integration | Fireâ€‘BMS / Fireâ€‘HVAC / Fireâ€‘Security / Emergency Power / Elevator Recall / SPOF | GR-SU-035 | Summary of integration readiness | All critical integrations verified | Visual Inspection | GEN-02-C-694 | Staircase Core | PHOTO-GOV-0694 | Photo | 3 | 60% | 2.72 | 1.632 | 4 | FM Contractor | CAPA-0200 | P2 | 2024-05-09 | Open | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | .

## Test Register
Test ID | Test Name | System | Standard / Reference | Instrument | Locations / Sampling | Acceptance Criteria | Readings | Pass/Fail | Linked Item Codes | Evidence Ref | Witness | Date
TR-001 | Fire Alarm Cause & Effect Test | Fire_LifeSafety | NFPA 20/25 | Laptop + programming tool / panel access | Ground + typical floor | All devices report correctly; outputs match matrix; no faults | All zones OK; 1 device delay 2s | Pass | FL-CD-026, FL-SB-004 | TR-001-FIR | Client Rep | 2025-12-08
TR-002 | Smoke/Heat Detector Functional Test (sample) | Fire_LifeSafety | SBC 801 (Fire Code) | Test smoke / heat gun | Random sample (10%) | Alarm within manufacturer spec; address correct | Response 3–8s; addresses OK | Pass | FL-SB-004, FL-ZN-033, FL-PF-014 | TR-002-FIR | Client Rep | 2025-12-09
TR-003 | Manual Call Point Activation Test (sample) | Fire_LifeSafety | SBC 801 (Fire Code) | Key + panel access | Stair cores / exits (sample) | Alarm activates; correct location displayed | Activated OK; reset OK | Pass | FL-FS-027, FL-VE-005, FL-FD-016 | TR-003-FIR | Client Rep | 2025-12-10
TR-004 | Fire Pump Start & Pressure Test | Fire_LifeSafety | Civil Defense Requirements | Pressure gauge + flow meter | Basement pump room | Auto start; pressure within design; no abnormal vibration | Pressure 7.0 bar (design 7.5) | Need Attention | FL-JP-008, FL-FD-015 | TR-004-FIR | Specialist Vendor | 2025-12-11
TR-005 | Jockey Pump Auto Cut-in/out Test | Fire_LifeSafety | SBC 801 (Fire Code) | Pressure gauge | Basement pump room | Cuts-in/out within setpoints | Cut-in 6.6 bar; cut-out 7.2 bar | Pass | FL-CD-026, FL-SB-004, FL-FD-015, FL-MCP-003 | TR-005-FIR | Specialist Vendor | 2025-12-12
TR-006 | Sprinkler System Visual + Valve Position Check | Fire_LifeSafety | NFPA 72 | Checklist | Risers / control valves | Valves sealed open; gauges normal; no leaks | All OK; minor label missing | Pass | FL-FS-027, FL-HH-010, FL-DR-035 | TR-006-FIR | Client Rep | 2025-12-13
TR-007 | Hydrant/Hose Reel Flow Test (sample) | Fire_LifeSafety | NFPA 20/25 | Flow/pressure gauge | Typical floor + basement | Flow and pressure meet requirement; hose condition OK | Basement reel kink noted | Need Attention | FL-CA-012, FL-FP-007, FL-SE-013, FL-BI-024 | TR-007-FIR | Client Rep | 2025-12-14
TR-008 | Emergency Lighting Duration Test (sample) | Fire_LifeSafety | SBC 801 (Fire Code) | Lux meter + timer | Egress routes (sample) | ≥ 90 min autonomy; adequate illumination | Autonomy 95 min; lux OK | Pass | FL-SB-004, FL-PF-014, FL-SC-032, FL-DR-035 | TR-008-FIR | MEP Supervisor | 2025-12-15
TR-009 | Exit Sign Visibility Check | Fire_LifeSafety | NFPA 20/25 | Visual inspection | All exits | Signs illuminated and visible | 2 signs dim in corridor | Need Attention | FL-MP-030, FL-BI-024, FL-ES-020 | TR-009-FIR | FM Manager | 2025-12-16
TR-010 | Civil Defense Certificates Review | Fire_LifeSafety | NFPA 72 | Document review | Document set | Valid certificates provided | Some certificates not available on site | Need Attention | FL-FD-016, FL-BT-006, FL-ES-020, FL-RS-034 | TR-010-FIR | MEP Supervisor | 2025-12-17
TR-011 | Main Feeder Insulation Resistance (Megger) | Electrical | IEEE Std 43 (IR) | Insulation resistance tester (5kV) | Main feeders (sample) | IR meets acceptance; stable readings | ≥500 MΩ measured | Pass | EL-FST-019, EL-ELX-010, EL-BMS-025, EL-LD-003 | TR-011-ELE | Client Rep | 2025-12-18
TR-012 | Earth Resistance Test | Electrical | SBC 401 (Electrical) | Earth tester | Earthing pit(s) / main bar | ≤ 1–2 Ω (project spec) | 0.9 Ω measured | Pass | EL-COM-030, EL-MTR-015 | TR-012-ELE | FM Manager | 2025-12-19
TR-013 | Protection Relay / Breaker Trip Test (sample) | Electrical | SBC 401 (Electrical) | Secondary injection kit | MSB incomers / critical feeders | Trips within settings; coordination OK | Trip time within curve | Pass | EL-CT-002, EL-OPS-027, EL-LD-003 | TR-013-ELE | Specialist Vendor | 2025-12-20
TR-014 | Power Quality (THD / imbalance) spot-check | Electrical | IEEE Std 43 (IR) | Power quality analyzer | MSB + 2 DBs | THD within project limits; imbalance within limit | THD 3–5%; imbalance <2% | Pass | EL-SPR-028, EL-LBL-016, EL-BMS-025 | TR-014-ELE | MEP Supervisor | 2025-12-21
TR-015 | Thermal Scan of LV Boards | Electrical | SBC 401 (Electrical) | Thermal camera | MSB/DBs (critical) | No hotspots >20°C above ambient | No abnormal hotspots | Pass | EL-QA-032, EL-LD-003 | TR-015-ELE | PMC Engineer | 2025-12-22
TR-016 | RCD/ELCB Trip Time Test (sample) | Electrical | SBC 401 (Electrical) | RCD tester | Wet areas + pantry circuits | Trip time within standard | Trip 22–35 ms | Pass | EL-OPS-027, EL-LD-003, EL-CT-002, EL-TRN-029 | TR-016-ELE | PMC Engineer | 2025-12-23
TR-017 | Internal Lighting Lux Level Test (sample) | Electrical | SBC 401 (Electrical) | Lux meter | Open office areas (sample) | Lux meets design | 350–520 lux | Pass | EL-SPR-028, EL-CLR-017, EL-ENV-034 | TR-017-ELE | PMC Engineer | 2025-12-24
TR-018 | External Lighting Coverage Check | Electrical | SBC 401/501 | Lux meter | Parking perimeter | Uniformity and average lux meet spec | Some dark spots | Need Attention | EL-LBL-016, EL-PQ-006, EL-BMS-025 | TR-018-ELE | Client Rep | 2025-12-25
TR-019 | Electrical As-built Drawings Review | Electrical | SBC 401 (Electrical) | Document review | Document set | As-builts complete and updated | Some revisions missing | Need Attention | EL-TH-007, EL-COM-030 | TR-019-ELE | PMC Engineer | 2025-12-26
TR-020 | Generator Auto-start & Run Test | Emergency_Power | NFPA 110 | Load bank (if available) / ATS simulation | Generator room | Starts within 10s; stable operation | Start 7s; stable | Pass | EL-ATS-013, EL-EML-022, EL-RES-035, EL-UPS-011 | TR-020-EME | Client Rep | 2025-12-27
TR-021 | ATS Transfer Test | Emergency_Power | NFPA 110 | ATS test procedure | Main ATS | Transfer within spec; no alarms | Transfer smooth 8s | Pass | EL-EML-022, EL-UPS-011, EL-GEN-012 | TR-021-EME | MEP Supervisor | 2025-12-28
TR-022 | UPS Autonomy Test (spot) | Emergency_Power | Manufacturer O&M | Load simulator / UPS monitor | UPS serving IT | Autonomy meets design | 18 min (design 20) | Need Attention | EL-EML-022, EL-UPS-011, EL-RES-035 | TR-022-EME | MEP Supervisor | 2025-12-29
TR-023 | Emergency DB Functional Check | Emergency_Power | NFPA 110 | Multimeter + checklist | Emergency DB(s) | Feeds labeled; breakers OK | Labels partially missing | Need Attention | EL-GEN-012, EL-ATS-013 | TR-023-EME | FM Manager | 2025-12-30
TR-024 | COP/EER Performance Spot-check | Mechanical_HVAC | ASHRAE 55 | BMS trends + portable meters | Chiller plant | Performance within tolerance | COP slightly low | Need Attention | ME-ALM-015, ME-COP-001, ME-TRN-032, ME-VAV-012 | TR-024-MEC | PMC Engineer | 2025-12-31
TR-025 | Airflow Balancing (TAB) Verification | Mechanical_HVAC | CIBSE Guide B | Anemometer + hood | Selected AHUs/VAVs | Within ±10% of design | Within ±8% | Pass | ME-DCT-010, ME-MNT-027 | TR-025-MEC | Specialist Vendor | 2026-01-01
TR-026 | Ventilation Effectiveness / CO₂ Check | Mechanical_HVAC | CIBSE Guide B | CO₂ meter | Meeting rooms (sample) | CO₂ < 1000 ppm under typical load | 650–950 ppm | Pass | ME-EXP-021, ME-FCU-009, ME-CLN-033, ME-NV-004 | TR-026-MEC | MEP Supervisor | 2026-01-02
TR-027 | Noise & Vibration Test | Mechanical_HVAC | TAB Report / O&M | Sound level meter | Server room + plant area | Within specified limits | Slightly high in server room | Need Attention | ME-FIR-026, ME-PU-007, ME-TST-031 | TR-027-MEC | MEP Supervisor | 2026-01-03
TR-028 | CHW/CW Pump Duty Point Check | Mechanical_HVAC | ASHRAE 62.1 | Clamp meter + pressure gauges | Pump room | Operating near duty point | Within range | Pass | ME-CH-005, ME-CTRL-014 | TR-028-MEC | MEP Supervisor | 2026-01-04
TR-029 | AHU Condition & Drainage Check | Mechanical_HVAC | ASHRAE 55 | Visual inspection | AHU rooms | Filters/coils clean; drain pans clear | Filters dusty; cleaning required | Need Attention | ME-WTR-022, ME-NV-004 | TR-029-MEC | Client Rep | 2026-01-05
TR-030 | Fire/Smoke Damper Interface Test (sample) | Mechanical_HVAC | ASHRAE 62.1 | Functional test | Selected dampers | Closes on alarm; feedback to BMS | 1 damper feedback missing | Need Attention | ME-DCT-010, ME-SNS-035, ME-PU-007, ME-ECN-024 | TR-030-MEC | Specialist Vendor | 2026-01-06
TR-031 | BMS Sequences Verification (HVAC) | Mechanical_HVAC | ASHRAE 62.1 | BMS workstation | Selected zones | Sequences match OPR; alarms configured | Schedules need optimization | Need Attention | ME-CTRL-014, ME-PRS-025 | TR-031-MEC | FM Manager | 2026-01-07
TR-032 | Water Pressure Test (spot) | Plumbing_Water | Hydrostatic Test Procedure | Pressure gauge | Upper floors (sample) | Pressure within range | Low at upper floors | Need Attention | PL-PRS-023, PL-HMR-024, PL-SAN-031 | TR-032-PLU | Client Rep | 2026-01-08
TR-033 | Booster Pump Auto Duty/Standby Test | Plumbing_Water | SBC Plumbing Code | Checklist + gauges | Pump room | Duty/standby alternation works; stable pressure | Auto alternation OK | Pass | PL-TST-030, PL-SAN-031, PL-GW-020 | TR-033-PLU | Client Rep | 2026-01-09
TR-034 | Leak Inspection - Wet Areas | Plumbing_Water | SBC Plumbing Code | Visual inspection | Toilets/pantries (sample) | No leaks; traps intact | Minor seepage under one basin | Need Attention | PL-INS-022, PL-MH-017 | TR-034-PLU | MEP Supervisor | 2026-01-10
TR-035 | Backflow Preventer Verification | Plumbing_Water | Hydrostatic Test Procedure | Checklist | Main incoming | Installed and labeled; test port accessible | OK | Pass | PL-RSK-034, PL-FLW-002 | TR-035-PLU | FM Manager | 2026-01-11
TR-036 | Elevator Functional Test + Ride Quality | Vertical_Transportation | SASO / Civil Defense | Elevator test tools | All cars (sample) | Smooth operation; leveling within tolerance | OK | Pass | VT-TC-010, VT-BL-035, VT-EC-002 | TR-036-VER | Specialist Vendor | 2026-01-12
TR-037 | Elevator Certificate Review | Vertical_Transportation | EN 81 | Document review | Certificate file | Valid certificates available | Valid | Pass | VT-BS-006, VT-IC-017, VT-GT-034, VT-BL-024 | TR-037-VER | FM Manager | 2026-01-13
TR-038 | BMS Point-to-Point Test (sample) | BMS_Controls | BACnet / BMS O&M | BMS workstation | Critical points (sample) | Points match field; correct scaling | Some points mis-labeled | Need Attention | BM-KP-035, BM-PT-033 | TR-038-BMS | PMC Engineer | 2026-01-14
TR-039 | Alarm Management & Trending Review | BMS_Controls | Point-to-Point Checklists | BMS workstation | Alarms/trends | Alarms configured; trends available | Trend database gaps | Need Attention | BM-HI-013, BM-UA-016 | TR-039-BMS | MEP Supervisor | 2026-01-15
TR-040 | Thermal Scan of LV Boards | Electrical | IEC 60364 | Thermal camera | Basement + roof plantrooms | No hotspots >20°C above ambient | No abnormal hotspots | Pass | EL-IR-001, EL-TST-031, EL-LX-009, EL-GND-020 | TR-040-ELE | PMC Engineer | 2026-01-16
TR-041 | Protection Relay / Breaker Trip Test (sample) | Electrical | IEEE Std 43 (IR) | Secondary injection kit | Basement + roof plantrooms | Trips within settings; coordination OK | Trip time within curve | Need Attention | EL-LBL-016, EL-LD-003, EL-RCD-008 | TR-041-ELE | Client Rep | 2026-01-17
TR-042 | Thermal Scan of LV Boards | Electrical | SBC 401 (Electrical) | Thermal camera | Random sample (5%) | No hotspots >20°C above ambient | No abnormal hotspots | Pass | EL-GND-020, EL-BMS-025 | TR-042-ELE | Specialist Vendor | 2026-01-18
TR-043 | Fire Alarm Cause & Effect Test | Fire_LifeSafety | Civil Defense Requirements | Laptop + programming tool / panel access | Critical areas only | All devices report correctly; outputs match matrix; no faults | All zones OK; 1 device delay 2s | Need Attention | FL-JP-008, FL-HS-025 | TR-043-FIR | FM Manager | 2026-01-19
TR-044 | BMS Sequences Verification (HVAC) | Mechanical_HVAC | ASHRAE 55 | BMS workstation | Basement + roof plantrooms | Sequences match OPR; alarms configured | Schedules need optimization | Need Attention | ME-CT-006, ME-FIR-026, ME-DOC-030 | TR-044-MEC | MEP Supervisor | 2026-01-20
TR-045 | Sprinkler System Visual + Valve Position Check | Fire_LifeSafety | NFPA 72 | Checklist | Random sample (5%) | Valves sealed open; gauges normal; no leaks | All OK; minor label missing | Pass | FL-HH-010, FL-MP-030 | TR-045-FIR | FM Manager | 2026-01-21
TR-046 | Thermal Scan of LV Boards | Electrical | SBC 401 (Electrical) | Thermal camera | Critical areas only | No hotspots >20°C above ambient | No abnormal hotspots | Pass | EL-PRF-023, EL-PR-005, EL-IR-001, EL-TST-031 | TR-046-ELE | Client Rep | 2026-01-22
TR-047 | Leak Inspection - Wet Areas | Plumbing_Water | Hydrostatic Test Procedure | Visual inspection | Random sample (5%) | No leaks; traps intact | Minor seepage under one basin | Pass | PL-BFP-014, PL-FLW-002 | TR-047-PLU | PMC Engineer | 2026-01-23
TR-048 | Power Quality (THD / imbalance) spot-check | Electrical | IEEE Std 43 (IR) | Power quality analyzer | Random sample (5%) | THD within project limits; imbalance within limit | THD 3–5%; imbalance <2% | Need Attention | EL-LX-009, EL-PRF-023, EL-EXB-018 | TR-048-ELE | FM Manager | 2026-01-24
TR-049 | Fire Pump Start & Pressure Test | Fire_LifeSafety | NFPA 20/25 | Pressure gauge + flow meter | Basement + roof plantrooms | Auto start; pressure within design; no abnormal vibration | Pressure 7.0 bar (design 7.5) | Need Attention | FL-RS-034, FL-FS-027, FL-ZN-033, FL-SS-009 | TR-049-FIR | Specialist Vendor | 2026-01-25
TR-050 | Civil Defense Certificates Review | Fire_LifeSafety | SBC 801 (Fire Code) | Document review | Basement + roof plantrooms | Valid certificates provided | Some certificates not available on site | Pass | FL-CP-001, FL-HH-010, FL-CA-012, FL-FI-031 | TR-050-FIR | Specialist Vendor | 2026-01-26
TR-051 | Leak Inspection - Wet Areas | Plumbing_Water | SBC Plumbing Code | Visual inspection | Random sample (5%) | No leaks; traps intact | Minor seepage under one basin | Pass | PL-RSK-034, PL-SAN-031, PL-DIS-007, PL-LK-004 | TR-051-PLU | FM Manager | 2026-01-27
TR-052 | Protection Relay / Breaker Trip Test (sample) | Electrical | IEEE Std 43 (IR) | Secondary injection kit | MSB incomers / critical feeders | Trips within settings; coordination OK | Trip time within curve | Pass | EL-FST-019, EL-PRF-023, EL-IR-001, EL-COM-030 | TR-052-ELE | Client Rep | 2026-01-28
TR-053 | AHU Condition & Drainage Check | Mechanical_HVAC | CIBSE Guide B | Visual inspection | Random sample (5%) | Filters/coils clean; drain pans clear | Filters dusty; cleaning required | Need Attention | ME-ACC-029, ME-CLN-033, ME-SNS-035 | TR-053-MEC | MEP Supervisor | 2026-01-29
TR-054 | Booster Pump Auto Duty/Standby Test | Plumbing_Water | SBC Plumbing Code | Checklist + gauges | Critical areas only | Duty/standby alternation works; stable pressure | Auto alternation OK | Need Attention | PL-DOC-029, PL-MIC-009 | TR-054-PLU | MEP Supervisor | 2026-01-30
TR-055 | Emergency Lighting Duration Test (sample) | Fire_LifeSafety | Civil Defense Requirements | Lux meter + timer | Basement + roof plantrooms | ≥ 90 min autonomy; adequate illumination | Autonomy 95 min; lux OK | Pass | FL-FD-016, FL-TC-028 | TR-055-FIR | Client Rep | 2026-01-31
TR-056 | Power Quality (THD / imbalance) spot-check | Electrical | IEEE Std 43 (IR) | Power quality analyzer | MSB + 2 DBs | THD within project limits; imbalance within limit | THD 3–5%; imbalance <2% | Pass | EL-IRN-026, EL-OPS-027, EL-LBL-016, EL-PR-005 | TR-056-ELE | PMC Engineer | 2026-02-01
TR-057 | Exit Sign Visibility Check | Fire_LifeSafety | Civil Defense Requirements | Visual inspection | Random sample (5%) | Signs illuminated and visible | 2 signs dim in corridor | Need Attention | FL-CD-026, FL-SC-032 | TR-057-FIR | FM Manager | 2026-02-02
TR-058 | Fire Alarm Cause & Effect Test | Fire_LifeSafety | NFPA 72 | Laptop + programming tool / panel access | Random sample (5%) | All devices report correctly; outputs match matrix; no faults | All zones OK; 1 device delay 2s | Need Attention | FL-ZN-033, FL-CD-026, FL-ER-022 | TR-058-FIR | MEP Supervisor | 2026-02-03
TR-059 | Protection Relay / Breaker Trip Test (sample) | Electrical | IEEE Std 43 (IR) | Secondary injection kit | Critical areas only | Trips within settings; coordination OK | Trip time within curve | Pass | EL-LBL-016, EL-IR-001, EL-MTR-015, EL-PRF-023 | TR-059-ELE | MEP Supervisor | 2026-02-04
TR-060 | AHU Condition & Drainage Check | Mechanical_HVAC | ASHRAE 62.1 | Visual inspection | Basement + roof plantrooms | Filters/coils clean; drain pans clear | Filters dusty; cleaning required | Pass | ME-LK-019, ME-CLN-033, ME-CH-005, ME-AHU-008 | TR-060-MEC | FM Manager | 2026-02-05
TR-061 | Exit Sign Visibility Check | Fire_LifeSafety | SBC 801 (Fire Code) | Visual inspection | Random sample (5%) | Signs illuminated and visible | 2 signs dim in corridor | Pass | FL-MCP-003, FL-CA-012, FL-FS-018 | TR-061-FIR | FM Manager | 2026-02-06
TR-062 | AHU Condition & Drainage Check | Mechanical_HVAC | SBC Mechanical | Visual inspection | Critical areas only | Filters/coils clean; drain pans clear | Filters dusty; cleaning required | Pass | ME-SNS-035, ME-CLN-033 | TR-062-MEC | Specialist Vendor | 2026-02-07
TR-063 | Water Pressure Test (spot) | Plumbing_Water | Hydrostatic Test Procedure | Pressure gauge | Critical areas only | Pressure within range | Low at upper floors | Pass | PL-LK-004, PL-REC-012, PL-ACC-028 | TR-063-PLU | Client Rep | 2026-02-08
TR-064 | External Lighting Coverage Check | Electrical | SBC 401/501 | Lux meter | Parking perimeter | Uniformity and average lux meet spec | Some dark spots | Pass | EL-BMS-025, EL-SAF-033 | TR-064-ELE | FM Manager | 2026-02-09
TR-065 | Exit Sign Visibility Check | Fire_LifeSafety | NFPA 20/25 | Visual inspection | All exits | Signs illuminated and visible | 2 signs dim in corridor | Pass | FL-ER-022, FL-FS-027 | TR-065-FIR | PMC Engineer | 2026-02-10
TR-066 | Internal Lighting Lux Level Test (sample) | Electrical | SBC 401/501 | Lux meter | Random sample (5%) | Lux meets design | 350–520 lux | Pass | EL-LX-009, EL-CT-002 | TR-066-ELE | FM Manager | 2026-02-11
TR-067 | Ventilation Effectiveness / CO₂ Check | Mechanical_HVAC | CIBSE Guide B | CO₂ meter | Critical areas only | CO₂ < 1000 ppm under typical load | 650–950 ppm | Need Attention | ME-LK-019, ME-ACC-029 | TR-067-MEC | Specialist Vendor | 2026-02-12
TR-068 | Emergency DB Functional Check | Emergency_Power | IEC 62040 (UPS) | Multimeter + checklist | Critical areas only | Feeds labeled; breakers OK | Labels partially missing | Pass | EL-GEN-012, EL-RES-035, EL-EML-022 | TR-068-EME | Specialist Vendor | 2026-02-13
TR-069 | Airflow Balancing (TAB) Verification | Mechanical_HVAC | TAB Report / O&M | Anemometer + hood | Basement + roof plantrooms | Within ±10% of design | Within ±8% | Pass | ME-PU-007, ME-SPR-028, ME-TRN-032 | TR-069-MEC | Specialist Vendor | 2026-02-14
TR-070 | Leak Inspection - Wet Areas | Plumbing_Water | Hydrostatic Test Procedure | Visual inspection | Critical areas only | No leaks; traps intact | Minor seepage under one basin | Need Attention | PL-PMP-015, PL-INS-022 | TR-070-PLU | FM Manager | 2026-02-15
TR-071 | External Lighting Coverage Check | Electrical | SBC 401 (Electrical) | Lux meter | Critical areas only | Uniformity and average lux meet spec | Some dark spots | Pass | EL-IR-001, EL-LD-003 | TR-071-ELE | PMC Engineer | 2026-02-16
TR-072 | Power Quality (THD / imbalance) spot-check | Electrical | IEC 60364 | Power quality analyzer | MSB + 2 DBs | THD within project limits; imbalance within limit | THD 3–5%; imbalance <2% | Pass | EL-QA-032, EL-CLR-017, EL-SAF-033, EL-SKT-021 | TR-072-ELE | PMC Engineer | 2026-02-17
TR-073 | Water Pressure Test (spot) | Plumbing_Water | Hydrostatic Test Procedure | Pressure gauge | Critical areas only | Pressure within range | Low at upper floors | Pass | PL-REC-012, PL-TMV-011, PL-CLN-018 | TR-073-PLU | MEP Supervisor | 2026-02-18
TR-074 | Fire Alarm Cause & Effect Test | Fire_LifeSafety | NFPA 20/25 | Laptop + programming tool / panel access | Critical areas only | All devices report correctly; outputs match matrix; no faults | All zones OK; 1 device delay 2s | Pass | FL-CB-021, FL-FD-016, FL-MCP-003, FL-ES-020 | TR-074-FIR | FM Manager | 2026-02-19
TR-075 | Thermal Scan of LV Boards | Electrical | IEC 60364 | Thermal camera | Critical areas only | No hotspots >20°C above ambient | No abnormal hotspots | Pass | EL-LD-003, EL-GND-020, EL-LX-009 | TR-075-ELE | Specialist Vendor | 2026-02-20
TR-076 | Ventilation Effectiveness / CO₂ Check | Mechanical_HVAC | ASHRAE 55 | CO₂ meter | Meeting rooms (sample) | CO₂ < 1000 ppm under typical load | 650–950 ppm | Pass | ME-CT-006, ME-DCT-010, ME-FIR-026 | TR-076-MEC | Specialist Vendor | 2026-02-21
TR-077 | Sprinkler System Visual + Valve Position Check | Fire_LifeSafety | Civil Defense Requirements | Checklist | Risers / control valves | Valves sealed open; gauges normal; no leaks | All OK; minor label missing | Pass | FL-FD-015, FL-BT-006, FL-RS-034 | TR-077-FIR | FM Manager | 2026-02-22
TR-078 | Sprinkler System Visual + Valve Position Check | Fire_LifeSafety | Civil Defense Requirements | Checklist | Critical areas only | Valves sealed open; gauges normal; no leaks | All OK; minor label missing | Need Attention | FL-HH-010, FL-EL-019, FL-MCP-003 | TR-078-FIR | Specialist Vendor | 2026-02-23
TR-079 | Emergency Lighting Duration Test (sample) | Fire_LifeSafety | NFPA 72 | Lux meter + timer | Basement + roof plantrooms | ≥ 90 min autonomy; adequate illumination | Autonomy 95 min; lux OK | Need Attention | FL-FD-015, FL-BT-006, FL-DT-002, FL-MCP-003 | TR-079-FIR | FM Manager | 2026-02-24
TR-080 | Leak Inspection - Wet Areas | Plumbing_Water | SBC Plumbing Code | Visual inspection | Basement + roof plantrooms | No leaks; traps intact | Minor seepage under one basin | Pass | PL-LK-004, PL-FLW-002, PL-RES-035, PL-DRN-016 | TR-080-PLU | MEP Supervisor | 2026-02-25

## CAPA Register
Corrective and Preventive Action (CAPA) ID | Priority | System | Item Code | Finding | Required Action | Responsibility | Due Date | Estimated Cost | Status | Verification Evidence
CAPA-0001 | P2 | Fire_LifeSafety | FL-MCP-003 | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | Submit missing certificates and update compliance records. | Specialist Vendor | 05/09/2024 | SAR 22,500 | Open
CAPA-0002 | P2 | Fire_LifeSafety | FL-SB-004 | Condition acceptable but requires attention; minor deficiencies observed. Evidence captured; recommend rectification and re-test. | Submit missing certificates and update compliance records. | Specialist Vendor | 05/09/2024 | SAR 24,000 | Open
CAPA-0003 | P2 | Fire_LifeSafety | FL-VE-005 | Condition acceptable but requires attention; minor deficiencies observed. Evidence captured; recommend rectification and re-test. | Replace faulty device and update fire alarm panel programming. | Specialist Vendor | 05/09/2024 | SAR 13,500 | Open
CAPA-0004 | P1 | Fire_LifeSafety | FL-BT-006 | Critical deficiency observed; immediate corrective action required to mitigate risk. Trend indicates aging components; prioritize within next maintenance cycle. | Submit missing certificates and update compliance records. | Specialist Vendor | 22/08/2024 | SAR 59,000 | Open
CAPA-0005 | P1 | Fire_LifeSafety | FL-JP-008 | Non-compliance / degraded condition observed; corrective action required. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | Replace faulty device and update fire alarm panel programming. | MEP Contractor | 22/08/2024 | SAR 26,000 | Open
CAPA-0006 | P2 | Fire_LifeSafety | FL-SS-009 | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | Submit missing certificates and update compliance records. | FM Contractor | 05/09/2024 | SAR 17,500 | Open
CAPA-0007 | P1 | Fire_LifeSafety | FL-HH-010 | Critical deficiency observed; immediate corrective action required to mitigate risk. Preventive maintenance records incomplete; verify PM completion. | Replace faulty device and update fire alarm panel programming. | Specialist Vendor | 22/08/2024 | SAR 25,500 | Open
CAPA-0008 | P1 | Fire_LifeSafety | FL-PF-014 | Non-compliance / degraded condition observed; corrective action required. Evidence captured; recommend rectification and re-test. | Rectify defect and re-test system in coordination with Civil Defense requirements. | FM Contractor | 22/08/2024 | SAR 58,000 | Open
CAPA-0009 | P1 | Fire_LifeSafety | FL-FC-017 | Non-compliance / degraded condition observed; corrective action required. Evidence captured; recommend rectification and re-test. | Submit missing certificates and update compliance records. | MEP Contractor | 22/08/2024 | SAR 48,500 | Open
CAPA-0010 | P1 | Fire_LifeSafety | FL-FS-018 | Non-compliance / degraded condition observed; corrective action required. Preventive maintenance records incomplete; verify PM completion. | Replace faulty device and update fire alarm panel programming. | MEP Contractor | 22/08/2024 | SAR 59,500 | Open
CAPA-0011 | P2 | Fire_LifeSafety | FL-CB-021 | Condition acceptable but requires attention; minor deficiencies observed. Evidence captured; recommend rectification and re-test. | Rectify defect and re-test system in coordination with Civil Defense requirements. | MEP Contractor | 05/09/2024 | SAR 24,500 | Open
CAPA-0012 | P2 | Fire_LifeSafety | FL-AC-023 | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | Rectify defect and re-test system in coordination with Civil Defense requirements. | Specialist Vendor | 05/09/2024 | SAR 9,500 | Open
CAPA-0013 | P2 | Fire_LifeSafety | FL-BI-024 | Condition acceptable but requires attention; minor deficiencies observed. Evidence captured; recommend rectification and re-test. | Rectify defect and re-test system in coordination with Civil Defense requirements. | MEP Contractor | 05/09/2024 | SAR 14,000 | Open
CAPA-0014 | P1 | Fire_LifeSafety | FL-HS-025 | Non-compliance / degraded condition observed; corrective action required. Evidence captured; recommend rectification and re-test. | Replace faulty device and update fire alarm panel programming. | MEP Contractor | 22/08/2024 | SAR 58,000 | Open
CAPA-0015 | P2 | Fire_LifeSafety | FL-FS-027 | Condition acceptable but requires attention; minor deficiencies observed. Housekeeping and labeling improvements required. | Rectify defect and re-test system in coordination with Civil Defense requirements. | FM Contractor | 05/09/2024 | SAR 22,500 | Open
CAPA-0016 | P1 | Fire_LifeSafety | FL-TC-028 | Critical deficiency observed; immediate corrective action required to mitigate risk. Housekeeping and labeling improvements required. | Repair/adjust equipment and conduct functional re-test. | FM Contractor | 22/08/2024 | SAR 48,000 | Open
CAPA-0017 | P3 | Fire_LifeSafety | FL-OP-029 | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | Replace faulty device and update fire alarm panel programming. | Specialist Vendor | 29/09/2024 | SAR 6,000 | In Progress
CAPA-0018 | P1 | Fire_LifeSafety | FL-FI-031 | Critical deficiency observed; immediate corrective action required to mitigate risk. Housekeeping and labeling improvements required. | Replace faulty device and update fire alarm panel programming. | FM Contractor | 22/08/2024 | SAR 38,500 | Open
CAPA-0019 | P2 | Fire_LifeSafety | FL-ZN-033 | Non-compliance / degraded condition observed; corrective action required. Housekeeping and labeling improvements required. | Submit missing certificates and update compliance records. | FM Contractor | 05/09/2024 | SAR 8,000 | Open
CAPA-0020 | P2 | Fire_LifeSafety | FL-RS-034 | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | Rectify defect and re-test system in coordination with Civil Defense requirements. | MEP Contractor | 05/09/2024 | SAR 22,500 | Open
CAPA-0021 | P1 | Electrical | EL-IR-001 | Non-compliance / degraded condition observed; corrective action required. Preventive maintenance records incomplete; verify PM completion. | Replace defective component and conduct functional testing. | MEP Contractor | 22/08/2024 | SAR 37,500 | Open
CAPA-0022 | P3 | Electrical | EL-ER-004 | Inspected and found generally compliant; minor observations noted (no immediate impact). | Improve labeling/housekeeping and update as-built drawings. | Specialist Vendor | 29/09/2024 | SAR 6,000 | In Progress
CAPA-0023 | P2 | Electrical | EL-PQ-006 | Condition acceptable but requires attention; minor deficiencies observed. Preventive maintenance records incomplete; verify PM completion. | Repair identified issue and re-test electrical performance. | Owner | 05/09/2024 | SAR 16,000 | Open
CAPA-0024 | P1 | Electrical | EL-RCD-008 | Non-compliance / degraded condition observed; corrective action required. Evidence captured; recommend rectification and re-test. | Improve labeling/housekeeping and update as-built drawings. | FM Contractor | 22/08/2024 | SAR 34,500 | Open
CAPA-0025 | P2 | Electrical | EL-LBL-016 | Condition acceptable but requires attention; minor deficiencies observed. Housekeeping and labeling improvements required. | Replace defective component and conduct functional testing. | FM Contractor | 05/09/2024 | SAR 17,000 | Open
CAPA-0026 | P2 | Electrical | EL-OPS-027 | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | Repair identified issue and re-test electrical performance. | MEP Contractor | 05/09/2024 | SAR 10,000 | Open
CAPA-0027 | P1 | Electrical | EL-TRN-029 | Non-compliance / degraded condition observed; corrective action required. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | Replace defective component and conduct functional testing. | FM Contractor | 22/08/2024 | SAR 26,500 | Open
CAPA-0028 | P1 | Electrical | EL-QA-032 | Non-compliance / degraded condition observed; corrective action required. Trend indicates aging components; prioritize within next maintenance cycle. | Improve labeling/housekeeping and update as-built drawings. | FM Contractor | 22/08/2024 | SAR 26,500 | Open
CAPA-0029 | P2 | Electrical | EL-ENV-034 | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | Improve labeling/housekeeping and update as-built drawings. | Specialist Vendor | 05/09/2024 | SAR 20,000 | Open
CAPA-0030 | P2 | Mechanical_HVAC | ME-NV-004 | Non-compliance / degraded condition observed; corrective action required. Housekeeping and labeling improvements required. | Carry out corrective maintenance and re-test system performance. | Main Contractor | 05/09/2024 | SAR 8,500 | Open
CAPA-0031 | P1 | Mechanical_HVAC | ME-CH-005 | Non-compliance / degraded condition observed; corrective action required. Preventive maintenance records incomplete; verify PM completion. | Adjust balancing and verify against design criteria. | Main Contractor | 22/08/2024 | SAR 20,000 | Open
CAPA-0032 | P1 | Mechanical_HVAC | ME-PU-007 | Critical deficiency observed; immediate corrective action required to mitigate risk. Preventive maintenance records incomplete; verify PM completion. | Carry out corrective maintenance and re-test system performance. | Owner | 22/08/2024 | SAR 33,000 | Open
CAPA-0033 | P2 | Mechanical_HVAC | ME-FCU-009 | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | Carry out corrective maintenance and re-test system performance. | Owner | 05/09/2024 | SAR 23,000 | Open
CAPA-0034 | P2 | Mechanical_HVAC | ME-VAV-012 | Non-compliance / degraded condition observed; corrective action required. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | Clean/replace components and optimize control sequences. | MEP Contractor | 05/09/2024 | SAR 20,500 | Open
CAPA-0035 | P2 | Mechanical_HVAC | ME-DIF-013 | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | Clean/replace components and optimize control sequences. | Main Contractor | 05/09/2024 | SAR 10,000 | Open
CAPA-0036 | P2 | Mechanical_HVAC | ME-CTRL-014 | Condition acceptable but requires attention; minor deficiencies observed. Observed corrosion/dust accumulation due to harsh environment; clean and protect. | Adjust balancing and verify against design criteria. | MEP Contractor | 05/09/2024 | SAR 14,000 | Open
CAPA-0037 | P3 | Mechanical_HVAC | ME-ALM-015 | Condition acceptable but requires attention; minor deficiencies observed. Trend indicates aging components; prioritize within next maintenance cycle. | Adjust balancing and verify against design criteria. | Main Contractor | 29/09/2024 | SAR 4,000 | In Progress
CAPA-0038 | P2 | Mechanical_HVAC | ME-REF-016 | Non-compliance / degraded condition observed; corrective action required. Evidence captured; recommend rectification and re-test. | Clean/replace components and optimize control sequences. | MEP Contractor | 05/09/2024 | SAR 10,500 | Open
CAPA-0039 | P2 | Mechanical_HVAC | ME-INS-017 | Non-compliance / degraded condition observed; corrective action required. Trend indicates aging components; prioritize within next maintenance cycle. | Clean/replace components and optimize control sequences. | Specialist Vendor | 05/09/2024 | SAR 18,500 | Open
CAPA-0040 | P1 | Mechanical_HVAC | ME-LK-019 | Non-compliance / degraded condition observed; corrective action required. Housekeeping and labeling improvements required. | Carry out corrective maintenance and re-test system performance. | Owner | 22/08/2024 | SAR 46,000 | Open
CAPA-0041 | P1 | Mechanical_HVAC | ME-EXP-021 | Non-compliance / degraded condition observed; corrective action required. Housekeeping and labeling improvements required. | Carry out corrective maintenance and re-test system performance. | Main Contractor | 22/08/2024 | SAR 28,500 | Open
CAPA-0042 | P1 | Mechanical_HVAC | ME-ACC-029 | Non-compliance / degraded condition observed; corrective action required. Evidence captured; recommend rectification and re-test. | Carry out corrective maintenance and re-test system performance. | MEP Contractor | 22/08/2024 | SAR 26,000 | Open
CAPA-0043 | P2 | Mechanical_HVAC | ME-DOC-030 | Non-compliance / degraded condition observed; corrective action required. Preventive maintenance records incomplete; verify PM completion. | Carry out corrective maintenance and re-test system performance. | FM Contractor | 05/09/2024 | SAR 9,500 | Open
CAPA-0044 | P2 | Mechanical_HVAC | ME-TST-031 | Non-compliance / degraded condition observed; corrective action required. Housekeeping and labeling improvements required. | Clean/replace components and optimize control sequences. | MEP Contractor | 05/09/2024 | SAR 23,500 | Open
CAPA-0045 | P1 | Mechanical_HVAC | ME-CLN-033 | Non-compliance / degraded condition observed; corrective action required. Trend indicates aging components; prioritize within next maintenance cycle. | Carry out corrective maintenance and re-test system performance. | Main Contractor | 22/08/2024 | SAR 55,500 | Open